## Live
|  |  | BSC |  |  |  |  | DCUSA |  |  |  |  | IGT UNC |  |  |  |  | REC |  |  |  |  | SEC |  |  |  |  | UNC |  |  |  |  | DIP | DTSA | CUSC | Grid Code | SQSS | STC | Distribution Code
Change Title | Lead Code | Other Codes impacts and number | Mod Number | IWA | W/G | DMR | FMR | DCP Number | IWA & TT | Report | Consult | Vote | Mod No | IWA | W/G | DMR | FMR | CP No | CPP | IAR | PCR | FCR | Mod No. | I.A. & F.I.A. | W/G Report | Consultation | FMR | Mod No | IWA | WGR | DMR | FMR | CP No | CP No | Mod No | Mod No | Mod No | Mod No | Mod No | Comment | Planned implementation date | Central System Impacted | Authority Determined | Comment archive
DP206 Allowing Generators to apply for Export MPANs | SEC | REC - tbc, BSC - tbc DCUSA - tbc | tbc | 2023-10-08 | 23/2/2024 |  |  | tbc | [9 empty] | tbc |  |  |  |  | MP206 | [16 empty] | 18/09/26 remains on hold. Seeking to ascertain next steps / requirements post R0207 implementation. 13/08/26 - REC Change R0207 approved, being implemented Nov 26 02/08/26 - Remains on hold. Seeking further info from Proposer to progress. 18 May 26 - 206 on hold pending outcome REC R0207 20/04/26 - remains on hold pending R207 02/02/26 - REC R0207 that has been sighted as a 206 dependency - on hold until outcome of R0207 known 12.01.26 - remains on hold 31.10.25 Change remains on hold 26.09.25 - Change on Hold. 10.09.25 - change on hold, pending discussion at Change Sub Committee, September 2025. (related change R207 not expected until mid 2026, Proposal to place on hold. 16.06.25 - SECAS seeking clarity from proposer on next steps 28 Feb 25 - the proposer notes that in withdrawing BSCP459 mod, they don’t consider the matter as closed/resolved, and will return to it, should R0207 not solve the problem they see. R0207 is on hold pending MHHS albeit charging issues are being progressed. SECAS determining next steps. 29 Jan 25 - Following withdrawal of BSC P459, awaiting confirmation from Proposer if he wants to continue with the mod. | tbc | tbc | No
ON HOLD - R0095 - Changes to allow DNOs to reinstate disconnect MPANs | REC | BSC - tbc, DCUSA - tbc, SEC - tbc | tbc |  |  |  |  | tbc | [9 empty] | R0095 | 2023-09-20 | 2023-09-20 | 2024-02-02 |  | tbc | [16 empty] | 30/05/24 - change on hold as part of MHHS system freeze 18/04/24 - need feedback from other codes to help look at business case for change, particularly the settlements impact Potential impact on DCUSA and BSC, needs further development, will check what happens in Gas, may be just DCUSA issue if Elec only |  | CSS, ERDS, EES, DIP | tbc
R0216 - REC Changes to tie in with DCP419 | REC | REC - I0216, BSC - n/a | [5 empty] | DCP419 | 2023-03-15 | 2023-06-14 | 2023-10-05 | tbd | [5 empty] | R0216 | 2024-11-05 | [20 empty] | 21/09/26 - DCP419 expected to be withdrawn 18/05/26 - still no updates from Proposer 02/02/26 - no updates from DCUSA proposer currently 16/01/26 - Rejection received from Ofgem for 216, confirmation on what is happening with DCP419 required 11/09/25 - MEP recommended rejection, with authority for decision 21/07/25 - at consultation, closing 08/08. Final vote expecting to be Sept MEP before Authority referral 16/06/25 - Legal text finalised. Now with performance assurance for check on any additional requirements. Next step will be presentation to MEP before being issued for consultation. 19/05/25 - REC change includes all legal text. Decision required on the need for DCUSA change. REC legal text currently out for legal review. 01/04/25 - RFI responses reviewed. Also discussions help with Ofgem and REC. Ofgem confirmed obligations are only set out in RIG and DNOs can lobby to amend these annually so justification for either solution is unclear. 03/02/25 - RFI issued and responses due 21/03/25 13/02/25 - joint REC / DCUSA RFI to be issued asking industry to pick a preferred option between app / website and flow. REC recommending app 20/01/25 - DCP419 working group to meet early Feb. Confirmed no SEC impact 02/12/24 - REC drawing up plans for non DTN solutions. 04/11/24 - I0216 is going to Change Issues Group to discuss flow and Schedule 14 options 16/09 - SEC monitoring potential impacts. Do not expect SEC Changes but if a market solution required their could be DCC system changes or SEC changes needed. 05/08/24 - REC to attend next working group. REC also to flag expected impacts to CoMCoP and Schedule 14. 17/06/24 - ElectraLink to confirm REC impact. New DCUSA Data Flow. MEM questioned whether there is a REC Impact? Meeting 15/11/23 will give an update on whether REC Change is required. | n/a | DTN | Yes
P441 - Complex Site Classes Creation | BSC | REC - I0268, DCUSA DCP424 | P441 | 2021-07-14 | 2023-09-11 |  |  | DCP 424 | [9 empty] | R0133 - withdrawn I0268 | 2023-07-07 | 2023-07-07 | [19 empty] | 21/09/26 - R0268 issued for consultation. Closes 03/10/26 07/09/26 - BSC and DCUSA now do need to align implementation, discussions ongoing as to what the proposed implementation date could be. No way to identify if an MPAN is a Complex Site - if this is a flag within EES, will need to progressed by REC 03/09/26 - REC send back received, just waiting for this to be publicly published and then will open a new consultation on the implementation date. REC plan to not put a specific date and just say "the same date as P441 with authority decision being received a minimum of 1 week in advance of implementation" to prevent any further send backs 13/08/26 - DCUSA/BSC/REC call with Ofgem - now thinking Ofgem consultation not required, but want to make decision on all 3 at the same time. REC can implement in Nov if decision received post 05 Oct only if Authority direct us to do so. 03/08/26 - DCUSA work group required to review second consultation responses, likely not making August Panel. DCUSA implementation going to need 6-12 month lead time due to IT changes, but no impact if delayed later than BSC/REC implementation. Chris Day from BSC attending DCUSA work groups. Potential for Ofgem to delay BSC/REC implementation, BSC meeting with Ofgem regarding. Ofgem still likely looking to consult, but no update on expected date. 15/06/26 - DCUSA second consultation out, expecting to be at July panel for approval and then to Authority 18/05/26 - DCP424 should be tracking for November, so theoretically all 3 change will be in same release. Potential for an Ofgem consultation to be issued on their minded to position in July. 16/04/26 - decision expected 05 October 2026 12/03/26 - R0268 approved by MEP and with Authority, P441 Approved by BSC Panel 02/03/26 - no change to planned final vote 12/01/26 - final vote delayed from Jan 26 to Mar 26 - DCUSA change may go later 31/10/25 - R0268 consultation open, closing 14/11/25 17/10/25- REC Proposal Plan published, review at Change Panel on 21/10/25. Assuming approval, consultation will be opened on 24/10/25 03/10/25 - Jenny has confirmed REC legal text is up to date. Earliest the REC can be at consultation is 24/10/25 (ending 14/11/25) - contingent on confirmation of BSC Final Vote date being received by 10/10/25 so we can align our plan. 18/08/25 - CB taken action to chase Jenny to confirm REC legal text is still correct or if any updates needed from more recent BSC work groups. REC cannot proceed to consultation without this confirmation 04/08/25 - DCP 424 Working Group have recently met and received update from Elexon at the meeting on 24 July 2025 and another meeting is due to be held on 08 August 2025 01/08/25 REC consequential issue I0268 raised 02/06/25 - still in Assessment procedure - 11th workgroup held on Tuesday 18 March 2025 01/04/25 - Elexon to confirm DCUSA impact as slides for March working group mention DUoS - https://www.elexon.co.uk/bsc/documents/change/modifications/p401-p450/p441-workgroup-meeting-11-slides/ 17/06/24 - ACTION - Elexon to confirm current status and update dates if required. 13/06/24 - REC CP withdrawn due to lack of solution. Needs new CP once REC requirements are understood. AP attending next workgroup meeting on Tuesday to discuss REC impacts, BSC to keep REC impacts in mind when drafting solution - could be an impact on DCUSA depending on where the solution lands, one option may have DCUSA impact due to DUOS impacts - update to CCSG at April 2023 meeting, DCUSA Rep aware of change and potential impacts . 9/10 6 months contingency added to plan for Ofgem information exercise. May revise timescales when more information available. DCUSA Plan needs to be updated on website, but plan pulled for voting. | 26/06/2026 (if decision received by 25/05) or 06/11/26 (if decision received by 05/10) TBD | tbc | Yes
I0175 - Introducing a Reasonable Endeavours Scheme within the REC | REC | Watching brief only | [15 empty] | I0175 | [21 empty] | 13/08/26 - post implementation review of R0173 required before I0175 can progress 21/07/25 - with RECCo to discuss TIG feedback and next steps 30/05/24 - theft change. No expected cross code impact |  | n/a | Yes
I0186 - Non dual-fuel Gas PSR customer | REC | UNC - tbc, iGT - tbc | [10 empty] | tbc |  |  |  |  | I0186 | 2024-07-23 | 2024-08-06 | [7 empty] | tbc | [11 empty] | 21/09/26 - proposer is reassessing their options 02/06/25 - REC in discussion with the proposer on a sandbox. 24/04/25 - discussions ongoing with main industry flow providers. 27/06/24 - initial conversation with Xoserve suggests there will be impact |  | tbc | No
0890 - Addition of Consumption Adjustment and Updated Meter Readings to initiate an AQ Calculation Month | UNC | IGT- none | [25 empty] | 0890 |  | 20/03/24 | 21/03/24 | 16/04/25 | [7 empty] | 27/03:- Indicative and unconfirmed im+A8+AO9 | 2026-11-01 | CDSP | Yes
0894/A - Facilitating Biomethane entry into the GDN by exporting methane from the GDN into the NTS via Compression | UNC | IGT- none | [25 empty] | 0894 |  | 20/02/25 | 21/02/25 | 20/03/25 | [7 empty] | 03/07/06: Decision date revised to TBC 11/06: decision date revised to 30 June 26 29/05 No decision yet as of 17:00 14/05: decision date revised to 29/05 27/03:- Authority Estimated Date of Decision 30-Apr-26 16/01: Mod and Alternate assessed at Dec 25 UNC Panel - now awaiting Authority Decision 17/10: 25 Day Consultation instructed for final Dec UNC Panel consideration 03/10: Workgroup extended to Report to October UNC Panel 04/07: Workgroup extended to Sept 2025 reporting date with new Alternate raised in June 29/05: Reporting to July 25 UNC Panel. 07/04: Update provided to CCSG - Reporting to May 25 UNC Panel. 11/11: Reporting to February 2025 UNC Panel - Cross Code Impact tbc | tbc | CDSP | Yes
0900 - Amendment to the Gas Quality NTS Entry Specification at Biomethane System Entry Points | UNC | iGT - no impact | [25 empty] | 0900 |  | TBC | TBC | TBC | [7 empty] | 18/05/2026 - still awaiting authority decision - still TBD 29/05: Panel recommended implementation; now awaiting Authority decision 07/04: Update provided to CCSG - Consultation complete, FMR reporting to April UNC Panel. 11/11: New Modification - consideration at November 2024 UNC Panel | tbc | None | Yes
0903 - The Introduction of a Single NTS Capacity Reference Price | UNC | iGT - no impact | [25 empty] | 0903 | [11 empty] | 27/03:- Authority Estimated Decision date 14 December 2026 17/10: Panel did not recommend implementation - now awaiting Authority decision (Dec 26?) 03/10: Consultation completed ahead of October UNC Panel Decision 04/08: Consultation commenced 18/07 and runs through to 02/10 17/07: Reported to Panel today and Consumers impact highlighted, going to Consultation for October Panel Decision 29/05: Reporting to July Panel. 07/04: Update provided to CCSG - reporting to July 25 UNC Panel | tbc | None | Yes
0908S - Removal of DNO meter reading obligations resulting from non-provision of a Valid Meter Reading | UNC | iGT UNC 177 | [10 empty] | IGT 177 | [14 empty] | 0908 | [11 empty] | 17/04/26 Apr UNC Panel confirmed Self Governance and directed to implement - now awaiting implementation date instruction 27/03 Consultation closed - Final Modification report for 16 April UNC Panel Decision 27/02 Workgroup Reported to Feb UNC Panel and Modification is out for consultation, closing on 27 March 2026 01/12 - Workgroup reporting extended from December to February 2026 15/09 - IGT177 has been approved, pending appeal window closing 21/08: Reporting extended to 19 December UNC Panel 29/05: Update provided to CCSG - reporting to September 25 UNC Panel 19/05: New IGT Mod submitted to take current must read provisions and drop them into IGT UNS to ringfence them and keep them from being removed via a UNC Mod. 07/04: Update provided to CCSG - reporting to September 25 UNC Panel | tbc | CDSP | Yes
0909S - Refining the Class 2 Individual Valid Meter Reading Requirement Performance Measures | UNC | IGT UNC - no impact | [10 empty] | tbc | [14 empty] | 0909S | [11 empty] | 31/07/26: Implementation date now anticipated to be later in the year 17/04:- Current Anticipated Implementation in July 2026 27/02 Feb 26 UNC Panel Directed this Modification be implemented 13/02: Consultation closed, Final Modification Report produced ahead of Feb 26 UNC Panel Decision 16/01; Reported to Dec 25 UNC Panel now at Consultation until 06 Feb 2026 03/10: Workgroup extended to report to December 2025 UNC Panel 01/07: Assessed at June UNC Panel and assigned to Workgroup (Dist) reporting back 18 Sept 2025. IGT UNC Impact thought likely - should be automatically implemented under IGT UNC due to cross reference, to keep an eye on 12/06: New Proposal Received for June UNC Panel Consideration | After related CDSP System works delivery - potentially July 2026 | CDSP | No
0911S - Amendment to DSC to introduce Shipper Assurance Audit (ISAE) | UNC | iGT - no impact | [25 empty] | 0911S | [11 empty] | 17/04 Awaiting implementation date instruction - anticipated long lead time on this one 27/02 Feb 26 UNC Panel Directed this Modification be implemented 13/02: Consultation closed, Final Modification Report produced ahead of Feb 26 UNC Panel Decision 16/01; Reported to Dec 25 UNC Panel now at Consultation until 06 Feb 2026 03/10: Workgroup extended to report to December 2025 UNC Panel 01/07: Assessed at June UNC Panel and assigned to Workgroup (Dist) reporting back 18 Sept 2025. IGT UNC Impact thought likely - should be automatically implemented under IGT UNC due to cross reference, to keep an eye on 12/06: New Proposal Received for June UNC Panel Consideration 13/02: Consultation closed, Final Modification Report produced ahead of Feb 26 UNC Panel Decision 16/01 Reported to Jan 26 UNC Panel and issued to Consultation, closing 05 Feb 2026 21/08: Workgroup reporting extended to Dec 2025 UNC Panel 01/07: Assessed at June UNC Panel and assigned to Workgroup (Gov) reporting back 18 Sept 2025, No Cross Code Impacts thought to exist at this stage 09/06: New Proposal Received for June UNC Panel Consideration | Potentially after Appeal Window closes when direction given | None | No
0914S Refining the Class 3 EUC1 read submission rules introduced through Modification 0700 | UNC | IGT UNC - no impact | [25 empty] | 0914S | [11 empty] | Workgroup extended to report to December 2026 Panel 29/05 - Workgroup period extended to September 2026 by May UNC Panel 18/05/16 - IGT UNC impact removed as is no longer renumbering any clauses 27/02 ; Feb 26 UNC Panel agreed to extend the Workgroup reporting date to June 2026 16/02: IGT UNC impact due to re-numbering or IGTUNC will point to the wrong clause 01/12: Workgroup reporting extended from December to March 2026 Sept UNC Panel allocated to Distribution Workgroup to report to Dec UNC Panel | No earlier than Project Trident implementation | CDSP | No
0915 Debt Relief Scheme Payments (DRSP) | UNC | IGT UNC - no impact | [25 empty] | 915 | [11 empty] | 16/01: Jan UNC Panel Recommended implementation - now with Authority 01/12: Workgroup extension until 18 December approved in Nov UNC Panel Sept UNC Panel allocated to Distribution Workgroup to report to Nov UNC Panel | six months lead time required for CDSP development and DNO charging statement alterations | CDSP | Yes
0916 Reform of Capacity Arrangements at Interconnection Points | UNC | IGT UNC - no impact | [25 empty] | 916 | [11 empty] | 03/07: Workgroup scheduled to report in June 2027 12/06: started up again - an interim update to the June UNC Panel detailing progress. 18/05/2026 - on hold, but report still due June 2027 at the moment 27/02 ; Feb 26 UNC Panel agreed to extend the Workgroup reporting date to June 2027 Oct UNC Panel allocated to Transmission Workgroup to report to March 2026 UNC Panel | to align with yet to be disclosed EU CAM Network Code reforms | CDSP | Yes
0918 Temporary reintroduction of the enhanced pressure service and increased MNEPOR for BBLC (reintroduced by UNC0891 and UNC0859 and introduced by UNC0814) | UNC | IGT UNC - no impact | [25 empty] | 918 | [11 empty] | 15/05 Authority approved, awaiting Implementation Instruction 16/01 Jan 26 UNC Panel recommended to Implement - now awaiting Authority Decision (decision date 07 May 26) 01/12: Reported to Nov UNC Panel and issued to consultation, started 21/11/25 to 02/01/2026 to report to Jan 2026 UNC Panel for Recommendation Oct UNC Panel allocated to Transmission Workgroup to report to December 2025 UNC Panel | tbc | None | Yes
0920 - PARCA Security Amount | UNC | IGT UNC - no impact | [25 empty] | 920 | [11 empty] | 31/07: Authority EDD listed to be issued of 16 October 26 17/07 July UNC Panel recommended implementation - now with the Authority 03/07: Consultation Closed and due to report for Panel recommendation in July UNC Panel 29/05: Reported to May UNC Panel and issued to Consultation, closing 19 June 2026 15/05 WG Reporting to May UNC Panel ahead of Consultation and July Panel Decision 01/12: Nov UNC Panel Assessed as Authority Directed and issued to Workgroup for 6 months (reporting May 26 UNC Panel) 14/11: Mod raised 07/11 for assessment at Nov UNC Panel | tbc | None | Yes
0922 CDSP Obligations required for the introduction of the Gas Shipper Obligation | UNC | IGT UNC | [10 empty] | IGT180 | [14 empty] | 922 | [11 empty] | 16/07: Workgroup extended to January 2027 at July UNC Panel 03/07: Likely to be withdrawn at this time due to GSO not yet confirmed 15/05: Mod currently on hold awaiting DEZNZ direction 16/01: Issued to a cross code UNC/IGT UNC Workgroup to report July 2026 UNC Panel | tbc | CDSP | Yes
0924R Review of UK retained EU Network Codes (to enable the streamlining of UK retained EU Network Codes) | UNC | IGT UNC | [10 empty] | tbc | [14 empty] | 0924R | [11 empty] | 27/02: Request Assessed by Feb UNC Panel and assigned to Transmission Workgroup to report 17 June 27 | n/a | CDSP | No
0925R Improving Smart / Automated Meter Reading Acceptance Levels for use in Settlement | UNC | IGT UNC - tbc SEC - tbc REC - tbc | [10 empty] | tbc |  |  |  |  | tbc - I0252, I0196 |  |  |  |  | tbc |  |  |  |  | 0925R | [11 empty] | 27/02: Request Assessed by Feb UNC Panel and assigned to Distribution Workgroup to report 18 March 27 - I0252 / R0196 potential overlap | N/a | CDSP | No
0926S Maintenance criteria for Emergency Contact data held in Central Systems | UNC | IGT UNC | [10 empty] | IGT183 | [14 empty] | 0926S | [11 empty] | 21/09/26 - IGT183 consultation ends 22/09. Aiming for Oct 26 Panel with same implementation date 04/09: Panel Decision to implement awaiting implementation date instruction 18/08: IGT183 WD Report to IGT Panel in August. 17/07: Reported to July UNC Panel and now in consultation until 06 August ahead of intended August UNC Panel Decision. IGT mod expected to proceed to consultation ~1 month after UNC 03/07 Now reporting to Panel 16 July 2026 27/02: Modification Assessed by Feb UNC Panel and assigned to Distribution Workgroup to report 18 June 2026 | tbc | CDSP | No
0928S - Enabling Amendment of Hydrogen Sulphide Limits in Network Entry Agreements | UNC | IGT UNC - no impact | [10 empty] | tbc | [14 empty] | 0928S | [11 empty] | 20/08: In Consultation until 25 September 2026 27/03:- March 26 UNC Panel assessment, allocated to Gas Quality Workgroup to Report to August 2026 Panel | tbc | CDSP | No
0929R - Consideration of an Independent Gas Quality Expert under the Uniform Network Code (UNC) | UNC | IGT UNC | [10 empty] | tbc | [14 empty] | 0929R | [11 empty] | 27/03:- March 26 UNC Panel assessment, allocated to Gas Quality Workgroup to Report to September 2027 Panel | n/a | n/a | No
0930S - Refining the Ratchet Charge Soft Landing Period | UNC | IGT UNC | [10 empty] | tbc | [14 empty] | 0930S | [11 empty] | 21/09 Workgroup report date extended until Dec 26 UNC Panel Meeting 18/05/26 - IGT UNC impact confirmed 17/04 Apr 26 UNC Panel Assessment, allocated to Distribution Workgroup to Report Oct 2026 | tbc | CDSP | No
0931S - Introduction of an Escalation process for Transportation invoice payment | UNC | IGT UNC - no impact | [10 empty] | tbc | [14 empty] | 0931S | [11 empty] | 17/08/26 - No IGT UNC code impact based on 11th Aug legal text 17/04 Apr 26 UNC Panel Assessment, allocated to Distribution Workgroup to Report Oct 2026 | tbc | TBC | No
0932S - Introduction of a Rolling Annual Quantity (AQ) backstop for Class 1 & 2 Supply Meter Points | UNC | IGT UNC | [10 empty] | tbc | [14 empty] | 0932S | [11 empty] | 29/05 Assessed at May UNC Panel, issued to Distribution Workgroup to report to November 2026 UNC Panel 15/05 - Raised 05 May for May UNC Panel assessment - IGT UNC impact confirmed | tbc | CDSP | No
0933S - Amendment to the designation arrangements outlined within TPD B4.7.16 – 4.7.21 to include a designate as ‘Daily Metered’ category. | UNC | IGT UNC | [10 empty] | tbc | [14 empty] | 0933S | [11 empty] | 04/09 - Workgroup now reporting 19 November 2026 29/05 - Assessed at May UNC Panel and issued to Distribution Workgroup to report to September 2026 UNC Panel 15/05 - Raised 05 May for May UNC Panel assessment - IGT UNC impact confirmed | tbc | TBC | No
0934 - Clarification of Panel Member Attendance Requirements | UNC | None | [25 empty] | 934 | [11 empty] | 20/08: In Consultation until 25 Sept 2026 29/05 - Assessed at May UNC Panel and issued to Governance Work to Report August 2026 UNC Panel 15/05 - Raised 07 May for May UNC Panel assessment | tbc | n/a | Yes
0935S - Updates to OAD Transporter Maintenance Arrangements | UNC | None | [25 empty] | 0935S | [11 empty] | 21/09: Workgroup report date extended until December 26 UNC+A32+AO32 | tbc | n/a | No
0936S - 3 Year Modified Extension to UNC 0780S | UNC | None | [25 empty] | 0936S | [11 empty] | 17/07: July Panel approved workgroup extension to December 2026 29/05: Assessed at May UNC Panel and issued to Gas Quality Workgroup to report to August 2026 UNC Panel 15/05 - Raised 12 May for May UNC Panel assessment | tbc | n/a | No
0937R - Aligning LDZ Charges with Actual Gas Usage for All Customers | UNC | IGT UNC | [10 empty] | tbc | [14 empty] | 0937R | [11 empty] | 17/07: Assessed at July UNC Panel, Cross Codes Impact was confirmed for IGT UNC, Issued to WG to report August 2028 03/07: Now going for July UNC Panel Assessment 12/06: Raised 05 June for June 26 UNC Panel Assessment - review likely won't impact, but any subsequent mods will impact IGT | n/a | n/a | No
0938R - Introducing Shipper Market Entry Requirements | UNC | IGT UNC | [10 empty] | tbc | [14 empty] | 0938R | [11 empty] | 03/07: Allocated to separate workgroup and due to report to Panel July 2027 12/06: Raised 05 June for June 26 UNC Panel Assessment - review likely won't impact, but any subsequent mods will impact IGT | n/a | n/a | No
0939R - Amendment to Gas Quality NTS Entry Specification at the Teesside or Easington System Entry Point | UNC | None | [25 empty] | 0939R | [11 empty] | 17/07 Raised 06/0726 assessed at July UNC Panel and reporting November 2026 | n/a | n/a | No
0940S - Updating the provision of Non-Daily Metered Sample Data | UNC | IGT UNC | [10 empty] | tbc | [14 empty] | 0940S | [11 empty] | 21/09/26 - updated to show expected iGT UNC impact 04/09 UNC August Panel assessment allocated to Distribution Workgroup to report 19 November 2026 17/08/2026 - added to tracker, IGT confirmed no impact | tbc | Minimal | No
0941S - Amending incorrect cross-references to National Gas NTS Licence Special Conditions following the RIIO-T2 to RIIO-T3 renumbering | UNC | IGT UNC - no impact | [25 empty] | 0941F | [11 empty] | 21/09: Awaiting Implementation on 09 October 2026 04/09: August UNC Panel assessment - changed from FT to SG and out for consultation to report to September UNC Panel 17/08/2026 - added to tracker, IGT confirmed no impact | 2026-10-09 | No | No
0942S - OAD Amendments to Annex E-1 | UNC | IGT UNC - no impact | [25 empty] | 0942S | [11 empty] | 21/09: Allocated to Offtake Arrangements WG and due to report to Panel 21 Jan 2027 04/09: Raised for September UNC Panel Assessment | tbc | No | No
0943S - Extension of the End Stop Date for the H100 Fife Project | UNC | IGT UNC - no impact | [25 empty] | 0943S | [11 empty] | 21/09 Now in Consultation until 05 November 2026 04/09: Raised for September UNC Panel Assessment | tbc | No | No
0944S - Proposal to remove obsolete clauses from TPD Section V 5.10 & Annex V-2, and V 5.11 & Annex V-3 of the UNC | UNC | IGT UNC - TBC | [10 empty] | tbc | [14 empty] | 0944S | [11 empty] | 21/09 - Raised 08 September, assessed in Sept UNC Panel and in Consultation until 22 Oct-26. Knock-on impact on iGT UNC due to renumbering at least (including annex) - can be included in iGT UNC housekeeping (fast tracked) | tbc | No | No
0945R - Review of NTS Access Arrangements | UNC | IGT UNC | [10 empty] | tbc | [14 empty] | 0945R | [11 empty] | 21/09 - Raised 09 September, assessed in Sept UNC Panel and allocated to Transmission Workgroup, to report 16 March 2028
I0187- Schedule 8 Review and Best Practice Guidance Development | REC | Watching brief only | [15 empty] | I0187 | 2024-10-15 | 2024-10-29 | [19 empty] | 16/04/26 - RECCo reviewing legal drafting 11/09/25 - expecting RECCo to provide papers for September TIG 14/08/25 - being presented at August Theft Issues Group 29/07/24 - theft change. Potential for knock on impacts to other codes | tbc | n/a | No
I0196 - Requiring the Supplier/Shipper to validate and enrich the data from the MEM prior to updating this in CDSP | REC | UNC - tbc, iGT - tbc | [10 empty] | tbc |  |  |  |  | I0196 | [9 empty] | tbc - 0925R | [11 empty] | 21/09/26 - on hold 26/02/26 - 4th working group 16/03/26 - delayed to 15/04/26 02/02/26 - 3rd working group 18/02/26 17/10/25 second working group scheduled 29/10/25 27/08/25 first working group scheduled 17/09/25 01/08/25 Code Manager looking for interest in a dedicated working group - do any other codes want to join? 16/06/25 - to be discussed at July Change Issues Group 24/04/25 - Code Manager reviewing IA responses. 03/03/25 - industry RFI closed 28/02/25 20/01/25 - to be discussed at Feb Change Issues Group 29/07/24 - raised by REC Performance Assurance. Potential cross code impacts on UNC / iGT UNC | tbc | tbc | No
I0197 - Introducing a Process to Provide Updates During Fault Resolutions | REC | BSC - Issue 112, UNC - tbc, iGT UNC- tbc, SEC - tbc, DCUSA - tbc | Issue 112 - see archive for info |  |  |  |  | tbc |  |  |  |  | tbc |  |  |  |  | I0197 |  |  |  |  | tbc |  |  |  |  | tbc | [11 empty] | 21/09/26 - on hold 14/05/26 - legal text being reviewed by RECCo and Gowlings 03/10/25 - work group meeting 4 scheduled 22/10/25 11/09/25 - next work groups expected October, exact dates TBC 01/08/25 - I0197 work groups held on 18/06, 09/07 and 17/07. More booked in for 07/08 and 12/08 21/07/25 - elec and gas specific work groups held in July, reviewing output 16/06/25 - first working group to be help on 18/06/25 at 2pm. Anyone can attend. 02/06/25 - first working group expected to be held w/c 16th June. 19/05/25 - MEP agreed to 3 changes strategy and to workshop gas and Elec together. Date of first working group tbc. 24/04/25 - scope updated by Performance Assurance. Expected to be split into 3 issues - I0197 will cover gas, new Issue for electricity and a separate one on D0302. Confirmation of this to follow. 03/03/25 - currently being reviewed by Performance Assurance 20/01/25 - update to be taken to Change Issues Group on 6th Feb 16/12/24 - RFI responses received and being reviewed. 07/10/24 - taken to Change Issues Group on 3rd Oct. Industry RFI to be issued in Oct and sign posted by other codes. 29/07/24 - potential to merge with Issue 112. Also related to gas | tbc | tbc | No
I0200 - Review of the REC's Address Management Service | REC | BSC - n/a, UNC - tbc, iGT UNC- tbc, DCUSA - n/a | [10 empty] | tbc |  |  |  |  | I0200 | [9 empty] | tbc | [11 empty] | 21/09/26 - fourth working group to be held on 05/10/26 30/07/26 - third working group being held 03/09/26 29/06/26 - second working group being held 17/07/2026 18/05/26 - working group set up, first one due 11/06 16/04/26 - renamed to Review of the REC's Address Management Service. Paper published with next steps and new scope, being reviewed at Change Panel on 21/04 02/06/25 - on hold while RECCo project continues 24/04/25 - discussions ongoing with RECCo to make sure no duplication of effort with their CRS projects. 20/01/25 - reviewing RFI responses and picking up with DNO specifically. 16/12/24 - RFI issued 04/11/24 - working group will meet after Change Issues Group on 07/11 07/10/24 - to be discussed at Change Issues Group on 07/11/24, noting tie in with I0172 | tbc | tbc | No
R0207 - Import / Export MOA Charging Clarification | REC | Watching brief only | [15 empty] | R0207 | 2024-09-17 | 2024-09-17 | [19 empty] | 11/08/26 - authority decision to approve, implementation on 06/11/2026 11/06/26 - with authority for decision, expected 28/08/2026 14/05/26 - final recommendation expected at June MEP being going back to Authority 16/04/26 - at consultation, closing on 01/05/26 02/02/26 - post impact assessment working group 02/02/26 13/11/25 - presented at MEP, impact assessment open 14/11 - 05/12 03/10/25 - working group 2 on 20/10/25 21/07/25 - working group to be set up - date confirmed as 03/09 02/06/25 - Authority sent back to REC on 30/05/25. 13/03/25 - rejected by MEP and passed to Authority for final determination 03/03/25 - due to be presented at March MEP. 13/02/25 - consultation responses being reviewed and Code Manager recommendation to be taken to MEP before going for Authority decision 20/01/25 - out for industry consultation 02/12/24 - IA confirms overall support. CP to progress. 02/09/24 - resolves issues raised in R0144 / P459. Already discussed with proposer and Ofgem. Both happy for it to be raised and issued for industry IA / consultation | 2026-11-06 | n/a | Yes
DCP420 - Include Car Charging Stations In The Definition For Non Final Demand | DCUSA | BSC - n/a, REC - n/a, CUSC - n/a | [5 empty] | DCP420 | [31 empty] | 21/09/26 - due to start again in Oct 18/05/26 - on hold, but expecting to progress to IA shortly 02/02/26 - interactions with CUSC, but no direct impact. Interim solution before DCP454, moving customer down a band. Would flow through to CUSC if approved, no separate change needed 16/09/24 - CUSC impact | tbc | tbc | Yes
I0219 - Stranded RMPs in Defunct Suppliers | REC | UNC - tbc, iGT - tbc | [10 empty] | tbc |  |  |  |  | I0219 | [9 empty] | tbc | [11 empty] | 19/05/25 - awaiting Xoserve input 24/04/25 - solution development discussions ongoing. 13/03/25 - not merging with I0178 and progressing as a separate Issue. 13/02/25 - maybe merged with I0178 | tbc | CSS, CDSP, ERDS | No
R0224 - Agile Reporting within CSS | REC | Watching brief only | [15 empty] | I0224 | [21 empty] | 21/09/26 - business case being updated 11/06/26 - second consultation expected, with a data spec doc from the DCC. Date tbc 12/02/26 - at consultation, closing 06/03/26 19/05/25 - Code Manager reviewing options and amending business case. 13/02/25 - with Service Provider for IA 02/12/24 - all codes listed as may require reports in the future | 2027-03-27 | CSS | No
MP169 Managing SEC Obligations and the Consumer’s Right to refuse a Smart Meter | SEC | REC, BSC - no impact | [20 empty] | MP169 | [16 empty] | 02/08/26 - discussions ongoing with proposer as to next steps 18/05/26 - Energy Ombudsman stance not changing. SECAS to review options with proposer 29.03.26 Discussions ongoing - including with energy ombudsman 02/02/26 - 169 remains on hold pending discussions with proposer 01 Dec 25 - SECAS holding discussions with Stakeholders on an agreed way forward. Planning final consultation in Q1 2026. 31.10.25 - Second refinement consultation issued - responses due 5 November 2025 10.09.25 - Refinement consultation issued, for views on solutions. Responses by 01 October 2025 21.07.25 - DCC Final I.A. received and reviewed. Working Group Exploring an alternative path via Agreed Procedure. 16.06.25 - awaiting Impact Assessment from the DCC 29 Jan 25 - REC impact potentially to COMCOP. Legal drafting for SEC required before relevant REC changes identifiable | tbc | tbc | Yes
Issue 117 - Incentivising Correction of Settlement Post-Theft | BSC | REC - tbc DCUSA - tbc | Issue 117 |  |  |  |  | tbc | [9 empty] | tbc+S52 | [21 empty] | 18/05/26 - next steps being looked at this week, potential for this to be closed 16/03/2026 - Next WG being organised 02/02/26 - work groups still on going 28/04/25 - working with TIG to make sure cross code is flagged at the start | tbc | tbc | tbc
R0253 - Theft - DNO/Networks not providing photos | REC | Watching brief only | [15 empty] | I0253 | [21 empty] | 12/03/26 - approved for implementation on 06/11/26 26/02/26 - final recommendation of approval published, going to Change Panel on 03/03/26 29/01/26 - consultation open 23 Jan to 13 Feb 19/01/26 - change report (for consultation) published, being reviewed at REC Change Panel 20/01. To be at consultation shortly 13/11/25 - party IA output due to be discussed at Nov TIG 17/10/25 - party impact assessment open, closing 07/11/25. Also being discussed at Oct TIG 21/07/25 - being presented at TIG on 25/07/25 | 2026-11-06 | n/a | No
I0252 - Increasing frequency of Annual portfolio reconciliation exercise to support Data Cleanse | REC | UNC - tbc, iGT - tbc | [10 empty] | tbc |  |  |  |  | I0252 | [9 empty] | tbc - 0925R | [11 empty] | 21/09/26 - requirements updated and 2nd service provider IA being scheduled 20/07/26 - service provider impact assessments on-going to assess assurance requirements and costs 26/02/26 - at party impact assessment, closing on 06/03/26 19/05/25 - gas only. Flagged as potentially cross code due to requirements on CDSP and iGTs as MAMs. | tbc | CDSP | No
R0261 - Addition of Export flag in D0303 flows | REC | BSC - tbc | tbc | [14 empty] | I0261 | [21 empty] | 28/05/26 - approved for implementation on 06/11/26 14/05/26 - final vote at TEP on 27/05/26 12/03/26 - change report for consultation being reviewed at March TEP, consultation will open 27/03 and run to 21/04 16/01/26 - moving forward with proposed solution to add Direction of Energy Flow to D0303, mandatory for MHHS migrated MPANs only. Out for party IA until 06/02/26 13/11/25 - information request open until 05/12/25. Q&A session on solution options 19/11/25 31/10/25 - proposal plan at change panel 04/11/25, expect to open Information Request for feedback on several solution options by 07/11/25 | 2026-11-06 | DTN | No
CP1607 Implementation of Data refresh message to ensure alignment of MHHS design | BSC | REC DIP | CP1607 CP1629 CP1647 | [14 empty] | R0294 | [14 empty] | DCR0016 | [6 empty] | 21/09/26 - see CP1647 - it is progressing to back out the approved solution for CP1607 30/07/26 "Cancellation of CP1607 'Implementation of Data Refresh Message" going to August SVG 06/07/26 updated CPs expected next month 11/06/26 CP1607 implementation agreed at SVG to be Feb 2029 so don't have to keep pushing back. 12/03/26 CP1629 rejected and implementation of CP1607 no longer going ahead. R0294 going on hold pending outcome of BSC actions. CP1607 implementation pushed back to June, potential to be pushed back further 02/02/26 - paper to BSC committee 03/02/26 to agree change in implementation date '29/01/26 - question from REC team, when are we expecting DIP CR? 16/01/26 - also linked to BSC CP1629, which is expected to change the implementation date of all 3 CPs to June 26 '27/11/25 - R0294 Implementation of IF-051 Data Refresh in EES for BSC CP1607 raised 18/08/25 - likely no REC impact, but potentially EES impacts. REC change may be needed if any EES testing is required '07/07/25 - action for REC to confirm any impacts ''Post-M10' change' | n/a | EES, DIP | No
I0262 Additional Registration Data (Gas) under Smart Energy Code | REC | SEC - DP301 UNC/IGT UNC - tbc | [10 empty] | tbc |  |  |  |  | I0262 |  |  |  |  | DP301 |  |  |  |  | tbc | [11 empty] | 18/05/26 meeting later this week to determine what data is being sent from Xoserve to DCC, and how this is being sent. '20/04/26 Discussions with Xoserv and DCC to establish if the obligation can simply be cut and pasted with no system / party changes or implications. Meetings held with Xoserv positive. Following up with DCC. '31/10/25 - being presented at Nov CHIG '17/10/25 - proposal plan being presented to REC Change Panel 21/10/25 '09/09/25 - SEC change DP301 raised - discussion on who is the lead code - decided REC as they are gaining obligations 'REC Change summary: Gas Transporters have very few obligations under the Smart Energy Code; those that they do have relate to provision of data owned by the REC. If these obligations were to be moved from the SEC to the REC, then the regulatory burden on GTs may be reduced as they would be able to completely secede from the SEC. | tbc |  | Yes
I0266 REC Data Specification Clarifications | REC | BSC -tbc UNC - no impact | tbc - BSC owned flows | [14 empty] | I0266 | [21 empty] | 16/04/26 - approved at Change Panel on 07/04/26 for November implementation 02/03/26 - consultation closed, expected to be at final vote 07/04/26. Confirmed again this will make changes to BSC SVs on messages part owned by BSC and part by REC, but wont touch messages wholly owned by BSC, and BSC will need to host Annex C if their messages still reference it by November release. JS taken away action to potentially raise a BSC CP. 29/01/26 - consultation closes 27 Feb 16/01/26 - being presented at Change Panel 20/01/26, expect to be at consultation by end of the week until end of Feb 11/12/25 - will be at consultation by end of January 20/10/25 - confirmed that REC will not host Annex C post implementation, so if there are any BSC flows that have not been updated, they will need to host 03/10/25 - at Party impact assessment until 28 Nov 2025 01/08/25 - will need a BSC cross code change as impacts D0011 and D0135 which have SVs owned by REC and BSC, unless the BSC are happy for REC to progress solo and they point to our IAs/consultations. There are also items of consideration on BSC owned flows (D0011, D0153, D0205, D0290 and D0310). These can be progressed under a separate change rather than cross-code, would the BSC like us to raise the change or just pass the information over for them to raise? 21/07/25 - addition of Annex B and Annex C back into the REC | 2026-11-06 | DTN | No
I0273 Sharing of SSC and TPR Information for MHHS Smart and Advanced Meters | REC | REC - I0273 BSC - Issue 118 (now closed) BSC - new CP to be raised | Issue 118 - closed tbc - new CP | [14 empty] | I0273 | [21 empty] | 21/09/26 - REC has started to draft a BSC Issue rather than a CP. To be shared shortly. 22/07/26 - looking to make SSC for smart segment meters, changes to SMRS validation required, BSC change to be raised. REC will be raising the BSC change. 29/06/26 - guidance document for interim solution has been published, work on enduring solution continues 16/04/26 - interim guidance document in the process of being drafted 12/02/26 - joint information request with I0303, closing on 13/03/26' 02/02/26 - BSC Issue 118 has been closed with no change required'. Information Request potentially going to be joint with I0303 as they're both about SSC/TPR 13/11/25 - information request expected to be issued by end of Nov - delayed 03/10/25 - plan being presented at Change Panel 07/10/25 '07/08/25 I0273 raised, with slightly wider scope that Issue 118 01/08/25 - REC cross code change being raised 07/07/25 - action for REC to confirm any impacts and to confirm they're happy for this to be BSC led | tbc | tbc | tbc
P494 Establishing a Smart Data Repository (SDR) | BSC | REC - n/a SEC - n/a | P494 | [36 empty] | 21/09/26 - Authority sent back. Solution being reviewed. Going to BSC Oct Panel 13/08/26 - decision date 31/08/26 30/07/26 - submitted to Authority on 14/07/26 06/07/26 - DESNZ/Ofgem publication received, going to July Panel before going to Authority for approval 18/05/26 - BSC panel delayed decision until June 20/04/26 - tbc on whether it goes on hold, or whether panel may defer decision post recent Ofgem announcement of a more central solution 12/03/26 - Assessment Report presented to Panel, RPC to be issued in March 02/02/26 - consultation open until Mid-Feb 18/08/25 - Modification Report submitted to Authority today 21/07/25 - discussion with REC, SEC and BSC needed, may impact on the Consumer Consent work Ofgem have delegated to RECCo. Also discussions about something similar happening under DESNZ | tbc | n/a | Yes
I0274 Gas Pressure and Capacity Information Transparency | REC | UNC? IGT UNC? | [10 empty] | tbc |  |  |  |  | I0274 | [9 empty] | tbc | [11 empty] | 26/02/26 - discussions ongoing with Proposer and Xoserve to determine what the Proposer wants vs what is possible 13/11/25 - proposal plan being presented at Change Panel 18/11/25 14/08/25 - accepted in on 12/08/25 | tbc | tbc - GES | No
I0278 Establishing the Safe Isolation Provider (SIP) as a Standalone REC Metering Party | REC | DCUSA - confirmed | [5 empty] | tbc | [9 empty] | I0278 | [21 empty] | 07/09/2026 - DCUSA raising their change shortly, potentially another consequential change coming about liability charges. No plans for anything to move from DCUSA to REC. 03/09/2026 - fifth working group being held on 10/09/2026 30/07/2026 - fourth working being held 18/08/26 29/06/2026 - third working group being held 21/07/26 14/05/2026 - first working group held on 11/05/26, working group meeting 2 due 26/06/26 13/02/2026 - information request open, closing 13/03/26 29/01/2026 - engagement with ENA, AMO and other trade associations to feed into solution 17/10/2025 - proposal plan being presented to Change Panel 21/10/25 21/08/2025 - accepted in | tbc | tbc | No
R0284 Updates to Schedule 14 Measurement Transformers Commissioning Timescales | REC | BSC | CP1640 | [14 empty] | I0284 | [21 empty] | 03/09/2026 - CP1640 already approved for June 2027 release 13/08/2026 - REC change approved with some tweaks to the solution which have been sent to BSC (Karan and Lee) 30/07/2026 - BSC consultation responses received, no comments. REC final vote 12/08 MEP, BSC likely to be Sept SVG 20/07/2026 - BSC consultation closes 28/07/26 01/06/2026 - BSC half aiming for July SVG, straight to consultation 11/05/2026 - impacts to BSCP515, BSCP705 and Notification of Commissioning Status Guidance V3.0 identified, BSC change will be required 16/04/2026 - consultation open, closes on 08/05/26 26/03/2026 - change report (for consultation) at MEP on 08 April, then proceeding to consultation. Expect to be open until early May 12/02/2026 - open for Party IA until 06/03/2026 29/01/2026 - going to Feb CHIG 25/09/2025 - accepted in | 2027-06-25 | n/a | No
I0285 - Organisations with multiple role types with EES and SDEP access | REC | BSC, UNC and iGT UNC - info only | [15 empty] | I0285 | [21 empty] | 21/09/26 - reviewing business case following IA responses 30/07/2026 - Party IA open, closing 28/08/26 14/05/2026 - Service Provider IA expected to finish mid June, and then proceed to Party IA 29/01/2026 - no longer going on hold, expect to progress to service provider IA ASAP 11/12/2025 - going on hold until at least end of Q1 2026 due to announcement re. enquiry services 06/10/2025 - enabler for R0162, and potentially other changes | tbc | EES/SDEP | No
DCR0005 - Extending SIT A Testing Environment | DIP | Info | [30 empty] | DCR0005 | [6 empty] | 18/05/2026 SIT A no longer exist and there are other test environments that exist, so hopefully this will be withdrawn shortly 23/02/2026 Work groups on-going, second one due 05/03/26 15/12/2025 A working group has been set up for 08/12/2025. 20/10/25 solution options have been presented; more work is required. Work groups expected. It is proposed to repurpose the SIT A testing environment to a DIP Testing environment. | tbc | tbc | tbc
DCR0006 - Managment of Major DIP incidents | DIP | Info | [30 empty] | DCR0006 | [6 empty] | 18/05/2026 legal text still being worked on. Second consultation expected 02/03/2026 The Legal text has been redrafted and addresses the concerns, queries, and suggestions raised via the consultation. Currently, the text is being reviewed internally before it is shared with a wider audience. 15/12/2025 Reworking the Legal text 20/10/25 consultation closed In order to ensure that the DIP Manager can effectively manage major incidents to the DIP it is proposed the desired outcome is: Introducing a framework that has provisions to assign and define actions from the DIP Manager, DIP Users, and/or their Contracted Service provider during a Major incident; Introducing Service Level Agreement (SLAs) to be agreed, which are enforceable; and Developing an central record of agreed actions. | tbc | n/a | No
DCP454 Provide enduring targeted relief from residual charges for electric vehicle charging sites | DCUSA | REC - n/a CUSC - tbc | [5 empty] | DCP454 | [26 empty] | tbc |  |  |  |  | 16/02/2026 currently undergoing impact assessment. SDEP not part of the solution, REC impact removed 06/05/2025 DCP454 raised - potential solution includes SDEP screens so may need a REC change | tbc | tbc | Yes
DCP461 Reducing the Impact of Transmission Distribution Charges | DCUSA | CUSC - CMP460 | [5 empty] | DCP461 | [26 empty] | CMP460 |  |  |  |  | 18/05/2026 out for consultation 16/02/2026 DCP461 potentially interim until CMP460 is implemented, joint working groups ongoing, multiple potential solutions (9) 13/08/2025 DCP461 raised | tbc | tbc | Yes
[Pre-raise] Inclusion of DI-086 Supplier Effective From data item in the IF/PUB-036 | BSC | REC | CP tbc | [14 empty] | tbc | [21 empty] | 18/05/26 - still on hold 16/02/26 - currently "on hold", potentially targeting M15 (may 2027) for implementation 17/11/25 - assuming this is linked to REC change I0230, would require a joint REC change to make the Supplier REGI date mandatory in the D0303 again The IF/PUB-036 goes to EES; EMDS change required | tbc | DIP, EMDS | tbc
CP1628 CT Trad Meter CP (Traditional Meters with Current Transformers) | BSC | REC - none | CP1628 | [36 empty] | 11/05/2026 approved for November implementation - no REC impact, not introducing a new Meter Type into the EMDS 10/04/2026 confirmed TRADCT meter type is not needed at April SVG, which would be no REC impact - potential to come back into scope following conversations with DNOs 16/03/2026 - JS taken an action to confirm on TRADCT Meter Type - likely missed the deadline for June implementation if required 29/01/2026 - potential REC impact, if advanced MOA needs to send D0149/D0150 which would require a change to REC Schedule 14. Plus if new Meter Type "TRADCT" is required, this Data Item is owned by REC (J0483 / DI-059). REC will be responding to BSC consultation with above | pending change to 09/11/26 - 05/11/2026 | ISD | No
CP1638 Enabling the optional use of the D0010 from Meter Reading Service to Smart Data Service | BSC | For info | CP1638 | [36 empty] | 05/08/2026 - approved for November 26 release 30/07/2026 - going for approval on 04/08 SVG 02/07/2026 - consultation closes 24/07/2026 - needs to be approved by end of August to hit November release. 01/07/2026 - in July SVG papers, does not include the red-lining for EMDS. Flagged to REC Technical Services 15/06/2026 expected to go to July SVG 16/02/2026 aiming to raise within next month No REC impact assuming impact is limited to D0010s | 2026-11-05 | EMDS | tbc
[Pre-raise] Linked Import/Export MPANS with meters in the Advanced and Trad or Smart Meter Groups | BSC | REC? | CP tbc | [14 empty] | tbc | [21 empty] | 21/09/26 - work expected to start early 2027 16/02/2026 discussions on-going between BSC, REC (Jonny Moore) and proposer. | tbc | tbc | tbc
[Pre-raise] Adoption of the DIP Market Role as the basis for all SVA Market Roles | BSC | tbc | CP tbc | [36 empty] | 21/09/26 - work expected to start early 2027 | tbc | tbc | tbc
Issue 120 GGCF Scaling Weights Issue group | BSC | For info | Issue 120 | [36 empty] | 21/09/26 - Mod expected with no cross code impacts 16/03/2026 - consultation closed with majority support 16/02/2026 Issue group on-going, consultation issued on potential updates feeding into 3 monthly review of scaling weights. Likely won't need a full BSC change | tbc | tbc | tbc
DCP467 Online reporting tools for Category A and B defects | DCUSA | REC | [5 empty] | DCP467 | [9 empty] | I0306 | [21 empty] | 03/09/2026 - next DCUSA working group 09/09/2026 30/07/2026 - REC to provide output (with ROM costs and implementation timescales) to DCUSA W/C 17th August, for DCUSA to convene the working group for discussion. REC to present this output, and overview of SDEP, at the working group. 20/07/2026 - REC progressing preliminary IA with SDEP provider 11/06/2026 - REC consultation closed, responses passed over to DCUSA 28/05/2026 - next work group 22/06/26, hopefully proceeding to report phase and voting 14/05/2026 - DCUSA consultation closes 19/05 and meeting to discuss on 27/05, REC consultation open 15/05 to 08/06 16/04/2026 - next working group 20/04/26, DCUSA expecting to move to consultation shortly after. REC will be presenting at MEP on 13/05/26 and opening their consultation later that week. 16/02/2026 - DCUSA IR delayed, still being drafted. May wait until REC IA is closed 29/01/2026 - going to Party IA (REC) and Information Request (DCUSA) 06 to 27 Feb 16/01/2026 - REC Issue I0306 raised 11/12/2025 - first DCUSA working group 12/01/26 24/11/2025 - added to tracker, REC Change will be required as will impact STIRG | tbc | DCUSA - none REC - EMDS | Yes
CP1616 Specific Event Scenarios for Backdated MHHS Service Provider Appointments | BSC | For info | CP1616 | [36 empty] | 05/08/2026 approved for Feb 27 release 30/07/2026 assessment report and decision at Aug SVG with third consultation responses, proposing Feb 27 implementation 16/02/2026 on hold, debate between two solutions. Third consultation will be required, target implementation delayed CP will be presented to SVG and ISG on 2/12/25 for decision. Target implementation date 26/03/26. This CP proposes to replace generic event codes with specific event codes for scenarios such as CoS, MCA, MCS, and SEG. | 2027-02-25 | DIP, EMDS | No
DCR0009 - DIP Status Error Messages affecting Licensed Distribution System Operators | DIP | TBC | [30 empty] | DCR0009 | [6 empty] | 21/09/26 - solution being reviewed 01/06/2026 being worked on now DCR15 is approved 02/03/2026 The DIP Manager is working on the solution. This is part of the issue with Level 3/4 validations. The DIP Manager is seeking to address this issue first before progressing with a solution for the error message received by LSDOs 15/12/2025 The DIP Manager is developing a solution. This will be presented in early 2026. The DIP is currently generating status error messages in two scenarios: 1. When IF messages from MPRS are processed by the DIP before the corresponding IF-050 message has created the related MPAN (e.g., IF-043 or IF-009 “Invalid MPAN” errors). 2. When there is no Supplier to route to, resulting in “no primary recipient” errors (e.g., IF-003 and IF-020). In these situations, LDSOs receive error notifications that do not require any action. However, they must still manually investigate each instance, which creates unnecessary operational overhead and cost. The presence of these non-actionable errors also introduces noise within monitoring systems, potentially obscuring genuine issues that require investigation. | tbc | DIP | No
CP1634 Change of Condition to Mandatory for B013 ‘CSS Registration ID’ group in DIP messages | BSC | REC, DIP | CP1634 | [14 empty] | I0296 | [14 empty] | tbc | [6 empty] | 07/07/2026 - approved at SVG for Nov release 15/06/2026 - consultation ran 11 May to 5 June. Aiming for July SVG for decision 11/05/2026 CP1634 raised. I0296 has been moved to resolved, changed so BSC is lead code 16/04/2026 Reports to be made available for all suppliers who request them. Likely will be moved to resolved as no code changes required. BSC change expected at May SVG? 26/02/2026 undergoing a trial with friendly parties to test the process 16/02/2026 REC change undergoing solution development on how practically we will get Parties their Reg ID, no update on BSC change 12/01/2026 - when are we expecting a BSC change on the IF-031 to make group CSS Registration Request ID 1-1 rather than 0-1? Presented at Change Issues Group 15/01/26 03/12/2025 Issue accepted in | 2026-11-05 | EMDS, DIP | No
I0297 - Meter Manufacturers Make and Type not Populated in SMRS | REC | BSC? Tbc | tbc | [14 empty] | I0297 | [21 empty] | 21/09/26 - change report being updated following Party IA 30/07/2026 - at Party IA, closing 21 Aug 29/06/2026 - going through full chance process, Update to Plan approved at June TEP. Expecting to be at Party impact assessment in July. 16/04/2026 - guidance document being drafted. TBC on whether obligation changes are required. 26/03/2026 - being presented at April CHIG 21/01/2026 - Information Request open, closing 13/02/2026 16/01/2026 - Presented at Change Issues Group on 15/01/26 - potentially seen as not an issue? 03/12/2025 Issue accepted in | tbc | n/a | No
DCP468 Remove Redundant DataFlow from DTC/EMDS | DCUSA | For info | [5 empty] | DCP468 | [31 empty] | 20/07/2026 - approved for November release 01/06/2026 - out for vote currently, still targeting November release 16/04/2026 - tbc but potentially targeting November release 12/02/2026 - D0164 / MM00069 might be redundant - to flag to REC Technical Services | 2026-11-06 | EMDS | No
DCP469 Cross Code Standardisation of Charging Arrangement Notice Periods | DCUSA | CUSC - tbc? UNC - tbc? | [5 empty] | DCP469 | [19 empty] | tbc | [6 empty] | tbc |  |  |  |  | 01/06/2026 - reviewing RFI (suppliers only) feedback, may lead to a wider industry consultation 13/01/2026 - raised following rejection of a previous mod, request from Ofgem to be more cross-code where other codes include similar charges (e.g tnuos under CUSC). CUSC/UNC to be included in the DCUSA working group if they wish | tbc | tbc | Yes
I0312 Review of export meter work arrangements | REC | BSC - tbc? DCUSA - tbc? | tbc |  |  |  |  | tbc | [9 empty] | I0312 |  |  |  |  | tbc | [16 empty] | 21/09/26 - working groups ongoing 11/06/2026 - third working group meeting 14/07/2026 28/05/2026 - second work group meeting 03/06/2026 16/04/2026 - proposal plan going to Change Panel on 21/04/26. Working groups being set up, first meeting to take place on 06/05/26 26/02/2026 - accepted in, potential to impact BSC and DCUSA | tbc | tbc | No
R0317 Number of Displayed Register Digits Data Item linkage | REC | BSC - info | [15 empty] | R0317 | [21 empty] | 28/05/2026 - approved for implementation on 06/11/2026 14/05/2026 - final vote at TEP on 27/05/26 16/04/2026 - at consultation, closes 01/05/26 26/02/2026 - accepted in, impacts market messages owned by both BSC and REC. The way EMDS is set up means changing the linkage will make the changes in the BSC owned IFs, even if no BSC CP is raised. | 2026-11-06 | EMDS | No
I0318 Introduction of Consumer Consent Solution | REC | BSC - tbc SEC - tbc | tbc | [14 empty] | I0318 |  |  |  |  | tbc | [16 empty] | 14/05/2026 - monthly updates being provided at Change Issues Group 26/02/2026 - accepted in, potential to impact BSC and SEC | tbc | tbc | Yes
DCR0011 - ‘Change to DIP Portal controls to allow Lead Admin to manage organisation MFA reset | DIP | For Info | [30 empty] | DCR0011 | [6 empty] | 02/03/2026 - The DIP Manager has added this request to the system backlog. This change request aims to improve the process for managing MFA issues, allowing Lead Admins to provide support directly before escalating to the ServiceDesk. Currently, when a DIP MFA is unusable due to application corruption, lost devices, or portal failures, Lead Admins must request MFA resets from Elexon through the ServiceNow portal. This process is slow, relies on multiple communications, increases workload, and depends on the ServiceDesk's ability to recognize issues quickly. | tbc | tbc | No
DCR0014 'Restrict DCP Access to MPIDs and Certificates from Organisational Level to DCP level ' | DIP | For Info | [30 empty] | DCR0014 | [6 empty] | Introduce functionality within the DIP to allow MPID-level access controls for DCPs, ensuring that: DCPs can only view, manage, and administer certificates for the MPIDs they are explicitly assigned to. Certificate admin permissions can be scoped at MPID level rather than applied at organisational level. Visibility and management of certificates for other MPIDs within the same organisation are explicitly restricted unless authorised. | 2026-11-06 | tbc | tbc
P509 'Consumer benefits and safety net for DSR participation in the wholesale market' | BSC | For info | P509 | [36 empty] | 13/08/2026 - working group 3 10/08/26 29/06/2026 - working group 1 19/05/26, working group 2 22/06/26 | 2027-11-04 | tbc | Yes
P510 'Introducing Direct Compensation for Virtual Trading Party actions in the Wholesale Market' | BSC | For info | P510 | [36 empty] | 13/08/2026 - working group 3 12/08/26 29/06/2026 - working group 1 19/05/26, working group 2 22/06/26 | tbc | tbc | Yes
R0321 DNOs Create Export MPANs after approving G98/99 commissioning documents | REC | For info | [15 empty] | R0321 | [21 empty] | 21/09/26 - reviewing responses to consultation 03/09/2026 - confirmation received via email from D Code no impact to their code. At consultation. 13/08/2026 - expected to be at consultation 21/08 to 14/09, change has been renamed to "DNOs Create Export MPANs after approving G98/99 commissioning documents" - have emailed Distribution Code for confirmation this does not impact them 30/07/2026 - consultation delayed while potential performance assurance requirements looked at 20/07/2026 - expect to be at consultation by the end of the week 11/06/2026 - investigating tweaks to the solution, which may make an obligation under Distribution Code (steps in G98/G99 form process) the trigger point, but will not require any changes to D Code. 14/05/2026 - Party impact assessment running 08/05 to 01/06 27/03/2026 - accepted in | 2027-06-25 | No | No
DCR0015 'Introducing Level 3 and Level 4 Response Codes into the DIP Rules' | DIP | For Info | [30 empty] | DCR0015 | [6 empty] | 13/05/2026 - approved for implementation 05/11/26 20/04/2026 - Consultation finished. Drafting Final Assessment 30/03/2026 - The DIP Rules outline the obligations that DIP Users must fulfil, including the process for validating messages exchanged between each other. Message validations within a message channel are categorised into four levels, ranging from 1 to 4. Levels 1 and 2 involve synchronous and asynchronous validations performed by the DIP, while the DIP Users themselves handle Levels 3 and 4, also with both synchronous and asynchronous validations. However, the DIP Rules do not specify response codes for DIP Users to utilise at Levels 3 and 4. This lack of clarity is affecting how applicants, potential users, and existing DIP Users develop their systems to manage both synchronous and asynchronous validations. | 2026-11-05 | DIP | No
DCR0017 'Amendment of L4 Rejection Non Functional Timing Requirements and exemption' | DIP | REC - confirmed none | [30 empty] | DCR0017 | [6 empty] | 17/08/2026 - looking for approval in Sept DCAB 30/07/2026 - consultation closed 24/07/26 07/07/2026 - legal text reviewed by REC, only Supplier asynchronous obligations in scope, no REC impact. 06/07/2026 - out for consultation. REC to confirm EES Service Definition impacts 01/06/2026 - working on legal text, expecting to publish initial assessment in next few weeks 30/03/2026 - may impact REC EES Service Definition 30/03/2026 - Level 4 (L4) validations are required in order to reject incorrectly sent flows based on participant and MPAN level data. Under current compliance rules these asynchronous rejections are required to be sent within 6 secs of receipt under Non Functional Requirement (NFR) E2E1009. These validation requirements are by nature required to be validated against user role and portfolio level data (MPAN) and as such the current turn around time for these flows are not indicative of a process that requires this level of validation. These compliance rules are valid for a number of PUB flows under MHHS and are also relevant to REP flows, which require decompressing to enable this level of validation. As such, and to ensure meaningful and realistic validation processing SLAs that are consistently applied across DIP users, we request that the NFRs be set to 90% of all messages are processed within 60 mins, allowing successful processing and rejection, while still enabling the operational choreography to progress without issue. We also believe that the inclusion of the REP flows in this NFR is illogical as they do not include MPAN level data to enable validation at this level and as such should be exempt from this level of validation. It is noted that this change is required across market roles of Suppliers, Data & Metering Services DIP roles. Relaxation of the timing Non Functional Requirements to enable asynchronous response within 60 mins (for 90%) rather than the current 6 seconds, which is unrealistic where validation and response is required at an MPAN level. Exemption of the REP Flows from this NFR as they are not MPAN level flows. 30/07/2026 - Consultation is now closed and DIPM is currently reviewing responses, and possible legal text will be amended, Comms and Final Assessment will be publish in due course. | 2026-11-05 | DIP | No
I0228 ECOES API for Export MPAN Creation at Scale | REC | DCUSA - confirmed none | [15 empty] | I0228 | [21 empty] | 01/06/2026 - going on hold until outcome of 321 is known, DCUSA have confirmed no impact. 10/04/2026 - to check for DCUSA impact, is there anything in DCUSA regarding the creation of Export MPANs? REC and DCUSA both believe no, but DCUSA have taken an action to double check | tbc | SDES | No
I0324 Use of REL Data to Support Key Regulations | REC | For info | [15 empty] | I0324 | [21 empty] | 21/09/26 - out for consultation. Limited to Gov departments and RECCo 12/05/2026 - not cross code, but will open up use of REL (which is currently limited to just switching) to support Ofgem reporting, cross code assurance and SEC Guaranteed Standards. | tbc | tbc | No
I0325 Post-MHHS Full Transition Complete (M15) REC updates | REC | tbc | [15 empty] | I0325 | [21 empty] | 21/09/26 - going to Oct CHIG 20/07/2026 - proposal plan being presented at Change Panel on 21/07, preliminary scope list available on the REC portal 12/05/2026 - Issue to be implemented at or just after M15 to remove any references to non-MHHS Metering Points or Transition arrangements from the REC. Expect other codes will need to do similar but possibly won't need to be true cross-code with same implementations - tbc | M15 at earliest | EMDS | No
DCR0020: ‘Decreasing the Retention Period for the DIP Archive’ | DIP | BSC, REC | tbc | [14 empty] | tbc | [14 empty] | DCR0020 | [6 empty] | 01/06/2026 - consulted on in May, supportive of reducing storage cost but more review required of whether there needs to be different retention periods for different messages. Likely to have a work group set up. Looking at post M15 implementation so to not impact Parties during migration 18/05/2026 - The Data Integration Platform (DIP) currently provides message archiving, replay, and re-queue services to support users in scenarios such as data loss or system failure. Under existing DIP Rules, messages are retained for two years, and users must demonstrate equivalent data retention capability during onboarding. To ensure the DIP remains efficient and cost-effective, it is proposed to reduce the archive retention period from two years to 90 days. This change would materially reduce storage and indexing costs while maintaining sufficient capability to support core recovery functions such as message replay and re-queue. 30/07/2026 - Currently gaining internal Market Design review of the retention doc. | Post M15 | DIP | tbc
I0327 Provision of Standard industrial Classification (SIC) Code to REC Parties | REC | For info | [15 empty] | I0327 | [21 empty] | 21/09/26 - discussions ongoing with the proposer 28/05/2026 - accepted in as Issue by Code Manager, to investigate why this data is needed and if it is appropriate or feasible for this be provided to Parties via the REC | tbc | tbc | tbc
R0328 Removal of D0383 & D0384 requirements from Sharing MTDs process | REC | For info | [15 empty] | I0328 | [21 empty] | 21/09/26 - updating final change report 13/08/2026 - consultation 14/08 to 07/09 20/07/2026 - proposal plan being presented at Change Panel 21/07, will be at consultation by mid-August 28/05/2026 - removal of sharing D0383/D0384 from MOA to DNO/Supplier from Schedule 14. Added by MHHS in error, was not part of legacy arrangements and SVs do not exist. Believe no cross-code impact. | tbc | None | No
DP315 Dual running of DCC Smart Meter Communication Licence | SEC | REC | [15 empty] | I0333 |  |  |  |  | DP315 | [16 empty] | 15/09/26 presented to Change Sub Committee for views - no comments raised. Agreed can progress as self governed change. 30/07/2026 - REC panel presentation delayed until 04/08, but now aiming for implementation on 01/10 so does not enter new DCC reporting period 20/07/2026 - REC Change Report (For Consultation) being presented at Change Panel 21/07 before proceeding to consultation 15/06/2026 - REC Issue I0333 raised - is being used as the REC version of both DP315 and DP325 rather than raising 2 separate Issues 01/06/2026 - DCC2 is going live on 02/11/26, updates needed to SEC and REC as they point to specific licence conditions and the numbers are changing. Shouldn't impact other codes, but sweep required to make they don't point to any DCC licence conditions numbers | 02/11/2026 at the latest | None | No
DP325 - SMCL2 Code Changes Housekpping and process changes imapcting SEC from new Smart Meter Licence and Transfer of DCC Licensee from Capita to DCC2.0 - due 2 Nov 26. | SEC | None direct (separate REC change is required for REC impacts but the two are autonomous) | [15 empty] | I0333 |  |  |  |  | DP325 | [16 empty] | 15/09/26 - presented to Change Sub Committee for views. None provided. Will go to consultation with aim to implement a week before Business Transfer. 02/08/26 - Modification consultation closing 05 august 26. 10/06/2026 - Change Sub Committee to discuss scope of changes at its meeting 16 June 26. NB there will be a corresponding REC change to address impacts of SMCL2 impacts to REC but the two changes are distinct to each code and as such not a true cross code impact although both will need to be implemented by 2 Nov 26 when DCC Business Transfer to new licensee DCC2.0 occurs. | 02/11/2026 at the latest | None | No
I0331 Regulatory Alliance Creation Rejections | REC | DCUSA - tbc, UNC tbc | [5 empty] | tbc | [9 empty] | I0331 | [9 empty] | No Impact | [11 empty] | 03/09/2026 - at Party impact assessment, closing 25/09/26 13/08/2026 - proposal plan being presented to Change Panel 18/08, solution development on-going but can share first draft if DCUSA/UNC would like to see 11/06/2026 - raised by a Party requesting a review of the creation of Regulatory Alliance process, particularly what happens when these get rejected. Potential impacts to DCUSA and UNC. | tbc | tbc | tbc
DCP476 Treatment of multi MPAN sites | DCUSA | REC tbc, BSC tbc | tbc |  |  |  |  | DCP476 | [9 empty] | tbc | [21 empty] | 17/08/2026 - working group due 18/08/26, range of solutions available 20/07/2026 - out for consultation 22/06/2026 - added to CCSG tracker. Potential to impact other codes depending on solution - if limited to charging, likely no impact. But if looks at amending or adding an MPAN status, may have BSC and REC impacts. | tbc | tbc | Yes
I0335 Introduction of Defined Electricity Metering Work Categories for Metering Accreditation | REC | For info | [15 empty] | I0335 | [21 empty] | 21/09/26 - change plan to be presented Oct 26 29/06/2026 - looking to introduce Electricity Metering Work Categories, similar to those already in place gas. | tbc | tbc | tbc
I0301 Updates to Enquiry Service API endpoints to support migration to RECCo’s API Gateway | REC | For info | [15 empty] | I0301 | [21 empty] | 21/09/26 - awaiting guidance document 29/06/2026 - not cross code, but will impact any codes who use the GES API as there will be new API URL to use. Expected to be a ~6 month transition period for GES Users to point to the new URL. Similar to change for EES to follow in due course. | tbc | GES | No
CP1639 Clarification of Rules Regarding MHHS Agent Appointments for Associated Export Metering System Identifiers (MSIDs) | BSC | REC - confirmed none | CP1639 | [36 empty] | 03/09/2026 - approved for November release 20/07/2026 - consultation closes 07/08/26 01/07/2026 - believed there to be impacts to REC Schedule 14 and 34. Offline conversation confirmed impact is limited to SMRS auto-appointment of agents, not the requirement to have the same MOA appointed on Import/Export using same asset. | 2026-11-05 | SMRS | tbc
CP1635 EMDS interface corrections from deferred Design Issue Notifications (DINs) | BSC | REC - confirmed none | CP1635 | [36 empty] | 03/09/2026 - approved for November release 20/07/2026 - typo confirmed, no REC impact. Consultation closes 07/08/26 - REC to respond to consultation with proposed changes referencing the REC Meter Config tables. 03/07/2026 -IF-025/MM20035 to "For the avoidance of doubt validation will be based on Profile Class and SSC values in isolation (i.e. no PC-SSC Combination checks) - need to double check solution as IF-025 is not MM20035, it is MM20019. MM20035 is the IF-005, which is REC owned. Also SSC is REC owned, and there may be a suggested wording change coming from RECCo to reference the REC Meter Configuration tables | 2026-11-05 | EMDS | tbc
P515 Delaying Settlement and Payment Runs | BSC | For info | P515 | [36 empty] | 21/09/26 - approved. Implementation 28/09/26 13/08/2026 - consultation ran 06/07 to 17/07 06/07/2026 - added to CCSG tracker, no impacts to other codes expected | 2026-09-28 | tbc | Yes
P516 Provision of Metered Data for MHHS Metering Systems to ESNAs | BSC | For info | P516 | [36 empty] | 03/09/2026 - approved for November release 20/07/2026 - consultation closes on 24/07/26 06/07/2026 - added to CCSG tracker, no impacts to other codes expected | 2026-11-05 | tbc | No
P517 Reporting to EMRS of chargeable volumes for CVA Metering Systems | BSC | For info | P517 | [36 empty] | 21/09/26 - working group nearly completed. Consultation due Oct / Nov 26 03/08/2026 - to be raised this week 06/07/2026 - added to CCSG tracker, no impacts to other codes expected | 2027-03-15 | tbc | Yes
Issue 123 - Review of Asset Metering Arrangements | BSC | For info | Issue 123 | [36 empty] | 07/09/2026 - REC to double check there is no appetite to attend working group 06/07/2026 - added to CCSG tracker, no impacts to other codes expected | tbc | tbc | tbc
CP1636 Correcting the L5 validation of the IF/PUB-021 | BSC | DIP | CP1636 | [29 empty] | tbc | [6 empty] | 03/09/2026 approved for November release 20/07/2026 consultation closes 07/08/26 | 2026-11-05 | tbc | No
CP1637 Mandating Registration of all Measured Quantities for Systems Connection Point Metering Systems | BSC | For info | CP1637 | [36 empty] | 03/09/2026 approved for November release 20/07/2026 consultation closes 07/08/26 | 2026-11-05 | None | No
CP1633 Capture Modem Module Details Under BSCP601 | BSC | REC - I0338 | CP1633 | [14 empty] | I0338 | [21 empty] | 21/09/26 - I0338 being discussed with the proposer 05/08/2026 - solution sent over for review, there is REC impact, REC Issue raised, agreed at SVG second consultation to happen on CP1633 following REC change being raised 30/07/2026 - SVG papers reviewed, looks like MOA obligations to check with DC/DS has not made it to final solution so no REC impact - Jenny to double check 22/07/2026 - BSC to keep REC updated on the solution, likely REC impacts identified to Schedule 14 and potentially D0268 if a Market Message solution is used. 20/07/2026 - added to CCSG tracker, call request to discuss potential REC impacts | tbc | tbc | No
Pre-raise additional routing to the IF-014 | BSC | DIP - tbc | tbc | [29 empty] | tbc | [6 empty] | 20/07/2026 proposal to add additional routing to the IF-014 'UTC Settlement Period Consumption Data (Warnings & Rejections)' so that the 'ConsumptionOnDeEnergisedMPAN' event is also sent to the Supplier, who will be responsible for investigating the issue with their MOA. EMDS impacting. | tbc | EMDS | No
CP1645 add a new recipient of the IF-036 SMRS Notification of Supplier Agent Appointment & Supporting Info MM20010 | BSC | DIP - tbc | CP1645 | [29 empty] | DCR0026 | [6 empty] | 03/09/2026 approved for November release 05/08/2026 short consultation in August to allow for Sept decision - been agreed with RTS this can make Nov release, but any delay to decision will delay implementation 20/07/2026 proposal to add MDS to Always on SV20109, Elexon need to talk to RTS about implementation date as approval is planned for past end of August deadline for November EMDS changes | 2026-11-05 | EMDS | No
DCR00023 Level 4 Validation – MPAN Invalid or Unknown (RCP1061) for IF-021s | DIP | BSC - tbc | tbc | [29 empty] | DCR00023 | [6 empty] | 21/07/2026 - Consultation starts, this will run till 10/08/2026. DIPM will then review the responses. | tbc | DIP | tbc
CP1646 Clarify Supplier obligations for IF/PUB-002 messages where a registration switch is cancelled | BSC | REC - R0339 | CP1646 | [14 empty] | R0339 | [21 empty] | 21/09/26 - CP1646 going to SVG in Oct for approval. R0339 out for consultation until 07/10/26 with proposed implementation date 26/02/27 07/09/2026 - potential for REC to not implement until February, BSC to see if they want to delay implementation 05/08/2026 - REC change being raised - R0339. BSC consultation open 10/08 to 07/09 30/07/2026 - added to CCSG tracker, may require an update to REC schedule 14 to add similar wording. To discuss whether need to align consultations. | 2026-11-05 | n/a | No
CP1648 REP009, REP002, REP002a REP002b Exceeding or Potentially Exceeding DIP 1 MB Limit. Implementing a file-splitting solution | BSC | DIP - tbc | CP1648 |  |  |  |  | DCP482 | [24 empty] | tbc | [6 empty] | 21/09/26 - CP1648 consultation closed and going to SVG for approval. SVG will have options 17/08/2026 - DCUSA change going to Aug DCUSA Panel - no dependency on DCUSA/BSC being in same release 13/08/2026 - RTS confirmed red-lining received, consultation 10/08 to 07/09 05/08/2026 - proposed solution implements splitting mechanism, solution to extend DIP limit has been discounted. Flagged at SVG that RTS have not received redlining and it is not yet clear if the proposed solution is EMDS compatible. Agreed consultation won't be issued will RTS have confirmed the solution is possible within EMDS 30/07/2026 - added to CCSG tracker, flagged as having EMDS impact, believe Nov implementation will be tough with end of August approval deadline, have BSC talked to RTS? DCUCA change being raised for REP900 - implementation being delayed to Feb | 2027-02-27 | DIP, EMDS | No
CP1649 IF-014 Potentially Exceeding DIP 1 MB Limit | BSC | DIP - tbc | CP1649 | [29 empty] | tbc | [6 empty] | 21/09/26 - CP1649 consultation closed and going to SVG for approval. SVG will have options 13/08/2026 - RTS confirmed red-lining received, consultation 10/08 to 07/09 05/08/2026 - action taken at SVG for BSC to confirm EMDS impacts with RTS, and provide legal text for them to confirm solution is EMDS compatible before going to consultation 30/07/2026 - added to CCSG tracker, believe will have DIP impacts. Flagged as EMDS impacts, to understand what those are - Jonny and Chris discussing if there is an EMDS impact or not | 2027-02-27 | DIP, EMDS | tbc
P518 Elexon to provide data for ABSVD for CLASS | BSC | NESO | P518 | [36 empty] | 03/08/2026 - will impact NESO, but not from a code (CUSC, SQSS etc) perspective | tbc | tbc | tbc
P519 Preventing Participants from registering Metering Systems in MHHS Market Segments for which they are not Qualified | BSC | REC - confirmed none | P519 | [36 empty] | 21/09/26 - with Authority. Panel recommended rejection 06/08/2026 - call confirmed solution is limited putting a block on a Party within CSS at request of BSC PAB, similar to other processes already in place, not a full technical solution that would prevent Parties registering within CSS (already looked at under I0194 and discounted). No REC impact from this solution. 05/08/2026 - emailed received saying this is looking at a CSS solution. To be discussed and lead code re-evaluated as may need to be REC if there is a CSS solution 03/08/2026 - potential REC impacts, going to have working groups so to look at getting REC to attend | tbc | None | Yes
CP1641 Modernisation of ECVN & MVRN Submissions and Acknowledgement process | BSC | For info | CP1641 | [36 empty] | 21/09/26 - Oct Panel for decision 13/08/2026 - con+A118+AO121+A118+AO121 | 2027-06-24 | tbc | No
CP1643 Exempting certain Asset meters from BSCP601 EMC testing requirements for CoP 11 | BSC | For info | CP1643 | [36 empty] | 05/08/2026 - plan for August consultation, Oct SVG decision for March 27 release 03/08/2026 - added to tracker | 2027-03-25 | tbc | No
CP1642 Updating BSCP601 EMC requirements for EV Chargers and Domestic Appliances | BSC | For info | CP1642 | [36 empty] | 05/08/2026 - plan for August consultation, Oct SVG decision for March 27 release 03/08/2026 - added to tracker | 2027-03-25 | tbc | No
CP1644 Data Services to access Confidential Assurance Reporting Platform (CARP) | BSC | For info | CP1644 | [36 empty] | 21/09/26 - going to Oct SVG for end Oct release. 05/08/2026 - going for consultation August, implementation date being reviewed as SVG queried why it was planned for end of Oct when there is a standard release at start of Nov 03/08/2026 - added to tracker | 2026-10-29 | tbc | No
CP1650 – Extending the lapse period for Smart to Advanced Change of Market Segment | BSC | REC - R0342 | CP1650 | [14 empty] | R0342 | [21 empty] | 21/09/26 - consultation planned for Oct 03/09/2026 - REC and BSC co-ordinating to go to consultation together 18/08/2026 - agreed offline BSC to be lead code 17/08/2026 - Lead Code not decided, no BSC representation 05/08/2026 - added to tracker, expected to be raised by Eon following conversations with REC and BSC. Lead Code to be decided | tbc | SMRS | tbc
I0337 Change to Location (A0059) data item within the ONAGE APPT file to MAMs, from ‘Optional’ to ‘Mandatory’ | REC | tbc - believe none | [15 empty] | I0337 | [21 empty] | 21/09/26 - CMIA to be triggered 11/08/2026 - added to tracker | tbc | EMDS | tbc
I0341 Improved Validation for DI51599 - Electricity Smart Meter Equipment (ESME ID) | REC | BSC - tbc DIP - tbc SEC - tbc | tbc | [14 empty] | I0341 | [14 empty] | tbc | [6 empty] | 21/09/26 - REC discussions with SCS show there are several hundred impacted ESME IDs. They have already discussed with DCC a potential solution so SEC added as a potential impact 14/08/2026 - added to tracker, to monitor solution as there is potential for SMRS impacts. Potential to require DIP engagement as may look at DIP validation for this data item | tbc | MPRS, DTN, DIP | tbc
Pre-raise IF-045 notification for Import/Export MPAN meter type misalignment | BSC | BSC - tbc REC - tbc | tbc | [14 empty] | tbc | [21 empty] | 21/09/26 - expected to be raised Oct for BSC. REC expected to be the same 07/09/2026 - BSC assigned lead code, REC will raise change this week if haven't heard back from BSC about them raising 03/09/2026 - added to CCSG tracker, REC have confirmed impacts to Schedule 14. Lead Code to be decided - suspect BSC. | 2027-03-25 | DIP, DTN | tbc
I0344 Explore use of CHECK as a Meter Type option on J0483 / DI-059 | REC | BSC - tbc | tbc | [14 empty] | I0344 | [21 empty] | 03/09/2026 - added to tracker. Looking to remove CHECK from list of Meter Type enumeration values. Potential BSC impact - do any of your BSCPs require the use of this value? | tbc | DTN | tbc
I0346 Gas Enquiry Service Evolution, required REC changes | REC | For info | [15 empty] | I0346 | [21 empty] | 03/09/2026 - for information, shouldn’t impact any other codes but know other codes use the GES so may be of interest | tbc | GES | tbc
P520 Update the Manifest Errors process to align with revised MHHS Settlement Timetable | BSC | For info | P520 | [36 empty] | 21/09/26 - consultation ends 25/09/26. Going to Oct Panel 07/09/2026 - added to tracker - potential interest to NESO | 2027-02-25
P521 Allowing Licenced Generators to choose their BMU Lead Party in CVA | BSC | For info | P521 | [36 empty] | 21/09/26 - consultation due to be issued this week. Aiming for Nov Panel 07/09/2026 - added to tracker - potential interest to CUSC and NESO | tbc
DCR0023: Level 4 Validation – MPAN Invalid or Unknown (RCP1061) for IF-021s | DIP | BSC | [30 empty] | DCR0023 | [6 empty] | 21/09/2026 - Currently in further assessment, plan to review redlining and amend. DIP M will reconsult following this. DCR0023 proposes to amend the application of Level 4 validation code RCP1061 “MPAN Invalid or Unknown” for IF-021 messages. DIP CR0015 introduced Level 3 and Level 4 validation response codes, including RCP1061, which is mandatory for IF-021 but not IF-013 | TBC | DIP | tbc
I0347 - REC change to align with BSC IF-045 notification for Import/Export MPAN meter type misalignment | REC | BSC - tbc | tbc | [14 empty] | I0347 | [21 empty] | 21/09/26 - added to tracker | tbc
DCR0026: IF-036 Metering Service Routing to MDS | DIP | BSC | CP1645 | [29 empty] | DCR0026 | [6 empty] | 21/09/2026 - Targeted DIP routing change raised to align IF-036 Metering Service routing to MDS with CP1645. BSC lead code | 2026-11-01 | DIP | TBC

## Archive
Change Title |  |  | BSC |  |  |  |  | DCUSA |  |  |  |  | IGT UNC |  |  |  |  | REC |  |  |  |  | SEC |  |  |  |  | UNC |  |  |  |  | DIP | CUSC | Grid Code | SQSS | STC
Change Title | Lead Code | Other Codes impacts and number | Mod Number | IWA | W/G | DMR | FMR | DCP Number | IWA & TT | Report | Consult | Vote | Mod No | IWA | W/G | DMR | FMR | CP NO | CPP | IAR | PCR | FCR | Mod No. | I.A. & F.I.A. | W/G Report | Consultation | FMR | Mod No | IWA | WGR | DMR | FMR | CP No | Mod No | Mod No | Mod No | Mod No | Comment | Planned implementation date | Central System Impacted | Authority Determined | Comment archive
Resolution of Missing Messages following Central Switching Service implementation and integration with REC Change R0067 | UNC | [11 empty] | iGT170 | 2023-10-12 | 27/10.23 | 2023-11-20 | 2023-11-22 | R0067 | 2023-03-07 | 2023-03-07 | 2023-04-05 | 2023-06-21 | [5 empty] | 0836S | 2023-02-06 | 2023-08-17 | 2023-09-11 | 2023-09-25 | [5 empty] | 08/04: UNC Change implemented 18/12/23. R0067 is scheduled for implementation on 30 June 2023 the UNC change is still at the workgroup stage with the Report to be published upon completion . Going to Panel 24/11/23
Improving the use of the D0215 data flow in the relevant industry processes | BSC |  | CP1574 | 2023-06-05 | 2023-06-25 | 2023-08-03 | 2023-11-02 | [10 empty] | R0017 | 2023-01-21 | 2022-01-21 | 2023-03-31 | 2023-05-26 | [15 empty] | R0066 Approved on 20/12/2022, BSC to Implement 02Nov 2023
Uplift to CSS Maximum Demand Volumes during MHHS Migration Period | REC? |  | tbd |  |  |  |  | tbd | [9 empty] | R0093 | 2023-04-06 | 2023-03-23 | 2023-11-29 | 2024-01-12 | [15 empty] | 18/04/24 - implemented April 24 KK to check, BSC will be Lead Code should there be impacts on the BSC
Clarify obligations on gas meter exchanges that occur close to CoS | REC | [16 empty] | R0094 | 2023-10-04 | 2023-10-04 | 2024-03-29 | 2024-06-05 | [15 empty] | 13/06/24 - CP approved 12/06/24 for Nov 24 release. 18/04/24 - discussions have been held with CDSP - no impact expected Potential impact on UNC, BF to check
Charging for de-energised sites | BSC |  | tbd |  |  |  |  | DCP411 | 2023-01-05 | 2023-04-28 | 2023-05-19 | 2023-06-13 | [5 empty] | R0133 | 2023-07-18 | 2023-07-18 | 2023-09-22 | tbd | [15 empty] | Ofgem rejected DCUSA DCP 18/04/24 - REC change withdrawn as no updates. Another can be raised when ready Still needs a BSC CP, ofgem decision delay to Jan 31st 2024
Aligning electricity and gas timescale requirements for sharing Meter Technical Detail information | REC | [16 empty] | R0109 | tbc | [18 empty] | 18/04/24 - CP withdrawn 22/03/24
Provision of Grid Supply Point Group ID from a Postcode search | REC | [16 empty] | R0111 | tbc | [18 empty] | 18/04/24 - CP rejected 05/04/24
Change the Logical Format of the J0001 (DI50001) ‘Market Participant Role Code’ data item to Char(2) | BSC | Yes | CP1589 | Withdrawn | Withdrawn | Withdrawn | Withdrawn | [10 empty] | R0116 | tbc | [18 empty] | 18/04/24 - REC change withdrawn as BSC only change. BSC CP was raised but now withdrawn and waiting until after MHHS completion
Aligning the Capacity requirements for NExA Supply Points with UNC for LDZX CSEPs Ancilliary Agreements | UNC | [11 empty] | iGT169 | 2023-09-14 | 2023-09-22 | 2023-10-02 | 2023-10-24 | [10 empty] | 0701 | [9 empty] | 08/04: Implemented 04/11/2023 9/10 Relates to UNC 701 /UNC 853- waiting to be implemented - Long date to implementation 4/11/23. With Ofgerm 13/11/23
Settlement Adjusmtents fo SMP Impcatied by P1 CSS Impact | UNC | [11 empty] | IGT171 | 2023-10-12 | 2023-10-20 | 2023-10-30 | 2023-11-22 | R0067 | 2023-03-07 | 2023-03-07 | 2023-04-05 | 2023-06-21 | [5 empty] | 0855 | UNC Mod Completed before IGT Mod Raised | [8 empty] | 18/04/24 - REC change implemented 08/04: Awaiting Implementation. IGT & REC IMPACT 9/10 REC 67 helps mitigate prolonged adjustment periods, Release 6/12/23. out for consultation 13/11/23, Panel 24/11/23
Permitting DNOs to charge Shippers negative Supplier of Last Resort (SoLR) unit rates | UNC | [26 empty] | 0865 | 2023-05-12 |  |  | 2024-08-03 | [5 empty] | 08/04: Implemented
Amendments to Demand Side Response (DSR) Arrangements | UNC | [26 empty] | 0866S | 2024-08-01 |  |  | 16/05/24 | [5 empty] | 08/04: IGT IMPACT. Possible IGT UNC impact identified - Workgroup still looking at.
Gas Demand Side Response (DSR) Aggregation Arrangements | UNC | [26 empty] | 0867 | 2024-08-01 |  |  | 19/09/24 | [5 empty] | NO CROSS CODE IMPACTS? Possible IGT UNC impact identified - Workgroup still looking at.
0822 - Reform of gas Demand Side Response Arrangements (UNC Urgent Mod) | UNC | [11 empty] | IGT167 | 2023-07-13 |  | 2023-08-11 | 2023-08-14 | [10 empty] | 0822 | 2022-09-05 | 2022-09-08 | 2023-05-18 | 2022-09-28 | [5 empty] | Implemented 31/8/23
0841A - Introduction of cost efficiency and transparency requirements for the CDSP Budget, and revisions to DSC change processes | UNC | [26 empty] | 0841/A | 2023-03-16 | 2023-11-16 | 2024-02-15 | tbc | [5 empty] | 08/04: Awaiting Ofgem Decision. IGT IMPACT CCSG Members did not think there would be any significant changes to other Codes. The IGT UNC may be impacted depending on how UNC change their section. 13/11/ Not yet implemented - panel agreed wgp extension to Feb 2024. IGT Workgroup confirmed no impacts to IGT UNC.
0856 - Introduction of trials for NDM Demand Side Response | UNC | [26 empty] | 0856 | 2023-09-08 | 2023-11-16 | 2023-12-07 | 2023-12-12 | [5 empty] | 08/04: Awaiting Implementation - Date TBC. IGT IMPACT Will impact iGT UNC. Proposer has decided to cease trials so no IGT UNC Mod required at this time.
0863S - ET Exception Process | UNC | [16 empty] | tbc | [9 empty] | 0863S | 2023-11-16 | 2024-02-15 | 2024-03-07 | 2024-03-12 | [5 empty] | 08/04: Reporting to Panel 16/05/24 Need to check REC impacts and iGT impacts
CP1589 - Create Additional Market Participant Role Codes / Change the Logical Format of the J0001 (DI50001) ‘Market Participant Role Code’ data item to Char(2) | BSC | Yes | CP1589 | [34 empty] | 05/08/24 - change withdrawn 17/06/24 - Name updated. ACTION - Elexon to confirm current status. R132 withdrwan, waiting for new BSC CP. 9/10 - progressing as a BSC only change, to be implemented in November 2024
0869 - Revision to the Calculation Methodology of the Security Amount for Planning and Advanced Reservation of Capacity Agreement (PARCA) | UNC | [16 empty] | tbc | [9 empty] | 0869 | 2024-11-03 |  |  | 29/06/24 | [5 empty] | 28/06: Expecting this to be Withdrawn NO CROSS CODE IMPACTS? 11/07: WITHDRAWN
0875S - Minor amendment to the Vacant Site exit process & 0819 Legal Text re-numbering | UNC | [16 empty] | tbc | [9 empty] | 0875S | 2024-05-04 | [8 empty] | 05/08 - removed as now linked to 0819 30/07: Linked to 0819. The changes proposed in this Modification do not impact IGT 168 which was raised to ensure the Vacant Site Process can apply to IGT Supply Meter Points. 28/06: Reporting to July 2024 UNC Panel. 08/04: Panel Assessment 16/04/24. IGT UNC Workgroup not yet reviewed. 20/05/2024 - IGT impacts upon IGT sites but not IGT codes.
0877S - Alignment of TO Revenue and TO Revenue Adjustment terms to the current Gas Transporter Licence | UNC | [26 empty] | 0877S | [9 empty] | 28/06: Implementation due 12/07/24 IMPLEMENTED
0921S - Broadening the definition of the Data Permissions Matrix to align with disclosure of UK Link Gemini data | UNC | IGT UNC | [10 empty] | IGT182 | [14 empty] | 0921S | [11 empty] | 29/05: Approved at May UNC Panel and to be implemented 15 June 2026 15/05: Consultation closed 08 May and due for Decision in May UNC Panel. IGT mod has now been raised (IGT182) as a fast track mod, expecting decision in June. May be a short period of misalignment as IGT mod will likely be implemented shortly after the UNC one. 17/04:- Consultation started 16 Apr and closing 08 May 2026 16/02: will impact IGT UNC 30/01: Distribution Workgroup due to report to UNC Panel 21 May 2026 09/12: Modification Raised | 2026-06-15 | None | No
0923 Disapplication of TPD Section D7 (DSR Options) for 2026 only | UNC | IGT UNC | [10 empty] | tbc | [14 empty] | 923 | [11 empty] | 31/07: Auhority rejection 14 July 03/07: EDD listed as 13 July 2026 29/05: May UNC Recommended not to Implement and this is now awaiting Authority Direction 15/05: Consultation closed 08 May and Panel Recommendation to be consider at May UNC Panel meeting 17/04 : Consultation Started 16/04 and closing 08 May 2026 27/02: Modification Assessed by Feb UNC Panel and assigned to Transmission Workgroup to report 21 May 26 | tbc | None | None
R0181 - Schedule 14 - Metering Operations Footnote Review | REC | [16 empty] | R0181 | 2024-06-11 | 2024-06-11 | n/a | 2024-06-19 | [15 empty] | 05/08/24 - no cross code impacts confirmed 13/06/24 - removal of all footnotes ahead of rewrite for MHHS. No cross code impacts expected
CP1594 - Removing the Enumerations from Communications Method Data Item (J0386) to align with BSC CP 1594 | BSC |  | CP1594 | 2024-02-04 | N/A | 2024-07-05 | 2024-07-05 | [10 empty] | R0164 | 2024-04-18 | 2024-04-24 | 2024-05-23 | 2024-06-20 | [15 empty] | 13/06 - REC Change approved, pending implementation
0842 - Gas Entry onto the Total system via an Independent Gas Transporter | UNC | [11 empty] | iGT172 | 2023-11-09 | 2024-01-26 | 2024-02-19 | 2024-03-22 | [10 empty] | 0842 | 2023-04-20 | 2023-12-14 | tbc | tbc | [5 empty] | 08/04: Awaiting Ofgem Decision. IGT IMPACT UNC Panel voted that there were Cross Code impacts - panel extended to align with iGT change, update dates 23/11/23 Next workgroup meeting. Panel decision 24.11 for iGT UNC 29/07: UNC0842 & IGT172 approved by Authority. Implementation expected in August 2024. 16/09: Both UNC and IGT UNC Modifications implemented on 12th August 2024.
0873 - Add specific roll-over functionality for the AUG Table 2025/26 | UNC | [26 empty] | 0873 | 2024-05-04 | [8 empty] | 30/07: The CDSP view is that an IGT modification is not required as the IGT UNC Part F points to the UNC for DAILY AND ANNUAL QUANTITIES AND SHRINKAGE. No objections or concerns were raised by Workgroup participants. 28/06: Reporting to July 2024 UNC Panel. 08/04: Panel Assessment 16/04/24. IGT UNC Workgroup not yet reviewed. | 2024-09-10
0878 Use of Entry Capacity Holdings at Easington at the Rough Storage ASEP in Winter 2024/2025 | UNC | [26 empty] | 0878 | [9 empty] | 28/06: Reporting to July 2025 UNC Panel. NO IGT IMPACTS | 2024-09-10
0883 - Update to the Annual Quantity (AQ) amendment process for Erroneous Domestic AQs | UNC | [26 empty] | 0883 |  | 16/01/25 | 17/01/25 | 2025-11-02 | [5 empty] | WITHDRAWN 28/06: Reporting to January 2025 UNC Panel. IGT party Impact, potental code impact
R0105 - Review of ONAGE SLAs | REC | [16 empty] | R0105 | 2024-04-05 | 2024-04-16 | 2024-07-05 | [16 empty] | REJECTED 18/04/24 - discussions with CDSP to date suggest no impact. | n/a
R0072 - Introduction of a new Meter Asset Condition Code | REC | n/a | [5 empty] | TBC | [9 empty] | R0072 | [19 empty] | REJECTED 13/06/24 - Ofgem discussion limited due to pre-election period. Proposer to be contacted to withdraw the change. 30/05/24 - to be discussed with Ofgem w/c 03/06/24 as consumer impact but limited scope within the codes 16/05/24 - discussions ongoing with proposer. Request REC CP is withdrawn and replaced with a cross code issue with DCUSA. Also ties in with STIR | n/a
I0204 - Sequence order of CSS00200 message | REC | BSC - tbc, DCUSA - tbc, SEC - tbc | tbc |  |  |  |  | tbc | [9 empty] | I0204 |  |  |  |  | tbc | [14 empty] | WITHDRAWN as covered by MHHS programme CR0056 | tbc
0871 - Facilitating IGTs with NTS Entry | UNC | n/a | [25 empty] | 0871 | 2024-05-04 | [8 empty] | WITHDRAWN 30/07: None. All the requirements for gas entering and exiting an IGT network are already covered, including within IGT172 – Provision for gas entry within the IGT UNC. Extended to September 2024. 28/06: Reporting to August 2024 UNC Panel. 08/04: Panel Assessment 20/05/24. IGT UNC Workgroup - still on watch list whilst the changes to the UNC are drafted. | tbc
R0170 - Withdrawal of Service Termination Issue Reporting Guidance (STRIG) from REC Governance | REC | n/a | [15 empty] | R0170 | 2024-05-31 | 2024-06-06 | 2024-07-25 | 2024-09-05 | [15 empty] | 18/11/24 - Authority rejected as per Code Manager recommendation 07/10/24 - with Authority for approval. Code Manager recommended it be rejected 16/09/24 - no cross code impact identified 16/05/24 - following on from R0145. Moving it to ENA | tbc
0819 - Amending Vacant Sites Process and 0875S - Minor amendment to the Vacant Site exit process & 0819 Legal Text re-numbering | UNC | iGT168 | [10 empty] | iGT168 | 2023-09-14 | 2023-11-24 | 2023-12-18 | 2023-12-19 | [10 empty] | 0819 | 2022-11-15 | 2023-10-19 | 2023-10-20 | 2023-11-21 | [5 empty] | 11/11 - 0819 & 0875S pending implementation on 08/11/24 30/07: Linked to 0875S: No implementation date set yet. Expected to be in the November major release. That said, 0819 cannot be implemented unless/until 0875 is approved as they both need to be implemented at the same time. The plan therefore is to wait till 0875 is approved and then check with Xoserve on exact date of the major release before, the implementation date for 0819 and 0875S will then be set. IGT IMPACT 08/04: Ofgem approved implementation on a date TBC. No legal drafting available, TL to review legal text and review impacts on IGT UNC, update to be provided at April 2023 CCSG meeting. iGT 168 raised. | 2024-08-11
R0203 - CSS Retry Strategy | REC | BSC - tbc, UNC - tbc, iGT UNC- tbc, DCUSA - tbc | tbc |  |  |  |  | tbc |  |  |  |  | tbc |  |  |  |  | R0203 | 2024-09-10 | 2024-09-10 | [7 empty] | tbc | [9 empty] | 07/10/24 - with REC service providers to determine solution options | 2024-11-01
R0206 - Cross code change to align with BSC CP1598 | BSC | BSC - CP1598 | CP1598 | [14 empty] | R0206 | [20 empty] | 2024-11-01
R0220 - Housekeeping Change for R0206 | REC | Watching brief only | [15 empty] | R0220 | [20 empty] | 2024-11-01
CP1596 - Amend BSCP40 to include the process for changes to the Retail Energy Code Energy Market Data Specification | BSC | n/a | CP1596 |  |  |  | 2024-07-02 | [31 empty] | 2024-11-01
P474 - Governance, funding and operation of the DIP | BSC | REC - R0208 | P474 | 13/06/2024 | N/A | 2024-08-08 | 2024-09-08 | [10 empty] | R0208 | [19 empty] | 02/09/24 - see below. REC change raised to add DIP to CCSG ToR attendee list 17/06/24 - ACTION - DCUSA, REC and SEC to review and respond to consultation. 20.06.24 - Initial SEC review do not believe P474 has SEC impacts (DIP is downstream of SEC, which manages comms between meter and DCC Users) 13/06/24 - REC CP to update CCSG ToR to include DIP will be raised w/c 17/06. Draft CP currently with the MHHS programme for review | 2024-10-01
P455 - On-site aggregation as a method to facilitate third party access | BSC | REC - R0150 | P455 | 2023-06-01 | 2024-01-01 | 2024-02-01 | 2024-02-01 | [10 empty] | R0150 | 2023-12-08 | 2023-12-08 | 2024-03-22 | 2024-04-26 | [15 empty] | 30/05/24 - REC change approved and pending implementation June 24 13/11/23 - Sandbox on the BSC, possible REC Change and DCUSA Change. BSC to send details to DT at DCUSA. SEC don't believe they're impacted. | REC - June 24 BSC - Sept 24
I0199 - A process for resolution of Gas unregistered sites | REC | UNC - tbc, iGT - tbc | [10 empty] | tbc |  |  |  |  | I0199 |  |  |  |  | tbc |  |  |  |  | tbc | [9 empty] | 02/12/24 - withdrawn as covered by I0172. 07/10/24 - expected to be rejected as most issues covered by I0172. Also shipperless process not covered by the REC so all issues to be handed to the UNC / iGT UNC once I0172 completes. 29/07/24 - raised by REC Performance Assurance. Potential cross code impacts on UNC / iGT UNC. Also potential to tie in with I0172 | tbc
I0184 - Gas Meter Type Code - Thermal Mass Measurement | REC | UNC - tbc, iGT - tbc | [15 empty] | R0184 | [19 empty] | 16/12/24 - withdrawn 28/06/24 - Potential SEC Impact….? What size metering change is this for and is it a physical hardware change? | tbc
I0195 - Addition of MEMs to the Gas Enquiry Service (GES) API. | REC | UNC - tbc | [10 empty] | tbc |  |  |  |  | I0195 |  |  |  |  | tbc |  |  |  |  | tbc | [9 empty] | 16/12/24 - rejected 07/10/24 - expected to be withdrawn and follow the data access process 29/07/24 - raised by REC Performance Assurance. No cross code impacts expected | 2024-12-02
R0144 - Allowing different Metering Equipment Managers (MEMs) to be appointed to Import and Export Metering Points | REC | BSC - P459 | P459 | 2023-08-01 | 2024-02-23 | N/A | N/A | [10 empty] | R0144 | 2024-04-16 | 2024-04-16 | tbd | tbd | [15 empty] | 31/01/25 - R0144 withdrawn 20/01/25 - P459 has been withdrawn by proposer. Status of R0144 is TBC 02/12/24 - waiting to see what proposer wants to do next. They recognise R0207 and MHHS will solve most of their issues. 07/10/24 - R0207 has been raised 05/08/24 - R0144 now adopted by BSC Mod proposer. REC working on an alternative CP to resolve some of the issues raised in these changes. 17/06/24 - BSC dates updated 30/05/24 - REC Change Plan withdrawn as totally dependent on BSC Mod to progress 18/04/24 - first working group held March 24. REC attended. 13/11 1st workgroup to be held in January. BSC Don't want to start in December, due to engagement levels/Christmas. SEC interested in this mod. Will join the BSC w/group. DP206 reliance on P459 progression | tbc
R0168 - Clarify & strengthen CRS Providers requirements | REC | All - n/a | tbc | [14 empty] | R0168 | 2024-07-18 | 2024-07-18 | 2024-12-12 | 2025-02-04 | [5 empty] | tbc | [9 empty] | 03/02/25 - to be voted on at Change Panel on 04/02/25 16/12/24 - due to be issued for industry Consultation 20/12/24 04/11/24 - expected to be a REC Guidance document. Solution development continues 30/05/24 - going to REC Change Issues Group on 06/06/24. Other codes requested to attend 16/05/24 - following the new issues process. Possible impact on Xoserve / MPRS TBC | 2025-02-28 | n/a
R0208 - Adding the DIP Rules to the CCSG ToR | REC | n/a | [15 empty] | R0208 | 2024-08-29 | 2024-08-29 | 2024-08-29 | 2024-11-22 | [15 empty] | 16/12/24 - approved and pending implementation 02/12/24 - final vote at Change Panel on 03/12/24. 02/09/24 - no cross code impact but listed as updating CCSG ToR | 2025-02-28 | n/a
R0210 - Evolution of the CRS Performance Charge | REC | Watching brief only | [15 empty] | R0210 | 2024-10-14 | 2024-10-14 | [17 empty] | 16/12/24 - approved, pending implementation | 2025-02-28 | n/a
P477 Data Protection Provisions for Market-wide Half Hourly Settlement | BSC | DCUSA - tbc, REC - tbc, SEC - tbc | P477 | 2024-08-08 | N/A | 2024-10-10 | 2024-10-17 | tbc | [9 empty] | tbc | [19 empty] | 23/01/2025 - approved for implemented in March 2025 | 2025-03-07
R0183 - DPI Extract from CSS | REC | n/a | [15 empty] | R0183 | 2024-07-16 | 2024-07-16 | [17 empty] | 01/04/25 - withdrawn 16/12/24 - awaiting IA from CSS service provider 27/06/24 - no direct impact but BSC, UNC and iGT UNC all have or will have some form of domestic indicator. This CP is first step with potentially more CPs to follow | tbc | CSS | N
R0217 - Amending contractual obligations for SIPs at Non-Domestic Premises | REC | Watching brief only | [15 empty] | R0217 |  |  | 2025-01-23 | [16 empty] | 03/03/25 - due to be presented at March MEP 13/02/25 - industry consultation closes 14/02/25 | 2025-04-01 | n/a | N
R0246 - Domestic Premises Indicator Clarifications | REC | BSC - tbc, UNC - TBC, iGT UNC - TBC | tbc | [9 empty] | tbc |  |  |  |  | R0246 | [9 empty] | tbc | [9 empty] | 24/04/25 - withdrawn |  | CSS - tbc | tbc
P476 - Exemption from MHHS Requirements for SMS Supplier Qualification | BSC | REC - I0194 | tbc |  |  |  |  | tbc | [9 empty] | I0194 |  |  |  |  | tbc | [14 empty] | I0194 - issue now resolved. Will not progress to CP 19/05/25 - solution now not system based. Will monitor with reporting. 24/04/25 - update to be provided to REC TEP on 30/04/25 03/03/25 - I0194 with CSS service provider for IA 20/01/25 - linked but do not have to be implemented together 29/07/24 - I0194 - CSS Change to Allow Prevent of Registration by Market Segment - assumed BSC led as paper from BSC PAB. However change will be delivered by CSS so decision required | BSC - implemented 27/02/25 REC - n/a | CSS, ERDS
P442 - Chargeable Volumes for Exempt and Licenced Supply reporting | BSC | REC- R0193 | P442 | 2022-08-08 | 2023-11-01 | 2024-01-01 | 2024-01-01 | [10 empty] | R0193 | 2024-09-05 | 2024-09-05 | 2024-10-11 | 2024-11-19 | [15 empty] | 16/12/24 - REC change approved, pending implementation. 29/07/24 - Elexon raised REC Issue to look at resolving the lack of MDD options. Linked to P442. 17/06/24 - ACTION - Elexon to confirm status and update on expected REC impacts Had first workgroup meeting, very early stages not confirmed impact on REC at this stage, impacts on REC will be considered throughout development - 9/10 No REC Impact envisaged, but IM will update after the meeting. 02/06/25 - P442 was implemented on 27/02/25. EMDS changes for new SVs for D0036 and D0275. No REC impact | REC - Jun 25 BSC - 27/02/25 | DTN | Y
R0236 - REC Party Auto de-accession proposal | REC | Watching brief only | [15 empty] | I0236 | [19 empty] | 03/06/25 - approved by Rec Change Panel 19/05/25 - collating final change report 24/04/25 - industry consultation closes 08/05/25. | 2025-06-27 | n/a | tbc
R0233 - Introduction of an Energy Theft Unit (ETU) under the REC | REC | Watching brief only | [15 empty] | R0233 | [19 empty] | 19/05/25 - awaiting Authority decision, approved by Change Panel. 24/04/25 - industry consultation closes 25/04/25. 03/03/25 - legal text confirmed. Preparing change report | 2025-06-27 | n/a | Y
I0234 - Introduction of an energy theft Referral Assessment Service under the REC | REC | Watching brief only | [15 empty] | I0234 | [19 empty] | 19/05/25 - Change Panel decision on 20/05/25, then goes to Authority for final approval. 24/04/25 - industry consultation closes 09/05/25. 03/03/25 - industry IA being prepared | 2025-06-27 | n/a | Y
R0193 - Add Enumeration Values to the DI51035 - Communications Provider Data Item | REC | BSC - MDD only | MDD only | [14 empty] | R0193 | 2024-09-05 | 2024-09-05 | 2024-10-11 | 2024-11-20 | [15 empty] | 16/12/24 - approved, and pending implementation 18/11/24 - REC consultation closed. Industry picked option B so original list in MDD will be cleansed as part of this implementation. Old codes removed and up to date ones added. List removed from MDD in Oct 24. REC implementation planned for Jun 25 so industry risk. | REC - Jun 25 MDD - implemented Oct 24 | DTN | N
R0225 - Clarification on TDIS portfolio transfers on sale | REC | Watching brief only | [15 empty] | R0225 | [19 empty] | 19/05/25 - approved pending implementation 24/04/25 - final determination due at Change Panel 06/05/25. 01/04/25 - out for industry consultation | 2025-06-01 | n/a | N
I0174 - Mandating ETTOS Follow up | REC | Watching brief only | [15 empty] | I0174 | [19 empty] | 22/07/25 - Issue moved to Resolved, problem statement resolved by R0173 21/07/25 - with RECCo to discuss TIG feedback and next steps 20/01/25 - awaiting outcome of R0173 30/05/24 - theft change. No expected cross code impact | tbc | n/a | tbc
CP1613 Transfer of ownership of four Data Items in the REC’s Energy Market Data Specification from BSCCo to RECCo | BSC | REC | [35 empty] | Moved to archive as duplicate of R0243 line - captured CP1613 on there Raised to complement R0243. | 2025-11-25 | EMDS | n/a
R0169 - Introduction of Gate Closure Notifications | REC | BSC - tbc, UNC - tbc, iGT UNC- tbc, SEC - tbc, DCUSA - tbc | tbc | [14 empty] | R0169 | [9 empty] | tbc | [9 empty] | 29/08/25 - change withdrawn, adoption window open until 12/09/25 01/08/25 - being presented at CHIG 07/08 04/11/24 - awaiting DCC IA 16/05/24 - Possible impact on Xoserve / MPRS TBC | tbc | CSS | N
DP301 Review of Additional Registration Data (Gas Transporters) | SEC | REC | [15 empty] | TBC |  |  |  |  | DP301 | [14 empty] | line not required - duplicate of row 83 10.09.25 - Proposal that Gas Transporter SEC obligations to provide Regsitration Data would better sit in the REC. Proposal going to Change Sub Committee September for review.
Issue 112 - Clarifying Half Hourly Data Collector (HHDC) obligations within BSCP502 (Half Hourly Data Collection for Supplier Volume Allocation (SVA) Metering Systems Registered in Supplier Meter Registration Service (SMRS)) regarding the fault investigation process. | BSC | DCUSA - tbc, REC - I0197 | Issue 112 | N/A | 2024-04-10 | N/A | N/A | tbc | [9 empty] | I0197 | [19 empty] | 11/09/25 - Code Manager working through actions, next work groups expected October (exact dates TBC) 01/08/25 - I0197 work groups held on 18/06, 09/07 and 17/07. More booked in for 07/08 and 12/08 16/06/25 - new working group holding first meeting on 18/06/25. 24/04/25 - I0197 to be split into 3, gas, electricity and one on D0302. Gas and electricity Issues will be discussed together at a stand alone working group, date tbc. 04/11/24 - REC RFI issued to get views on options 29/07/24 - REC Issue I0197 has been raised as a dual fuel option looking at fault resolutions. Decision needed if should combine with this issue. 17/06/24 - ACTION - Elexon to confirm current status. 18/04/24 - discussions have been held with REC performance assurance only. REC change has joined the issue group to help establish REC impact, particularly Schedule 14 and flows 02/06/25 - 2nd Issue group was in August 24... | tbc | tbc | tbc
R0173 - Improvements to the Theft Detection Incentive Scheme | REC | Watching brief only | [15 empty] | R0173 | 2024-08-13 | 2024-08-13 |  | 2024-11-26 | [15 empty] | 22/09/25 - implemented 02/06/25 - approved by the Authority. Implementation date to be set by R0259 24/04/25 - Authority passed back. Response provided and now back with them for determination. 16/12/24 - with Authority for final decision. 02/12/24 - going to Change Panel on 03/12/24 for final vote before Authority decision. 04/11/24 - number now updated to R as final solution established 30/05/24 - theft change. No expected cross code impact | 2025-09-22 | n/a | Y
P478 - Implementation of MHHS Arrangements | BSC | DCUSA - DCP445, REC - R0209 | P478 | 2024-09-12 | N/A | 2024-11-06 | 2024-11-07 | DCP445 | [9 empty] | R0209 | 2024-09-10 | 2024-09-10 | n/a | [16 empty] | 22/09/25 - implemented 16/12/24 - all approved pending implementation Three further Mods to be raised to amend the BSC Sections and Code Subsidiary Documents for M86/2/2025: - one to amend references to HH to 'UTC Period' (Pxxx) - one to align documentation with final MHHS Design (Pyyy) - one to amend SVAA service to allow 3 separate SVAA BSC Agents One CP to align SVA Data Catalogue with MHHS version of EMDS | MHHS M8 | MHHS SCR | Y
I0222 -ESME ID Update Rejections | REC | REC only - no cross code | [15 empty] | I0222 | [19 empty] | 22/09/25 - implemented 25/06/25 - approved with M8 as implementation date 02/06/25 - final change report being drafted 19/05/25 - out for industry consultation, closes 23/05/25 24/04/25 - Code Manager reviewing the service provider IA. 13/03/25 - solution amended to mirror IF-005 validation and not progressing. 13/02/25 - discussions ongoing with DNOs, MHHS Programme and REC on timings of an update to the validation. 20/01/25 - update to be provided at Change Issues Group on 6th Feb 16/12/24 - REC working on sampling rejections with DNOs and MOAs to establish route causes to investigate | MHHS Programme Milestone M8 (Code changes delivered) | ERDS | N
R0241 - MHHS Incremental Changes for Go Live | REC |  | P489 |  |  |  |  | tbc | [9 empty] | I0241 | [19 empty] | 22/09/25 - implemented 14/08/25 approved for implementation at M8 16/07/25 - sent to Authority for determination | MHHS M8 | tbc | Y
R0259 - Update to R0173 Implementation Date | REC | Watching brief only | [15 empty] | R0259 | [19 empty] | 15/07/25 - approved for implementation on 22/09 07/07/25 - consultation has closed, final vote due 15/07/25 | 2025-09-22 | n/a | N
P486 Aligning BSC Terminology with the Terminology Introduced by P478 | BSC | None - for information | P486 | [34 empty] | 22/09/25 - implemented 24/07/25 - approved Impacts M8 baseline approved for P478. The P486 Final Modification Report was submitted to the Authority on 17 June 2025. | 22/09/2025 | N
P489 - P489 Update approved P478 for alignment with the latest MHHS Design | BSC | None - for information | P489 | [34 empty] | 22/09/25 - implemented 07/08/25 - approved Impacts M8 baseline approved for P478..Authority Led SCR Modification Report submitted to Authority | 22/09/2025 | N | N
P490 - Introduction of three new BSC Agents to provide the SVAA Service | BSC | None - for information | P490 | [34 empty] | 22/09/25 - implemented 18/08/25 - P490 approved in July and new SVAA Service Descriptions and amended BSCP508 and BSCP703 approved in August Impacts M8 baseline approved for P478. Will go to July Panel for approval | 22/09/2025 | N | N
CP1603 Updating the SVA Data Catalogue to reference new and amended interfaces | BSC | None - for information | CP1603 | [34 empty] | 22/09/25 - implemented Impacts M8 baseline approved for P478.Approved for M8 on 3 June. | 22/09/2025
DP299 - Update Citizens Advice Scotland to Consumer Scotland | SEC | None - for information | [20 empty] | DP299 | [14 empty] | 26.09.25 - Change to be implemented 07 October 25) 10.09.25 - Change proposal going to September Change Sub Committee for decision to progress. The Consumer Scotland Act 2020 (Consequential Provisions and Modifications) Order 2022 replaced references in the Electricity Act 1989 and the Gas Act 1986 and various other energy-related legislation to ‘Citizens Advice Scotland’ with ‘Consumer Scotland’. This confirms that energy-related functions are now being exercised by Consumer Scotland instead of Citizens Advice Scotland. Proposal will not impact other codes directly, as SEC text change, but other codes that ref Citizens Advice Scotland and that have yet to update may wish to take note. 07.10.25 - Change Implemented SEC V121.0 self governance Modification. | 2025-10-07 | n/a | n/a
P496 Defining DIP Manager Data and its access and use (also DIP Change Request 0004) | BSC | REC - no cross code required, listed as a recipient party | P496 | [29 empty] | DCR0004 |  |  |  |  | 10/10/2025 - approved for 22/10/25 implementation This Modification will clarify in the DIP Rules that due to the transactional nature of data in Common Blocks, this data shall be defined as DIP Manager Data for service management and issue resolution. Establish a mechanism for sharing DIP Manager Data, including from Messages’ Common Blocks, with relevant stakeholders like Code Bodies, ensuring a clear legal basis for sharing personal information, such as MPAN data, when necessary. | M11 (22 October 2025) | N/A | n/a
0902R - EU Capacity Allocation Mechanism Network Code Review | UNC | iGT - no impact | [25 empty] | 0902R | [9 empty] | 17/10: Request to close Review Group agreed by Oct UNC Panel Raised 06/12/2024 reporting 18/12/2025
0901R - Review of the arrangements for reservation of NTS Capacity | UNC | iGT - no impact | [25 empty] | 0901R |  | TBC | n/a | n/a | [5 empty] | 17/10: Request to close Review Group agreed by Oct UNC Panel 17/07: Reporting extended to October 25 04/07: Reporting extended to July 25 UNC Panel 29/05: Reporting to June UNC Panel. 07/04: Update provided to CCSG - Reporting to June UNC Panel. 11/11: New Request - consideration at November 2024 UNC Panel | n/a
0913S - Amending referencing and naming errors in TPD Section B and V | UNC | iGT - no impact | [25 empty] | 0913S | [9 empty] | 17/10: Panel instructed implementation - awaiting date direction 03/10: Consutation closed 02 Oct ahead of Final Report to October 2025 UNC Panel 21/08 Reclassified from FT to SG allocated to Workgroup reporting 18 Sept Panel 18/08: New Housekeeping Fast track Mod raised 12 August for UNC Panel and decision in 21 August Meeting | 2025-11-10
0879R - Review of current Supply Meter Point Classes (Class 1, 2, 3 and 4) | UNC | iGT - tbc, REC - tbc | [10 empty] | tbc |  |  |  |  | tbc | [9 empty] | 0879R | [9 empty] | 17/10: Request to close Review Group agreed by Oct UNC Panel 03/10: Extended - Reporting to Jan 26 UNC Panel 04/07: Extended - Reporting to Oct 25 UNC Panel 2/06 : No change, reporting to July 25 UNC Panel 11/11: Reporting to August 2025 UNC Panel. IGT & REC IMPACTS | tbc
0910S - Amendment to DSC T&Cs to include a requirement to provide data incident contact details | UNC | iGT - no impact | [25 empty] | 0910S | [9 empty] | 01/12: Nov UNC Panel voted unanimously to Implement, awaiting implementation date 15 Dec 25 14/11: Consultation closed to be considered at Nov UNC Panel 03/10: Consulation underway until 09 October ahead of October 2025 UNC Panel Decision 01/07: Assessed at June UNC Panel and assigned to Workgroup (Gov) reporting back 18 Sept 2025.No Cross Code Impacts thought to exist at this stage 12/06: New Proposal Received for June UNC Panel Consideration | 2025-12-15
0912S - PARCA Quarterly NTS Entry Capacity minimum duration quantity | UNC | IGT UNC - no impact | [25 empty] | 0912S | [11 empty] | 01/12: Nov UNC Panel voted unanimously to Implement, implementation date tbc 14/11 Consultation closed and to be Consider at Nov UNC Panel 17/10 Issued to Consultation 03/10: Workgroup Reporting to October 2025 UNC Panel 17/07 New Proposal received for July 25 UNC Panel and issued to Workgroup (Trans) to report back 16 Oct 25 | 2025-12-12
0897S - Removal of Non-Obligated Entry Capacity from Capacity Neutrality | UNC | None reported | [10 empty] | tbc | [14 empty] | 0897S |  | 16/01/25 | 17/01/25 | 2025-11-02 | [5 empty] | 01/07: Implemented 20/06: Implementation instructed for 01 July 25 29/05: Awaiting implementation - date TBC. 07/04: Update provided to CCSG - Awaiting implementation - date tbc. 11/11: Reporting to February 2025 UNC Panel - Cross Code Impact tbc | 2025-07-01 | CDSP - Gemini
0862 - Amendments to UIG Reconciliation Period | UNC | REC - None noted | [15 empty] | None Noted | [9 empty] | 0862 | 2023-11-16 | 2024-05-16 | 2024-06-10 | 2024-06-20 | [5 empty] | 01/07/25: Implemented 29/05/25: no update on implementation date 07/04/25: no update on implementation date 02/12/2024 - approved but implemented date TBC 04/11 - with Authority for decision 08/04: Reporting to Panel 18/07/24. REC IMPACT Possible REC Impact reported by REC party | tbc |  | Approved 03 December 2024
0881S - Review and consolidation of UNC Transition Document TDIIC - Transitional Rules | UNC | IGT175 | [10 empty] | iGT175 | [14 empty] | 0881S |  | 17/10/24 | 18/10/24 | 2024-03-12 | [5 empty] | 29/05: NFA for UNC 19/05 - IGT175 picking up required IGT UNC changes, going to May IGT UNC Panel for final decision, implementation in June 2025. 07/04: Update provided to CCSG. UNC 0881S Implemented 15 Jan 25 17/03: IGT Mod raised which makes changes to IGT UNC needed following UNC0881, as these changes were on our housekeeping log. Will be considered by Panel on 28th March and WG in April, IGT175 will be 11/11: Within Consultation and will report back to December UNC Panel 28/06: Reporting to October 2024 UNC Panel. IGT Impact | UNC 0881S implemented 15/01/25 iGT UNC - tbc |  | N
Derogation D0001 - Hydrogen Blending: An NTS Transportation and Power Station Consumption Demonstration | UNC | [26 empty] | D0001 | [9 empty] | Confirmed implemented and completed during time window of HSE exemption certificate which ran from 01 October 2025 until 11 October 2025, with an implementation diuration of 8 hours | 8 hrs between 01-Oct-2025 until 11-Oct-2025 | Low CDSP impacts
0870 - Amendments to Wobbe Index and Calorific Value Lower Limits at NTS System National Transmission System (NTS) Entry Points | UNC | n/a | [25 empty] | 0870 | 2024-11-03 |  |  | 19/09/24 | [5 empty] | 07/04/25: Update provided to CCSG. Implementation due 07 April 2025 01/04/25 - approved pending implementation 24/03: No IGT Impact, the WG are not tracking this Modification 11/11: No cross code impacts 30/07: This is an enabling Mod, no Legal Text, therefore, suggest there are no cross code impacts 28/06: Reporting to September 2024 UNC Panel 08/04: IGT IMPACT. IGT UNC Workgroup do not believe there is an impact, however, is being left open for discussion. | 2025-04-07
0874S - Amendments to UNC to align with Gas Demand Forecasting Methodology | UNC | n/a | [25 empty] | 0874S | 2024-05-04 | [8 empty] | 29/05: Implemented 05/05/25 07/04: Update for CCSG - no change 04/11 - pending implementation - date tbc 30/07: No Cross Code Impacts 28/06: Reporting to August 2024 UNC Panel. 08/04: Panel Assessment 20/05/24. IGT UNC Workgroup - still on watch list whilst the changes to the UNC are drafted. | tbc
0899S - To ensure the suite of Network Exit Agreements (NEXA) Modifications has been implemented, taking into account the changes introduced by 0804 (REC 3.0) | UNC | IGT175 | [25 empty] | 0899S |  | TBC | TBC | TBC | [5 empty] | 07/04: Update provided to CCSG - UNC Mod implemented 23 March 25 17/03: IGT Mod raised, will be considered by IGT UNC Panel on 28th March, expected to go to April WG and the WG report to go to Panel at the end of April. 11/11: New Modification - consideration at November 2024 UNC Panel | Implemented 23/03/2025 | None expected | No
0905S - Update to Offtake Arrangements Documents Points of Telemetry | UNC | TBC | [25 empty] | 0905S | [9 empty] | 13/06: Implemented 09 Jun 25 - NFA UNC 29/05: Awaiting implementation - due 09 June 2025 07/04: Update provided to CCSG - reporting to April 25 UNC Panel
0868 - Change to the current Allocation of Unidentified Gas Statement frequency | UNC | REC - tbc | [15 empty] | tbc | [9 empty] | 0868 | 2024-07-02 |  |  | 15/08/24 | [5 empty] | 11/11: Reporting to November UNC Panel - Workgroup did not identify any cross-code impacts 30/07: being extended to October 2024. Cross Code impacts not yet discussed at Workgroup as of 25/07/24 28/06: Reporting to Panel 15/08/24 REC IMPACT | UNC - 07/02/25
0872S - Single-sided Nominations for clearing houses of gas exchanges | UNC | n/a | [25 empty] | 0872S | 2024-05-04 | [8 empty] | 04/11 - pending implementation - date tbc 30/07: No IGT impacts 28/06: Reporting to August 2024 UNC Panel. 08/04: Panel Assessment 16/04/24. 24/03: No IGT Impact, the WG are not tracking this Modification | 2025-03-23
0880 Amendment to Wobbe Index upper limit in the Network Entry Agreement at the York Entry Point | UNC | n/a | [25 empty] | 0880S |  | 15/08/24 | 16/08/24 | TBC | [5 empty] | 01/11 - Reporting to Panel Nov 24 September 2024 UNC Panel determined new issues identified during consultation - returned to Workgroup 28/06: Reporting to August 2024 UNC Panel. No Cross Code Impacts | 2025-02-07
0882S - Transparency of non-standard Gas Quality parameters at new entry connections to the NTS | UNC | iGT - tbc | [25 empty] | 0882S |  | 21/11/24 | 22/11/24 | 17/12/24 | [5 empty] | 11/11: Reporting to November 2024 UNC Panel. IGT Impact | 2025-04-01
0885S - Amendment to Gas Quality NTS Entry Specification at the St Fergus SAGE System Entry Point | UNC | n/a | [25 empty] | 0885S |  | 17/10/24 | 18/10/24 | 2024-12-11 | [5 empty] | 11/11: Consultation closed - FMR reporting to November UNC Panel 28/06: Reporting to Janaury2024 UNC Panel. No Cross Code Impacts | 2024-12-13
0889S - Clarifying Inclusion of the Reserve Price in the System Entry Overrun Charge | UNC | TBC | [25 empty] | 0889S |  | 19/12/24 | 20/12/24 | 21/01/25 | [5 empty] | 11/11: Reporting to December 2024 UNC Panel - Cross Code Impact tbc | 2025-02-07
0891 - Reintroduction of the enhanced pressure service and increased MNEPOR for BBLC (reintroduced by UNC0589 and introduced by UNC0814) | UNC | TBC | [25 empty] | 0891 |  | 15/08/24 | 16/08/24 | 2024-09-09 | [5 empty] | 11/11: Awaiting Ofgem Decision - sent to Ofgem for authority decision 19/09/2024 | 2025-02-25
0892FT - Update incorrect NTS Entry Capacity paragraph references and reintroduce Daily Auctions to Entry Overrun Charges | UNC | TBC | [25 empty] | 0892FT |  | n/a | n/a | n/a | [5 empty] | 11/11: New Fast-Track Modification - consideration at November 2024 UNC Panel | 2024-12-13
0893S - Reintroduce NTS Capacity Surrender text and update TPD B2.12 | UNC | TBC | [25 empty] | 0893S |  | 20/09/24 | 21/09/24 | 18/10/24 | [5 empty] | 11/11: Consultation Closed - FMR consideration at November 2024 UNC Panel | 2024-12-13
0849R - Commercial Framework Review to Enable Hydrogen Blending | UNC | IGT UNC - no impact | [10 empty] | tbc | [14 empty] | 0849R | [11 empty] | 01/12: Request Group was closed in UNC Nov Panel by unanimous vote Raised 09/05/2023 reporting to UNC Panel 21 Nov 2025
0895S - Replacing ‘Energy Networks Association’ with another publishing method | UNC | TBC | [25 empty] | 0895S |  | 17/10/24 | 18/10/24 | 2024-08-11 | [5 empty] | 11/11: Consultation Closed - FMR consideration at November 2024 UNC Panel | 2024-12-13
0898S - Amendment to Gas Quality NTS Entry Specification at the St Fergus Shell System Entry Point | UNC | TBC | [25 empty] | 0898S |  | 16/01/25 | 17/01/25 | 2025-11-02 | [5 empty] | 11/11: Reporting to February 2025 UNC Panel - Cross Code Impact tbc | 2025-03-25
R0060 - ERDS Service Definition time zone correction | REC | n/a | [15 empty] | R0060 | 2024-06-07 | 2024-06-07 | 2024-06-28 | 2024-08-15 | [15 empty] | 07/07/25 - implementation pushed out to First available release after MHHS Milestone 8 – Code changes delivered in R0250 07/10/24 - approved, awaiting implementation 03/07/24 - confirmed no BSC impact | First available release after MHHS Milestone 8 – Code changes | ERDS | N
I0191 - Introduction of SLA for Supplier De-Registration on Disconnected Meters | REC | BSC - n/a, DCUSA - n/a | tbc |  |  |  |  | tbc | [9 empty] | I0191 |  |  |  |  | tbc | [14 empty] | 14/08/25 approved for Nov implementation 01/08/25 final vote at Change Panel 05/08 13/06/25 being reviewed by Change Panel on 17/06 and then should proceed to consultation - closes 11/07 19/05/25 - reviewing responses to industry IA. 24/04/25 - title updated. Presented to April Change Issues Group. Legal text currently out for industry impact assessment setting suppliers a SLA to either de-register or query disconnection. IA closes 29/04/25. 29/07/24 - discussed at RIG, raised by DNOs. Potential additional impact to DCUSA / BSC | 2025-11-07 | n/a | No
I0205 - Provision of HH consumption data for Advanced Meter ETs | REC | BSC - n/a, DCUSA - n/a | [15 empty] | I0205 | [19 empty] | 16/09/25 - approved for Nov implementation 11/09/25 - final vote at Change Panel 16/09 14/08/25 - consultation open, closing 08/09 21/07/25 - IA closed, refined solution expected to be presented at Change Issues Group in August 16/06/25 - to be presented to Change Panel on 17/06/25 before going out for industry impact assessment - IA closes 11/07/25 24/04/25 - solution development continues. Proposer confirmed expectations are new process would use existing ES screens on SDEP. 16/09/24 - No SEC impact as Advanced not Smart Meter 02/09/24 - proposer has confirmed it was rejected by MHHS programme | 2025-11-07 | n/a | N
R0212 - Protecting Crimestoppers and their Contacts | REC | Watching brief only | [15 empty] | I0212 | 2024-10-01 | 2024-10-01 | [17 empty] | 01/07/25 - approved for Nov implementation 24/04/25 - legal text developed and consultation being drafted | 2025-11-07 | n/a | tbc
R0215 - Schedule 30 Switch Meter Reading Problems - Rejections and Timings | REC | REC only - no cross code | [15 empty] | I0215 | [19 empty] | 17/06/25 - approved for Nov implementation 05/06/25 - final recommendation published and out for comments, final vote by change panel on 17/06 19/05/25 - out for industry consultation, closes 27/05/25 24/04/25 - code manager reviewing responses to industry impact assessment. 16/12/24 - initial discussions at December's REC Change Issues Group | 2025-11-07 | n/a | N
R0227 - Domestic Elective HH Switching | REC | BSC - n/a, SEC - n/a, DCUSA - n/a | [15 empty] | I0227 | [19 empty] | 17/06/25 approved for Nov release 05/06/25 - final recommendation published and out for comments, final vote by change panel on 17/06 19/05/25 - out for consultation. Closes 02/06/25 24/04/25 - industry impact assessment due to close 29/04/25. 02/12/24 - expectations are no change is required. All Elec codes listed for now. | 2025-11-07 | n/a | N
I0240 - Data alignment of meter information through MHHS Migration | REC | BSC | tbc | [14 empty] | I0240 | [19 empty] | 11/09/25 - draft document avalaible on the REC portal for comments until 30/09 27/08/25 - Draft solution to be presented at September Change Issues Group 08/07/25 - proposal plan approved by REC Change Panel 07/07/25 - action for REC to confirm why this needs to be BSC led - confirmed it does not need to be | 2025-11-07 | tbc | tbc
R0243 - Transfer of Standard Settlement Configuration and Time Pattern Regime Data Item Ownership | REC | BSC | CP1613 | [14 empty] | R0243 | [19 empty] | 06/10/25 - CP1613 going to SVG on 07/10 - approved 24/09/25 - approved for Nov implementation 11/09/25 - final vote at Technical Expert Panel 24/09 14/08/25 - REC consultation open, closing 03/09 29/07/25 - full change report published with plan, solution and business case assessment. Being presented to REC Change Panel 05/08 03/07/2025 - BSC CP will be raised at August SVG | 2025-11-07 | n/a | N
DCP451 Suspending Registrations | DCUSA | REC - I0248 | [5 empty] | DCP451 | [9 empty] | I0248 | [19 empty] | 05/08/25 - REC change approved for Nov implementation 01/08 - final vote at REC Change Panel 05/08 21/07/25 consultation closed, looks to be no amendments to REC legal text post consultation 19/06/25 out at consultation, closing 11/07. Expect to be at final vote by end of Aug 13/06/25 REC I0248 plan being presented at Change Panel 17/06, assuming approved will proceed straight to consultation 19/05/25 - changes progressing separately. REC legal text with legal support for review. 24/04/25 - to be discussed at the next DCP451 working group on 02/05/25 | DCP451 - Jun 25 R0248 - Nov 25 | ERDS - tbc - CSS - tbc | tbc
R0263 Sharing Confirmed Energy Theft Data with the BSC | REC | BSC - info only | [15 empty] | R0263 | [19 empty] | 16/09/25 - approved for November implementation 11/09/25 - final vote at Change Panel 16/09 15/08/25 consultation issued, closes 08/09/25 15/07/25 out for impact assessment with REC Performance Assurance, will be returned mid August 03/07/25 accepted in by REC - shouldn't require a BSC change but will impact them | 2025-11-07 | n/a | tbc
CP1611 Supplementary Drafting to Improve the BSCP 700 Series | BSC | Info | CP1611 | [34 empty] | This CP will clarify BSCP700 series documents that went live at M8 - approved for M11 implementation | 2025-11-06 |  | n/a
[Pre-raise] Valid set for the Measurement Quantity (J0103/DI-052) | BSC | REC | N/A | [14 empty] | tbc - likely does not need a CP, but does impact | [19 empty] | 17/11/25 REC emailed BSC requesting they are looped in when this goes out for consutlation, this Data Item is in 43 Market Messages, some of which are REC owned, so we would like to flag to REC Parties Awaiting confirmation from SVG that they endorse fixing this as a defect. BSC CP may not be required, as new Enumeration Value 'UN' would not be relevant to Settlement processes. 01/12/25 - SVG endorsed approach and EN added to valid set in EMDS v4.1.1 on 28/11/25 | 2025-11-28 |  |  | yes
New Urgent Mod - unfreezing MDD for iDNOs | BSC | REC? | P506 | [14 empty] | ? | [19 empty] | new line P506 To be raised on 20/11. This Mod won't impact ISD 15/12 With the Authority for a decision
[Pre-raise] Amendment of validation within SMRS for number of Meter Digits | BSC | [16 empty] | ?
[Pre-raise] Enduring Complex Sites and Shared SVA Metering System arrangements post MHHS | BSC
[Pre-raise] Linked Import/Export MPANS with meters in the Advanced and Trad or Smart Meter Groups | BSC
P507 Reverting legacy Half Hourly scaling factors to pre-M10 values | BSC |  | P507 | [34 empty] | The P507 Urgency Request letter was sent to Ofgem on 12 December 2025
P503 Unfreezing MDD to enable load diversity | BSC | REC | P503 | [16 empty] | C3-0149 | [17 empty] | REC Category 3 CP C3-0149 implemented 11/12/2025 This Mod won't impact ISD. Approved on 27 November 2025. P503 will be implemented within 12 working days. Implemented 15 December 2025. | 2025-12-15
‘Clarification of Self Testing Requirements for Potential DIP User within the DIP Rules’' | DIP | BSC and REC | [30 empty] | DCR0007 |  |  |  |  | 15/12/2025 This change will be implemented tomorrow. 05/11/2025 Prospective DIP Users participating in the DIP Onboarding process should pay attention to this important change regarding the testing of sending and receiving messages for all DIP interfaces. This testing is now part of a self-testing protocol for prospective DIP Users, rather than being included in the DIP Manager's testing process. This adjustment aims to clarify the expectations for prospective DIP Users during their onboarding to the DIP. This document update shifts the requirement for testing from the DIP Manager to self-testing by prospective DIP Users. As a result, these users must demonstrate their ability to send and receive all messages across all DIP interfaces within their systems. | 2025-12-16 | n/a | n/a
P506 Unfreezing specific MDD entities to allow legacy Suppliers access to newly-Qualified LDSOs’ networks during MHHS Transition | BSC | For info | P506 | [34 empty] | 14/01/2026 Ofgem approved, implementation on 16/01/26 01/12/2025 - CF to check REC impacts - no impacts if no new SSCs are being introduced P506 relates to unfreezing five MDD Entities until M15: Entity 53 – Meter Timeswitch Class for Distributor (NHH & HH) Entity 54 – Valid MTC SSC Combinations (NHH) Entity 55 – Valid MTC LLFC Combinations (HH) Entity 56 – Valid MTC LLFC SSC Combinations (NHH) Entity 63 – Valid MTC LLFC SSC PC Combinations (NHH) Ofgem granted Urgency on 24 November 2025. P506 was issued for an Urgent Modification Consultation on 25 November 2025, with responses invited by 8 December 2025. | 2026-01-16
I0288 - Schedule 14 review - DNOs do not remove Metering Assets | REC | BSC - tbc, DCUSA - tbc, SEC - tbc | tbc |  |  |  |  | tbc | [9 empty] | I0288 |  |  |  |  | tbc | [14 empty] | 12/01/2026 - this has been withdrawn 11/12/2025 - discussed at REC Metering Expert Panel on 10/12/25, there are scenarios where DNOs remove meters (mostly emergencies). This will likely be withdrawn. |  | tbd | tbd
MHHS Issue: Specific Event Scenarios for Backdated MHHS Service Provider Appointments | BSC | REC - tbc | [15 empty] | tbc | [19 empty] | Moved to archive - duplicate of CP1616 Centrica raised a CP which has been with the MHHS Expert group to address the issue: The Service Provider appointment message (IF-031) requires an event scenario to be used and the current design states that “Change of Service Provider (CSP)” must be used for all backdated appointments. This will cause confusion across participants as it does not identify the scenario behind the appointment such as COS, Forward Migration, Change of Agent etc. This will be raised at the September SVG. Likely to impact agent appointment processes.
I0172 - New Build - Commissioning Process Review | REC | BSC - tbc, UNC - tbc, iGT UNC- tbc, SEC - tbc, DCUSA - tbc | tbc |  |  |  |  | tbc |  |  |  |  | tbc |  |  |  |  | I0172 |  |  |  |  | tbc |  |  |  |  | tbc | [9 empty] | 26/02/26 - resolved 16/01/26 - expected to move to resolved rather than progress to a CP (address items to be looked at under I0200, crossed meters expected to be looked at under a new CP) 17/10/25 - update will be provided at Nov CHIG 16/06/25 - gas meter installations to be discussed at Aug Change Issues Group. Code Manager still accepted edge cases for future discussions. 24/04/25 - due to be presented to June 25 Changes Issues Group. 16/12/24 - actions from Nov meeting to be completed before progressing to meter install. Expected update in the new year. 07/10/24 - discussed at Change Issues Group on 3rd Oct. Agreed address issues stay, shipperless also stays and will start with process from MPXN creation to meter install at Nov meeting. 30/05/24 - going to RFI before REC Change Issues Group. List of questions will be given to all Codes to make sure it is a cross code RFI 16/05/24 - raised by a consumer. Following the new issues process. End to end review of new connections process so expect cross code discussions. Impacts / CPs are TBC |  | tbc | tbc
D0002 - Derogation from UNC TPD V5 (Protected Information) to allow the provision of data to hydrogen producers linked to East Coast Hydrogen FEED study | UNC | IGT UNC - no impact | [25 empty] | D0002 | [9 empty] | 16/02 Ofgem direction issued 12 February 2026 and Implementation confirmed for 16-Feb-26 through to 31-Dec-27 03/10 September UNC Panel recommended Implementation now with the Authority for direction 17/07: New Derogation request at June UNC Panel going to consultation (closing 29 August ) to return to 18 September UNC Panel | 2026-02-16 |  | Y
I0189 - Voice of the Consumer | REC | n/a | [15 empty] | I0189 | 2024-11-05 | [18 empty] | 26/02/26 - issue has been resolved 03/10/25 - at Service Provider IA, expected to run through until end of Dec and open Party IA in early 2026 21/07/25 - working group on 28/07 expected to be last one 24/04/25 - development at working group continues 16/12/24 - working group agreed to focus only on smart installs (previously known as SMICOP) 29/07/24 - proposing to extend use of consumer surveys beyond SMICOP. |  | None - introducing new sevice provider | Yes
R0190 - Related Meter Point RMP status rules | REC | BSC - tbc, DCUSA - none | tbc | [14 empty] | I0190 | [19 empty] | 29/01/26 - voted to approve, implementation in Feb 26 27/11/25 - consultation closes 12/12/25, final vote at 20/01/26 change panel 31/10/25 - extension to plan approved, expect to be at consultation by end of Nov 18/09/25 - at Party IA, closing 10/10/25 11/09/25 - draft legal text reviewed by Gowlings, getting confirmation from St Clements no impact to their systems before proceeding to Party IA 18/08/25 - Potential BSC impact? - no update at this time, CB taken away 01/08/25 no longer on hold, being presented at August CHIG and open Information Request closing on 22/08. Scope of Issue has changed to looking at allowing for MHHS Metering Points, Primary Operational and Secondary Created MPANs to be linked. Potential BSC impact? 24/04/25 - on hold as expected to be covered by I0191 29/07/24 - flagged by MHHS as mismatch in obligations | 2026-02-27 | None | No
R0198 - GAS MEMs move towards a single interface for key market messages | REC | UNC - n/a, iGT - n/a | [15 empty] | I0198 | [19 empty] | 14/08/25 - approved for implementation in Feb 26 01/08/25 - at final vote at MEP 13/08 16/06/25 - issued for industry consultation - ends 04/07/25 following discussion at MEP 19/05/25 - reviewing responses to industry impact assessment 24/04/25 - out for industry impact assessment until 29/04/25. 20/01/25 - to be taken to Change Issues Group on 6th Feb 29/07/24 - raised by REC Performance Assurance. Potential cross code impacts on UNC / iGT UNC | 2026-02-27 | n/a | No
I0235 / R0235A - Missing Scenario Variant (DNO to MOA) in D0179 | REC | BSC - tbc | tbc | [14 empty] | R0235A | [19 empty] | 01/07/25 R0235 rejected and R0235A approved (removal of D0179 from REC legal text). Decision on whether the BSC want to raise a similar change to remove D0139 from their legal text with them 13/06/25 - consultation closes on 16 June 2025. Has been flagged to the BSC on 04/06/25 via email that the alternate to this change very likely has BSC impacts 19/05/25 - to be discussed at Change Panel on 20/05/25. 24/04/25 - Code Manager reviewing responses to industry impact assessment. | 2026-02-27 | DTN | No
R0242 - Missing Scenario Variant from R0043 | REC | BSC - n/a | [15 empty] | R0242 | [19 empty] | 25/06/25 approved at TEP for Feb 26 implementation 13/06/25 - final vote at REC Technical Expert Panel on 25/06/25, final recommendation report has been published for comments 19/05/25 - out for industry consultation, closes 27/05/25 | 2026-02-27 | DTN | No
I0244 - C21 to be introduced into STIRG Document | REC | BSC - tbc | tbc | [14 empty] | I0244 | [19 empty] | 09/07/25 approved at MEP for Feb 26 release 16/06/25 - Consultation responses being reviewed. Due to be presented to MEP for final vote July 25 19/05/25 - out for industry consultation, closes 02/06/25. 24/04/25 - industry impact assessment closes 29/04/25. 19/02/25 Confirmed no DCUSA change needed, waiting for confirmation from BSC | 2026-02-27 | DTN | No
R0256 - MM00023 /D0135 - Asset Condition Report clarification of intent on R0021/R0101 | tbc | BSC - tbc, DCUSA watching brief | tbc | [14 empty] | I0256 | [19 empty] | 24/09/25 - approved for Feb 26 implementation 11/09/25 - final vote at Technical Expert Panel 24/09 14/08/25 at consultation, closing 08/09 19/05/25 - decision needed on which code owns the specific scenario variant | 2026-02-27 | DTN | N
I0270 Clarification of SIP Qualification Requirements | REC | DCUSA - tbc, REC - I0197 | [5 empty] | tbc | [9 empty] | I0270 | [19 empty] | 12/02/26 - approved for February implementation 29/01/26 - final vote 11 Feb MEP meeting, for Feb implementation. Discussions with DCUSA confirm they should be fine for Feb implementation, but also happy to go slightly after us if needed 27/11/25 - at MEP 10/12/25 for review, consultation 12/12/25 - 16/01/26 13/11/25 - proposal plan being presented at Change Panel 18/11/25. Assuming approval, will be at consultation in mid-December after presentation at MEP 03/10/25 - offline discussion has determined there is DCUSA impact (otherwise REC could have progressed as HK) - do we have an ETA for a DCUSA change being raised? 24/07/25 - Issue accepted | 2026-02-27 | None | No
I0277 Data Latency SLA Alignment for Gas Enquiry Service | REC | info only | [15 empty] | I0277 | [19 empty] | 27/11/25 - approved for implementation in Feb 26 13/11/25 - final vote at TEP 26/11/25 17/10/2025 - consultation closes 31/10/25 03/10/2025 - proposal plan being presented at 07/10/25 Change Panel, plans to proceed immediately to consultation for a Feb 25 release 21/08/2025 - accepted in | 2026-02-27 | GES - Service Provider only, no system impacts | No
CP1619 Creation of Category 3 BSC Configurable Items for Accurate/Limited Status and Settlement Performance Weightings of Consumption Component Classes | BSC | For info | [35 empty] | CP1619 seeks to create two new Category 3 BSC Configurable Items to formally record and publish the Accurate / Limited status and the Settlement Performance Weightings. | 2026-02-26
0876S - Updates to the Annual Quantity (AQ) amendment process | UNC | iGT - no impact, REC - None noted | [25 empty] | 0876S | [9 empty] | 13/02: Implementation confirmed for 27 February 2026 Automatic application of changes under IGT UNC as a result of cross referencing. 21/08 Panel Approved implementation - date to be determined 17/07/25: Consultation complete & FMR published - to Panel Decision 21 August 2025 04/07/25: Reported to June UNC Panel - Consulation underway until 10 July 2025 12/06/25: Workgroup Report complete and published ahead of reporting to June 25 UNC Panel 29/05: Update provided to CCSG - reporting to June 25 UNC Panel 19/05: Auto-application under IGT UNC via cross reference 07/04: Update provided to CCSG - reporting to June 25 UNC Panel 24/03: Currently, IGT UNC Part CI6 already cross references G2.3 of the UNC. The text allows for G2.3 provisions to apply under the IGT UNC for the purposes of determining AQ. Therefore, any changes implemented to G2.3 will automatically apply under the IGT UNC without any need for an equivalent IGT UNC Modification. The Chair of the Distribution Workgroup reached out to the CA and informed them that the Workgroup wanted it highlighted that there will be impacts to IGTs as parties, even though there is no change to Code. The CA has recommended that IGTs review the documents for this Modification. 11/11: Reporting to Panel March 25 28/06: Reporting to November 2024 UNC Panel. | 2026-02-27 | CDSP | Y
0884 - Extending the PC4 Read Submission Window | UNC | iGT - iGT178 | [10 empty] | igt 178 | [14 empty] | 0884 |  | 16/01/25 | 17/01/25 | 2025-01-02 | [5 empty] | 30/01: Implementation confirmed for 27 Feb 26 01/02/25 - IGT UNC targeting implementation Feb 2026 15/09 - iGT178 just finishing working group 21/08 Panel Recommeded implementation - awaiting Authority Decision 18/08: Consultation responses and FMR published - Panel recommendation Aug ahead of subsequent Authority Decision 17/07: Consultation finishing today - For Panel Decision 21 August 04/07: Reported to June Panel and out to Consultation 12/06: Workgroup Report Published for Report to June 25 UNC Panel. 29/05: Reporting to June 25 UNC Panel. 07/04: Update provided to CCSG - Reporting to April 25 UNC Panel. 17/03: IGT has reached out and is prepping an IGT Mod, which will look to amend the Must Read window for IGTs to align it with the extended PC4 read submission window under this Mod. Mod expected ahead of April Panel. 11/11: Reporting to January 2025 UNC Panel. IGT party Impact and code impact. IGT178 raised and approved. | 0884 - 27/02/26 anticipated IGT178 - 27/02/26 | CDSP | Y
0904R - Review of the profiling arrangements with respect to LDZ Shrinkage Quantity | UNC | iGT - no impact | [25 empty] | 0904R | [9 empty] | 27/02: Feb UNC Panel confirmed Request Group closure 07/04: Update provided to CCSG - reporting to March 26 UNC Panel | n/a | None | No
DCR0013 - DIP System enhancements | DIP | For Info | [30 empty] | DCR0013 |  |  |  |  | 02/03/2026 - The DIP has been used by its users since August 2025, and during this time, the DIP Manager has implemented various system enhancements. For example, in November 2025, new functionality was introduced that allows users to start and stop the application programming interface (API). However, there is a concern regarding the continuous improvement of the DIP. If the SP does not keep the system updated, it may become outdated, potentially impacting the adaptability of the service and the ability of DIP participants to use and provide accurate data. The DIP Manager is introducing a range of enhancements, including: - Role-based filtering for DIP Manager. - Improving DIP ID allocation; - Registration Connection Report; - Service Analyst Role; - Separate Retries from Failures in the performance graph; - Message Admin Status; - Expired date text highlight; - Ability to download Dead Letter Queue (DLQ); and - Reporting enhancements. First Certificate Roles Message Tracker | 2026-03-12 | DIP | No
I0231 - Shared Sites in Electricity Enquiry Service (EES) | tbc | BSC | tbc | [14 empty] | I0231 | [19 empty] | 12/03/26 - withdrawn 16/01/26 - On hold until post MHHS M16 (Dec 2026) 19/08/25 - conversation had with Proposer (Elexon), they have taken away to investigate if this change is still required 24/04/25 - on hold until MHHS M8 | tbc | EES | No
I0303 Potential Consumer detriment for Smart Economy 7 | REC | For info | [35 empty] | 12/03/2026 - moved to resolved, will be explored under I0273 12/02/2026 - joint information request with I0273, closing on 06/03/26 12/01/2026 - accepted in - theoretically linked to I0273 and I0290 |  | tbc | tbc
DCR0008/10 - Removing the message limit in the DIP Portal | DIP | For info | [30 empty] | DCR008/10 |  |  |  |  | 02/03/2026 The message limit will be introduced in the March DIP Manager System Release 12/03/2026 23/02/26 expected release pushed back from Feb to March There is a max limit of 250 for the IF messages and 100 for PUB messages. This is an issue because set max limit of messages is preventing us to see full list of messages and messages status. | 2026-03-12 | DIP | DIP
DCR0016 | DIP | For info | [30 empty] | DCR0016 |  |  |  |  | 23/03/2026 - Implement a new DIP message - IF-0XX ’Data Refresh’ (the actual DIP message number will be allocated in the implementation phase of this CP, subject to its approval). This would be generated by the SMRS, when required, and passed to the DIP and/or EES and/or MDS to enable data resetting or realignment between these systems. The new message would be exchanged via the DIP or, if required, using native JSON files secured via password-protected ZIP files exchanged directly. The refresh flow would be issued to an individual party or all parties, depending on the incident. For this CP, any use of the refresh flow, its exchange mechanism, and processing timescales would be agreed bilaterally between the SMRS and the recipient(s), considering the incident's nature and the wider coordinated industry response. The new ‘refresh’ message is intended for the bulk correction of data following a data-impacting incident. Day-to-day operational correction of individual MPAN discrepancies would continue to be resolved on a case-by-case basis, using existing MHHS Design guidance and mechanisms. The current view is that Suppliers, Data Services, and Metering Services would obtain the refreshed data from EES, using existing functionality. Enabling market participants to access refreshed data following major data misalignment incidents. | 2026-03-23 | DIP | DIP
R0201 - Creation of a Tool to Manually Correct ERDS / CSS Discrepancies | REC | BSC - CP1606, DCUSA - n/a, SEC - n/a | CP1606 | [14 empty] | R0201 | 2024-08-27 | 2024-08-27 | [17 empty] | 17/10/25 - REC change approved for implementation on 27/03/26 - BSC change also approved 03/10/25 - final vote at REC Change Panel 07/10/25 20/08/25 - at consultation, closing 10/09/25 14/08/25 - Change Report (For Consultation) published for review at 19/08 Change Panel. Consultation expected to open 22/08, with proposed implementation 27 March 2026 24/04/25 - potentially requires a BSC cross code change. 16/12/24 - awaiting impact assessments 07/10/24 - with REC service providers to determine solution options | 2026-03-27 | CSS, ERDS | No
CP1612 Extend Customer Direct Contract requirements from 1130 days to 1827 days in BSCP706 | BSC | Info | CP1612 | [34 empty] | 15/12/25 - this has been approved for implementation on 26/03/26 17/10/25 - some changes required to flow notes in EMDS, decision delayed This CP will require a small change to SMRS systems | 2026-03-26 | SMRS | No
0896 - Reducing the current Code Cut-Off Date (Line in the Sand) from 3 to 4 years to 2 to 3 years | UNC | iGT - no impact | [25 empty] | 0896 | [9 empty] | 22/08 - Authority direction issued to implement on 01/04/26 18/08 With Ofgem 17/07: Consulation complete and Published - July Panel recommended implementation ahead of referral to Authority. 29/05: Consultation underway, reporting to July 25 UNC Panel. 19/05: Auto-application under IGT UNC via cross reference 07/04: Update provided to CCSG - Reporting to May 25 UNC Panel. 11/11: Reporting to February 2025 UNC Panel - Cross Code Impact tbc | 2026-04-01 | CDSP | Yes
0886V - Amend the Code Cut-Off Date to a Rolling 3-Year Period | UNC | iGT - no impact | [25 empty] | 0886 | [9 empty] | 22 Aug - Authority direction issued to implement on 02/04/26 17/07: Consulation complete and published, July Panel recommended implementation ahead of subsequent Authority Decision 04/07: Consultation underway until 10/07 for July JUNC Panel Implementation Decision 12/06: reporting to June UNC Panel 29/05: Reporting to July UNC Panel. 19/05: 19/05: Auto-application under IGT UNC via cross reference 07/04: Update provided to CCSG - Reporting to May UNC Panel. 11/11: Reporting to February 2025 UNC Panel. IGT Impact as the code cut off date applies to IGTs as parties. However, code impacts will not be known until we see the UNC legal text. | 2026-04-02 | CDSP | Yes
0843 -Establishing the Independent Shrinkage Charge and the Independent Shrinkage Expert | UNC | IGT165 | [10 empty] | IGT165 | 2023-06-08 | [13 empty] | 0843 | 2023-04-20 | 19/09/2024 | [7 empty] | 16/04 Authority has rejected the mods 27/03 Authority Estimated Date of Decision revised to 15 April 2026 12/03 decision date no 16/03/26 13/01: Ofgem decision expected by 30th January for UNC0843 and IGT165 - pushed back to at least 27/02 for decision, maybe further 21/08 Panel Recommeded implementation - awaiting Authority Decision 17/07 Consultation responses & FMR published - Panel Decision 21 August 2025 07/07 consutlation responses to be published 14/07 12/06: Consultation still underway - no responses yet 29/05: within consultation, closing 18 July 2025, FMR to August UNC Panel. 19/05 - IGT165 going to IGT UNC panel on 30th May. Will be issued for consultation alongside UNC0843. 07/04: Update provided to CCSG. Workgroup Report due to go to UNC Panel on 15 May 2025. 24/03: UNC Panel agreed a 2 month extension for UNC0843 to May 2025. TL will be attending the next UNC WG meeting and keep up to date on progress to ensure that IGT165 remains close to UNC0843. Please note that IGT165 will not go to IGT UNC Panel with WG report until after UNC0843 has gone to ensure we are not progressing ahead of the main framework. 17/03: IGT165 nearing completion, aiming for last WG meeting to be April, and WG report and DMR to be agreed at April WG. Consultation for this Mod will likely be issued in line with / or shortly after, the UNC Mod. There will be a level of overlap if UNC0843 has a full 15 WDs consultation. 11-Nov: Workgroup Extension request accepted by UNC Panel - now reporting to March 2025 28/06: Workgroup extension agreed to 19 September 2024. IGT IMPACT 08/04: Workgroup extension agreed to 18 July 2024. IGT IMPACT UNC Panel voted that there were Cross Code impacts. 15/05/23 - IGT UNC mods are being raised. 13/11/23 Proposer has been off sick. Going to DWG meetings going forward. Hope to get it moving again. 29/07: IGT UNC waiting on updated UNC legal drafting before progressing related IGT UNC modification. 30/07: Currently reporting to September 2024, but may need further extension. Legal drafting has been submitted but not yet reviewed by Workgroup. | tbc | CDSP | Yes
0907 - Extension to current maintenance period | UNC | IGT UNC - No impact | [25 empty] | 0907 | [9 empty] | 24/06 Rejected by Ofgem 12/06 Authority Estimated Decision date revised to 24 June 2026 14/05 expected decision date 10/06/26 27/02 Feb 26 UNC Panel recommended not to implement this Modification which is now awaiting Authority Direction No IGT UNC Impact but IGTs are requires to align to the best of their abilities to the GDN maintenance periods. But no code change required. 01/12: Workgroup reported to Nov UNC Panel and now out for Consultation representations from 21 Nov 25 until 06 Feb 26 for a Feb 26 UNC Panel recommendation 17/10 Workgroup extended reporting date to November 2025 UNC Panel 03/10 Workgroup Extended reporting to October 2025 UNC Panel 29/05: reporting to September 25 UNC Panel 19/05: IGT Impacts unclear, inconsistent impacts on website vs documentation. IGT UNC CA keeping an eye on this for now. Also - potential downstream impacts to IGT SPs unknown. 07/04: Update provided to CCSG - reporting to September 25 UNC Panel | For first potential use March 26 | None | Yes
0917R Should biomethane producers fully bear the cost of propanation, and are there more equitable options for funding the activity? | UNC | Review Group - no Impact | [25 empty] | 0917R | [11 empty] | 17/07: Request withdrawn at July UNC Panel 18/05/2026 - report due July UNC panel. Any mods that are raised off the back off this are expected to impact IGT UNC Oct UNC Panel allocated to Gas Quality Workgroup to report to April 2026 UNC Panel | Review Group | None | No
0919S Housekeeping amendments to TPD Sections B, G and M | UNC | IGT UNC - no impact | [25 empty] | 919S | [9 empty] | 17/04 :- implemented 14 April - will move to archive in next update 27/03 :- March UNC Panel directed implementation, scheduled for 14 April 2026 16/03 Consulation closed 27 Feb and implementation decision expected at March UNC Panel 16/01 Reported to Jan UNC Panel and now out for Consultation closing 27 February 2026 Oct UNC Panel allocated to Distribution Workgroup to report to January 2026 UNC Panel | 2026-04-14 | None | No
0927S - Moving the Market Participant Identity Verification Approach Document out of the UK Link Manual and into the CDSP Service Document – Contract Management Arrangements | UNC | IGT UNC - confirmed none | [25 empty] | 0927S | [9 empty] | Implemented 14 September 2026 04/09: Panel Decision to implement with a date of 14 September 2026 directed 17/07 Reported to July UNC Panel, now in Consultation until 06 August for August UNC Panel decision 03/07 Now reporting to Panel 16 July 2026 27/03:- March 26 UNC Panel assessment, allocated to Distribution Workgroup to Report to June 2026 Panel | 2026-09-14 | CDSP | No
P507 Reverting legacy Half Hourly scaling factors to pre-M10 values | BSC | For info | P507 | [34 empty] | 16/04/2026 - Authority approved alternate mod on 02/04/26, implementation 05/05/26 16/02/2026 still with Ofgem for decision 12/12/2025 - request to Ofgem for urgency | 2026-05-05 | tbc | Yes
I0230 - Meter Asset Providers may not receive effective from settlement date (J0049) in the D0303 flow following MHHS design changes. | REC | BSC - none | [15 empty] | I0230 | [19 empty] | 14/05/26 - has been withdrawn by the Proposer as no consensus amongst MAPs for a temporary solution 29/01/26 - expecting to hear back from Proposer on what they wish to do by mid-feb 13/11/25 - information request open until 05/12/25. Q&A session on solution options 19/11/25 31/10/25 - proposal plan at change panel 04/11/25, expect to open Information Request for feedback on several solution options by 07/11/25 | tbc | DTN | No
DCR0012 - Housekeeping amendments to the DIP Subsidiary Documents’ | DIP | For Info | [30 empty] | DCR0012 |  |  |  |  | 02/03/2026 - The DIP Rules, including the DIP Supplement and DIP Subsidiary Documents (DSDs), are updated via BSC modifications or DIP Change Requests (DCRs). Recent changes stem from BSC Modification P496 and DCR 0004, both aimed at defining how the DIP Manager shares transactional data with Code Bodies like the BSC and REC. These changes affected several documents, including the DIP Supplement and DSDs 001, 002, 003, 006, and 007. However, issues have arisen due to formatting errors in the legal text of DSD006, where numbering does not align with the approved version. This discrepancy leads to confusion regarding the "source of truth" for the documents. | 2026-04-28 | n/a | No
R0157 - Code Communication Methods - PTSN close down | REC | BSC - CP1594, SEC - MP260, UNC 864S, iGT - 174 | CP1594 |  |  |  | 2024-05-07 | DCP457 |  |  |  |  | iGT 174 |  |  |  |  | R0157 | 2024-01-30 | 2024-01-30 | 2024-02-09 | 2024-03-19 | MP260 | 2024-04-01 | 2024-04-01 | 2024-05-01 | 2024-05-01 | 0864S | 2023-03-11 |  |  | 20/6/24 | [5 empty] | 29/06/2026 - IGT174 and 864S implemented 02/02/2026 - UNC 864S potentially tracking for Jun-26 implementation, but still TBC 04/08/25 - DCUSA Housekeeping CP raised (DCP 457 Housekeeping Items) which includes removal of relevant references. 04/11 - 864S pending implementation. Date tbc 28/06: 0864S Consultation closing 19/07/24. 17/06/24 - not cross code but listed together as same problem. Possible iGT UNC Impact - Code Communication methods. Removing fax comms - so all codes to check if they have fax in their notifications. 31.05.24 - SEC Housekeeping Mod included in June 2024 release, awaiting Implementation 18/04/24 - R0159 was approved and is now awaiting implementation | REC - Nov 25 BSC - 27/06/24 SEC - June 24 DCUSA - Nov 25 IGT UNC - Jun 26 UNC - Jun 26 | n/a | No
P487 Incentive of BSC Supplier Parties to meet the M15 MHHS Milestone | BSC | REC - no impact | P487 | [34 empty] | 11/05/26 - approved for implementation "on the date on which the notified changes to the Market-wide Half Hourly Settlement (MHHS) Migration Framework setting out the process for P487 implementation are implemented, or 25 June 2026, whichever is the earlier" 16/04/26 - decision expected 30/04/26 02/02/26 - back with Authority for decision in December 22/08/25 - authority send back received Raised at April 25 BSC Panel; June Panel recommended 'Reject'; with Authority | 2026-06-25 | n/a | No
R0276 SFIC to CMRM - missing Scenario Variant in D0126 / MM00016 | REC | BSC - info only | [15 empty] | R0276 | [19 empty] | 11/12/2025 - going to TEP for approval on 17/12/25 - approved for June 26 implementation 31/10/2025 - consultation closes on 14/11/25 18/09/2025 - party IA closes 10/10/25 11/09/2025 - plan being presented to Change Panel 16/09, then should be at Party IA end of the week 14/08/2025 - accepted in | 2026-06-26 | DTN | No
I0290 Legacy Data Item API Service | REC | BSC - no impact DTSA - tbc | [15 empty] | I0290 | [15 empty] | tbc |  |  |  | 11/06/26 - Change Panel agreed with recommendation to reject, will move to archive once appeal window is closed 28/05/26 - going to Change Panel on 02/06/26 with a recommendation to reject 14/05/26 - out for consultation closing 21/05, likely being recommended for rejection due to high costs 12/02/26 - conversations on-going on whether this can be a centrally funded solution under the REC, or if Parties would be required to organise bespoke/direct reporting arrangements directly with DTN/DTSA 16/01/26 - Information Request open until 30/01/26 31/10/25 - accepted in | 26/06/2026 but recommending rejection | DTN | No
CP1622 Amendment of validation within SMRS for number of Meter Digits | BSC | REC | CP1622 | [14 empty] | R0300 | [19 empty] | 11/05/26 - both changes approved for June release 26/03/26 - both consultation open, BSC closing 17 April and REC 21 April. Concerns raised by REC TEP that June implementation is too soon 26/02/26 - now no longer urgent, REC is at Party IA closing 13/03/26. Discussed with Sam at BSC, we will look to align consultations in early April 12/01/26 - further investigation has suggested the validation rule need to stay in place as it's Displayed register digits - believe this needs to go on hold while this is investigated (BSC currently aiming for Feb final vote) 15/12/25 - REC change R0300 has been raised 27/11/25 - potential REC change needed, may impact D0312 and IF-005 St Clements s/w impacted | 2026-06-25 | DTN, SMRS | No
R0299 Data Latency Targets for the GES Service Definition | REC | info only | [15 empty] | R0299 | [19 empty] | 26/03/2026 - approved for June release 26/02/2026 - at consultation, closing 12/03/26 12/02/2026 going to Change Panel on 17/02/2026, expected to go immediately to consultation later that week 04/12/2025 Issue accepted in - follow on fron R0277 | 2026-06-26 | GES | No
R0307 Release and Licensing of the CoMCoP Logo for Accredited Parties | REC | For info | [15 empty] | R0307 | [19 empty] | 11/05/2026 - approved for June implementation 16/04/2026 - final vote at Change Panel on 21/04/26 12/03/2026 - consultation closing 27/03/26 26/02/2026 - plan published, for approval at Change Panel on 03/03/26. Expected to proceed immediately to consultation 15/01/2026 - accepted in | 2026-06-26 | n/a | No
I0308 Update CCSG ToRs to include cross-code prioritisation as per Code Reform | REC | For info | [15 empty] | I0308 | [19 empty] | 11/05/2026 - approved for June implementation 26/03/2026 - consultation closes 14/04/26, legal text updated as per CCSG review 12/03/2026 - report going to change panel 17/03/26 and then will immediately proceed to consultation 05/02/2026 - accepted in | 2026-06-26 | n/a | No
R0310 Addition of value 11 to data item J0418 | REC | For info | [15 empty] | R0310 | [19 empty] | 11/05/2026 - approved for June implementation 16/04/2026 - final vote at TEP on 29/04/26 26/03/2026 - consultation closes 14/04/26 12/03/2026 - report going to change panel 17/03/26 and then will immediately proceed to consultation 05/02/2026 - accepted in - believe will have no BSC impact as CoP11 already exists and this data item is owned by REC, but to confirm | 2026-06-26 | EMDS | No
DCR0021: ‘Enabling early DIP On-Boarding for Applicants and Potential DIP Users’ | DIP | BSC, REC | tbc | [14 empty] | tbc | [14 empty] | DCR0021 |  |  |  |  | 15/06/2026 - final assessment published, expecting approval 01/06/2026 - out for consultation, closing this week. Expected to be a "last resort" situation - to be on boarded but could not send/receive messages as can set EFD to the required date. Power would only exist until M14 (end of qualification) 18/05/2026 - The DIP Rules, outlined in the DIP Subsidiary Document (DSD) 002, titled “DIP Connection and Operation,” specify the procedures that DIP Applicants and Users must follow when using the DIP. A key part of this process involves transitioning an Applicant or Potential User to the Production Environment, which occurs after they have qualified under an Industry Code or the MHHS Qualification. In the coming months, a large number of market participants will pursue the MHHS Qualification and subsequently seek to be on-boarded to the DIP. This situation poses a risk for the DIP Manager and could impact the service and support provided. To mitigate this risk, the DIP Change Request (CR) aims to empower the DIP Manager to onboard select market participants early. This proactive measure is intended to prevent any service or support disruptions that may arise from the increase in MHHS qualification volumes. The DIP Manager plans to implement this change as part of a non-standard release scheduled for June. | 2026-06-25 | tbc | tbc
MP184 - Changing the way twin elements are used - additional MPANs for Export capability | SEC | REC - I0221, BSC - no impact, DCUSA - no impact | [15 empty] | I0221 - linked, but not "true" cross-code |  |  |  |  | MP184 | [14 empty] | 29/06/26 - SEC mod withdrawn, REC mod should be withdrawn by 10 July 10/06/26 - Proposer has withdrawn proposal. SEC allows 10 working days for another party to adopt. If elapsed and no Party takes up changes, the proposal will be removed from register. 18/05/26 - Change board decision due 24 June 26 - might ask Proposer to withdraw, but unsure at this stage. 20/04/26 - SECAS exploring options with proposer 30/03/26 - Change board rejected request for latest Impact Assessement - next steps tba 13/02/26 - updated PIA requested from the DCC 02/02/26 Requirements workshop top be held 09/02. 12.01.26 - Requirements workshop to be arranged 07.11.25 further requirements Workshop to be arranged for New Year confirming against new DSP build. Will then likely progress to final Impact Assessment. 31.10.25 - refinement consultation responses undergoing analysis expect to move to request for full I.A. 08.10.25 - Refinement Consultation issued. BSC & REC have indicated that requirements can be supported without changes to industry data / flows / processes. 10.09.25 - Detailed requirements being developed ahead of refinement consultation. 16.06.25 - SECAS discussing meter design impacts with manufacturers, & review with the DCC for assessment and potential move to consultation. 29 Jan 25 - SEC in discussion with REC and BSC re relevant changes. Awaiting confirmation from Proposer re solution to progress. | tbc | tbc | No
I0176 - Creation of an Energy Theft Detection and Resolution Body | REC | Watching brief only | [15 empty] | I0176 | [19 empty] | 20/07/26 - withdrawn, adoption window closes 31/07/26 21/07/25 - expected to be part of RECCo White Paper being consulted on in September 30/05/24 - theft change. Creating new central option for investigation. No expected cross code impact |  | n/a | Yes
Issue 119 Understanding and assurance of increasing electricity losses (LLF & GCF) | BSC | DCUSA - tbc, REC - tbc | Issue 119 |  |  |  |  | tbc | [9 empty] | tbc | [19 empty] | 20/07/26 - Issue closed 18/05/26 - fourth work group expected shortly, proposer wants to close Issue down. CP expected with post closure with legal text 02/02/26 - second work group in Oct 25, no solution identified as yet There are growing concerns in the industry about rising electricity losses, especially as shown by Line Loss Factors (LLFs) and the Group Correction Factor (GCF). BSCP128: Production, Submission, Audit & Approval of Line Loss Factors explains how to calculate LLFs. However, many in the industry do not fully understand why LLF and GCF values change. | n/a | n/a | No
0887 - Facilitating Bi-Directional Connections Between IGT Pipelines and the NTS | UNC | iGT - iGT176 REC - none | [10 empty] | iGT176 | [14 empty] | 0887 | [9 empty] | 17/08/26 - IGT176 Implemented. 31/07/26 Implementation confirmed for 14 August 2026 20/07/2026 - no updates on when in August this is due to be implemented 17/04: Current anticipated implementation date in Aug 26 13/01: UNC0887 and IGT176 approved. Implementation TBC. 01/12/25 - IGT176 approved by Authority, implementation date TBD 15/09 - iGT 176 still with Authority 19 Aug - Authority direction issued to implement on a date to be determined 04/07: June UNC Panel Recommended Implementation, now with Authority for decision 29/05: WGR Published and reporting to June 25 UNC Panel 19/05: IGT176 raised, under WG progression, 07/04: Update provided to CCSG - Reporting to April 25 UNC Panel 24/03: IGT176 has been raised, which will enable the elements under 0887. IGT Impact 17/03: IGT has submitted draft proposal for necessary IGT changes to allow for IGT supply points on these NTS connected networks to be considered non-CSS / NTS supply points, also means SPA arrangements need re-introducing. Mod expected to be raised ahead of March Panel. 11/11: Reporting to January 2025 UNC Panel. | 2026-08-14 | CDSP | Yes
DCR0018: DIP Swagger alignment with Energy Market Data Specification (EMDS) | DIP | DCUSA |  | tbc | [28 empty] | DCR0018 |  |  |  |  | 30/07/2026 - decision to be published this week, alongside DCR0022 and DCR0019 (Scope of Aug release) 20/07/2026 - final assessment being published 18/05/2026 - Currently, there is a misalignment between EMDS and DIP Swagger concerning the list of Meter Point Administration Numbers (MPANs) on site in the REP900 file. This has created misalignment between EMDS and DIP Swagger. The DIP Manager has amended this to ensure there is alignment between Swagger and EMDS. | 2026-08-13 | DIP | tbc
DCR0019: Defining the Sender Unique References (SUR) in the DIP Rules | DIP | For Info | [30 empty] | DCR0019 |  |  |  |  | 30/07/2026 - decision to be published this week, alongside DCR0022 and DCR0018 (Scope of Aug release) 06/07/2026 - final decision to be published 01/06/2026 - out for consultation, closes end of the week 18/05/2026 - When sending and receiving messages through the DIP, Users are required to use a ‘Sender Unique Reference’ (SUR) to identify the origin of the Message. This reference must consist solely of alphanumeric characters (such as A, B, C, 1, 2, 3). However, some users have been using non-alphanumeric characters (such as £, $, %, or -), which have caused validation issues and disrupted message flow among DIP users. To address this problem, it is proposed that the SUR requirements be defined in the DIP Rules (DSD002, Annex 2), mandating that only alphanumeric characters be used. This change aims to reduce the risk of validation failures. The implementation of DCR0019 is scheduled to occur as part of the DIP Manager monthly release in August 2026 30/07/2026 - | 2026-08-13 | tbc | tbc
Pre-raise Enabling trad WC in advanced segment | BSC | REC | tbc | [14 empty] | tbc | [19 empty] | 05/08/2026 - discussion with BSC, REC and Proposer (Eon) have lead to determining this change will be withdrawn and a new CP raised (added to tracker) 07/07/2026 - assumption made the main impacts will be to SMRS, if this assumption is correct BSC should be lead code 06/07/2026 - conversation about whether REC or BSC need to be lead code | tbc | SMRS | tbc
I0247 - Effective Dates in EES | REC | BSC- tbc | tbc | [14 empty] | I0247 | [19 empty] | 13/08/2026 withdrawn, adoption window closes 28/08/2026 | tbc | EES, CSS - tbc, MPRS - tbc | No
I0275 MHHS Metering Points across Market Segments | REC | BSC - n/a DIP - n/a | [15 empty] | R0275 | [21 empty] | 21/09/26 - resolved - guidance document published. 13/11/2025 - will be moved to resolved once guidance document published, no REC change needed. Expected there will be a BSC change (this has now been raised as CP1628) 31/10/2025 - to be presented at Nov CHIG, potential to be withdrawn 02/10/2025 - presented at Change Issues Group 14/08/2025 - accepted in | n/a | n/a | No
Note on X47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do not believe any direct impact to SEC from 459 proposals. However the proposer for DP206 is reliant on P459 progressing.

## Sheet2
Compatibility Report for CCSG Log.xls
Run on 10/02/2023 16:14
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 5 | Excel 97-2003

## Key
withdrawn / implemented
no impact
open action