## Slide 1: Supplier Fuse Upgrades Giannis Katsaros, ENA
12 February, 2025

## Slide 2: Agenda
Project overview
Benefits for parties involved
Timeline
Work scenarios for MEMs/SIPs
Training programme
Associated costs
Questions to the audience

## Slide 3: Project Overview
Why is this project important?
Objectives
What has happened so far?
1
2
3
UKPN trialled this with Octopus Energy Services under the NIA funded Emerge Project Trials from March 2022 to February 2023.
NGED has performed similar trials with Octopus Energy Services
The decarbonisation of customer’s homes remains a key focus in the transition to Net Zero.
DNOs are at risk of being a barrier to the uptake of heat pumps and electric vehicle charge points with installations highly dependent on the successful upgrade of domestic supplies.
To develop a training programme that will allow MEMs/SIPs to upgrade cut-out fuses facilitating new installations (LCTs, property extensions, etc.) in domestic properties

## Slide 4: Benefits for parties involved
Benefit | Description | Benefit to DNOs | Benefit to suppliers | Benefit to Customers
No need for a DNO engineer to perform a site visit | Currently DNO engineers need to visit the site when a fuse upgrade is needed | Varies per DNO Circa £250 per visit | Organisations may complete the fuse upgrade and LCT installation in a single visit Organisations can schedule the LCT installation and fuse upgrade date in advance | Fewer site visits and disruption
Faster for customers | Customer should get the LCT installation more quickly | Improved customer service | Improved customer service | Improved service Supporting with emergency purchases
Politically beneficial | DNOs are under pressure to improve this fuse upgrade offering following Emerge innovation project | Completes the action outlined in Octopus letter to Ofgem DNOs increase their consistency and collaboration credentials | Improved customer service | Improved customer service

## Slide 5
2024 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
July | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | April | May | June | July | Aug | Sep | Oct | Nov | Dec
WS1: Engineering recommendation(EREC)doc. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WS2: Determine changes on standards and codes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WS3: Design of training program |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
WS4: Program comms and launch |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
First stage gate
TODAY
ENA develops the first draft of EREC
Identify ENA groups for input, development, sign-off
ENA to issue RFI to DCUSA
Formation of DCUSA WG and implementation of code changes
Industry consultations discussing proposed changes
Task
Develop training assessment strategy (duration, quals needed, etc.)
Develop training material (based on outcome of WS1)
Second stage gate for ENFG to approve
Engagement with REC to implement code changes
Develop Comms plan (key messages, target audience, press release, etc.)
High level project timeline
Please not that these are estimated timescales
DCUSA decision to form a WG
Implemented changes in
DCUSA and REC
Milestone
Stage gate
Program
launch
Review time for ENA groups
Update EREC
Engagement with MEMs/SIPs

## Slide 6: Work scenarios for MEMs/SIPs
ENA outlined three work scenarios for MEMs/SIPs
Scenarios were developed based on discussions with various ENA groups
DNOs decided to proceed with scenario 1 excluding phenolic resins
Training Level | 1 | 2 | 3
 | Scenario 1 | Scenario 2 | Scenario 3
Type of Supply |  |  | 
Single phase |  |  | 
Three phase |  |  | 
Type of cables |  |  | 
Plastic |  |  | 
PILC |  |  | 
Type of cut-outs |  |  | 
Single phase plastic/(grey, black)* |  |  | 
Three phase plastic (grey, black) |  |  | 
Location of service lines |  |  | 
Underground network |  |  | 
Overhead line network |  |  | 
* Excluding phenolic resins

## Slide 7: Pre-authorisation potential routes
Pre-authorisation strategy
Option A. Pre-authorise each Supplier and each SIP organisation before signing-up to the scheme
Option B. Pre-authorise each fuse upgrade request from a supplier or SIP before introducing a larger fuse on each job
Threshold on limit upgrades (based on pre-authorization step)
If Option A:
  A standardised threshold across the DNOs would need to be agreed
  Currently the majority of DNOs have the position to limit upgrades to 80 amps
If Option B:
  The size of the fuse can be determined on a per job basis

## Slide 8: Design of training program - Potential route through NSAP
National Skills Academy for Power (NSAP) Smart Meter Installer course includes fuse replacement (module 06)
Develop additional module for upgrading a fuse (module 07)
All DNOs to agree module content
Module delivered by various educational organisations
The programme will be designed to:
    Replacing and upgrading fuses only
    Include auditing of training provider (auditing of installers as part of the requirement)
    Each installer will register on Energy and Utility Skills Register (EUSR)

## Slide 9: Costs
# | Cost item | Description | Info about cost to DNOs | Info about cost to suppliers/installers
1 | Training programme | (MEMs/SIPs) Training through NSAP modules. EUSR platform registration | Effort to create the additional module | EUSR Registration £30 per 3 years
2 | Fuse upgrade decision and audit trail | Creation of new data flow as a mean of communication between DNOs and MEMs/SIPs | £70,000-£90,000 (addition of relevant feature in ENA Connect Direct platform if chosen) | Option A: IT costs to create this new data flow in the current system (Data Transfer Network) Option B: £0 if ENA Connect Direct is chosen
3 | Impedance loop testing | Purchase and maintenance of equipment | £0 | TBD - depends on the supplier how they prefer to manage this cost
4 | Compensation | Compensation to MEMs/SIPs for the fuse upgrade work | Option A: £0 for DNOs as suppliers offer this work to enhance customer service Option B: DNOs offer some compensation for the work | Option A: Cost of fuse (small amount of money)
Assumptions: NSAP designing the training program
EUSR: Energy and Utility Skills Register

## Slide 10: Questions for the audience
What are your thoughts about the proposal?
What are your thoughts about the additional training/competency (earth loop impedance testing etc).
What are the possible blockers to your company getting involved?

## Slide 12: Code changes in DCUSA/REC
DNOs to to participate in DCUSA/REC working groups to:
  Identify the necessary changes required within DCUSA and REC (MOCoP) to accommodate the new arrangements in industry governance and recommend changes
Aim is for implementation to happen by November 2025, but this will be subject to following due process with DCUSA and REC
7