## Slide 1: I0237 WORKING GROUP 6
19 February 2026

## Slide 2: Agenda
Agenda Item | Presenter
Welcome and Introduction | Chair
Review minutes and actions of previous meeting | Chair
Review updated guidance document | Chair / All
Feedback on existing processes or issues: MHHS Programme Consumer billing Change of Supplier reads Phone line requirements Ombudsman process Objections following an agreed ES New topic - Erroneous Switch and Vulnerable Consumers | Chair / All
Any Other Business – see slides for Code Manager additions | All
Next Steps | Chair
Date and Time of Next Meeting | All

## Slide 3: Review minutes and actions of previous meeting

## Slide 4: I0237 actions log
Date action taken | Action Detail | Action Owner | Due | Action status
10/09/25 | Discuss options for Performance Assurance review of re-registrations and objections when ES flag set | LM | tbc | Ongoing – to be discussed after Working Group 6.
09/10/25 | Review possible proposals for multilateral ES and bring to future working group | LM & JaH | tbc | Ongoing – to be discussed at a future working group
06/11/25 | New reason code for Non-Domestic only to account for TPI Sales and discussion with Ofgem | LM & JaH | tbc | See update in AOB
11/12/25 | Draft options for handling pending Switching and multilateral Erroneous Switch cases. | LM & JaH | tbc | Ongoing – to be discussed at working group 7
22/01/26 | Reconfirm with DCC whether ES-flagged Switches bypass Objections or only standstill; and assess whether REC Schedule appropriate accounts for this and determine whether a separate REC Change is required. | LM / JaH | 19/02/26 | Discussions with DCC on what, if any changes are required ahead of any CSS solution.
22/01/26 | Publish Domestic Rejection Reasons Guidance and add a Technical Reasons clarification and scope fraud-related guidance. | LM | Following WG 6 | On agenda and will be published following discussions.
22/01/26 | Investigate SDEP Domestic/Non-Domestic split feasibility and review prior Change Proposals and impacts. | LM |  | Initial view to be presented at a future meeting.
22/01/26 | Add clear escalation signposting to the Guidance Document (i.e. Code Manager, OAMs, Performance Assurance). | LM |  | To be included in next guidance document update.

## Slide 5: I0237 actions log
Date action taken | Action Detail | Action Owner | Due | Action status
22/01/26 | Review Energy Supplier evidence on CoO flag use patterns. Code Manager to explore interim reporting by Performance Assurance and include in CSS assurance scope. | LM / BR | tbc | 
22/01/26 | Energy Suppliers to provide further feedback with the Code Manager on the Change of Occupier flag and its potential misuse. | Energy Suppliers | 19/02/26 | To be submitted ahead of the February meeting.
22/01/26 | Draft REC Change to include short terms solutions, including to reduce ES time limit from 24 to 12 months ahead of the CSS solution. | LM / JaH | 19/02/26 | Duplicate – see action from 09/10/25

## Slide 6: I0237 actions log
Date action taken | Action Detail | Action Owner | Due | Action status
09/10/25 | Review options for reducing Erroneous Switch time limit | LM & JaH | 19/02/26 | Closed - draft CP and legal text provided in pack
09/10/25 | Following Ofgem engagement, draft guidance note on ES rejection reasons | LM & JaH | 19/02/26 | Closed – updated guidance provided in pack.
06/11/25 | New definition for “Technical Issues” reason code and to ensure there are no reason code duplicates | LM & JaH | 19/02/26 | Closed – updated guidance provided in pack.
06/11/25 | Draft template for Non-Domestic Gas Suppliers Contacts and circulate via OAMs for Population | LM & JaH | 22/01/26 | Closed – with OAMs for population
11/12/25 | Working Group members to provide further feedback to the Code Manager on the proposed CSS option and any alternative solutions | All Working Group Members | 22/01/26 | Closed – updated solution to be presented at working group 7

## Slide 7: Review updated guidance document

## Slide 8: Updated Guidance document
What is the guidance document?
It has been drawn up by the Code Manager following feedback at the I0237 working group to support the Erroneous Switch Process as set out in Schedule 30.
It is already available on the REC Portal providing guidance on the correct use of the ES Flag.
New Section - Domestic Rejection Reasons
Examples of valid and invalid rejection reasons have been set out. This has been drawn up primarily using the MRA Transitional Schedule.
Non-Domestic rejection examples will be drawn up separately.
New Section – “Technical Issues” ES Reason
The MRA Transitional Schedule was used to provide a definition of the electricity only ES reason code.
It has been updated to recognise the implementation of CSS which has reduced considerably the risk of split Related MPANs.
New Section – ES Escalations Structure
The Code Manager has drawn up an ES specific summary of the end to end escalations process.
Links have been provided to the SDEP User Guide and the SDEP escalations guide

## Slide 9: Feedback on existing processes

## Slide 10: Feedback on existing processes
Any MHHS Issues to flag?
Have there been any unexpected impacts on the ES process as a result of MHHS migration?
  For example - if MPAN is migrated but losing supplier hasn’t started yet
  Is there anything needed in the guidance document?
Consumer billing
Should the REC provide further details on the steps a Losing Supplier should or should not take following the re-registration of the MPXN.
  Is the SLA and the back billing obligations enough?
  Should the REC include any SLAs or additional detail?
  Is there anything needed in the guidance document?
Change of Supplier Reads
Are there any Erroneous Switch specific issues with D0086 / D0300 / SAR processes that require investigation?

## Slide 11: Feedback on existing processes
Phone line requirements
Having a phone line for supplier-to-supplier calls is currently mandatory – is it still required?
How often is it used?
What are the alternatives?
Ombudsman Process
Any recommended improvements or feedback – for example both suppliers are made aware of the recommendation to resolve via an ES
Objections following an agreed ES
Aware it can happen – what updates or clarifications to the REC are needed?
How often does it happen?
Is it an issue more for Non-Domestic or Domestic Consumers?
Erroneous Switch and Vulnerable Consumers
Are additional steps required for Vulnerable Consumers?
  For example is a mechanism needed for sharing Priority Services Details if an update is provided before the Consumer’s MPXN Switches back?

## Slide 12: Any other business

## Slide 13: Microbusiness & TPI processes
How did we get here?
The working group suggested the Code Manager looks into created new Erroneous Switch processes for Microbusiness consumers and TPI sales.
As Microbusiness consumers have (or will have) additional protections the working group wanted the ability to flag these separately.
As TPIs will soon be regulated the working group suggested there should be an ability to flag an Erroneous Switch that was caused by a TPI to help assure them once the regulations are in place. This would not be limited to Microbusiness Consumers so would be for all Non-Domestic Consumers
What has happened since?
Code Manager has discussed the 2 suggestions with Ofgem who has agreed they are worth further development.
Code Manager has looked into how each suggestion could be taken forward. This has focussed on how to implement them as efficiently as possible in terms of system impacts, additional training and consumer impacts. Also looked for options that could be implemented before the CSS Solution.
Use of the Erroneous Switch Reason Code
Create ES Reason Codes that would be specific to Microbusiness and TPI scenarios and also continue to flag the type of ES.
  For example: code Q = TPI Incorrect MPXN and code L = Microbusiness

## Slide 14: Microbusiness & TPI processes 2
Does the working group have any alternative solutions they would like investigated?
Is a new data item and grouping better?
Is the working group happy for this to be developed further?
Code Manager would draw up the ES Reason Codes and bring back to the next working group.

## Slide 15: Multilateral ES
How often do they happen?
Any data available?
Do they happen more in gas or electricity
Do they impact Domestic or Non-Domestic Consumers more?
What are the options longer term?
No process is developed and instead the REC confirms what steps suppliers should follow when one is uncovered.
Code Manager develops option separate to the CSS solution. Code Manager welcomes suggestions.

## Slide 16: Customer service returners
Should they be included in the CSS Solution?
They aren’t an erroneous switch so should they follow the same process and SLAs?
What are the options longer term?
No process is developed and instead the REC confirms what steps suppliers should follow when one is uncovered.
Code Manager includes them in the CSS Solution.
Code Manager develops option separate to the CSS solution. Code Manager welcomes suggestions.

## Slide 17: Next steps

## Slide 18: topics for discussion for working group 7
Update on all actions
Review draft CP based on discussions to date
Review Microbusiness and TPI solutions
Review of CSS solution changes to date
Discussion on working group recommendations for assurance reporting
Review topics decision log
What happens next

## Slide 19: Date and time of next meeting – 26 March 2026