## Sheet1
Reference | Action | Owner | Progress | Status
MSAG03-01; 30/09/22 | RECCo to confirm with the MHHSP that the D0300 will not be sent to the NHHDC / SDS following agreement of the read and instead the Supplier will enact a consumption correction. | JH | 19/04/23 - this is the understanding of the design being taken forward 15/03/23 - ongoing and being addressed under the Registration tranche of the MHHS Code Drafting | Complete
MSAG05-05; 18/01/23 | RECCo to confirm the approach and timeline for engaging with industry on the changes to the EES API technical specification. | JM | 19/04/23 - milestones dates to be provided in meeting 12/04/23 - specification expected in August 23, to be included in Code Drafting Conseq Change tranche. Milestones being tracked under EES. 12/04/23 - specification expected in Aug 23, to be included in Code Drafting Conseq Change tranche. Milestones beign tracked under EES 15/03/23 - ongoing | Complete
MSAG06-03; 18/01/23: | Members to provide comments on redlined CFSB drafting. | SJ | 15/06/23 - Action closed in meeting, further feedback to be covered in agenda item 4, Switch Read Exceptions. 19/04/23 - Action to remain open, members encouraged to review redlining on Switch meter reads exceptions. Document will be included with the post meeting papers. 15/03/23 - ongoing and that the latest drafting of Schedule 30 will be shared with the post meeting papers on 22/03 | Complete
RECMSAG_23_0315_01 | Committee Secretary to upload new actions log to REC MSAG Committee page on the REC Portal. | HT |  | Complete
RECMSAG_23_0315_02 | HT to look into options for easily identifying MHHS related Change Proposals on the REC Portal. | HT | 08/06/23 - Downloadable CP Register now includes MHHS indication in column Q. CP front pages will start to include a note where applicable in the Latest Update section. 19/04/23 - propose to update downloadable CP tracker to include MHHS indicator and ensure Change Summary text on CP front page to provide indication. Update to be provided at next meeting. | Complete
RECMSAG_23_0315_03 | JB to gather input from DNO community as to whether the Expected Connection Type would be required in the New/Additional MPAN request in SDES in order for the DNOs to process the request. | JB | 19/04/23 - KK provided an update in the meeting on behalf of JB. No external input had been received but an internal response confirmed that the key information they needed as a DNO was whether the MPAN was for import or export as the DNO needs to provide the LLFC | Complete
RECMSAG_23_0315_04 | RECCo to bring back analysis on ETs and the impact on the current processes for anything not NHH to a future meeting. | SJ | 12/04/23 - On agenda for 19/04/23 | Complete
RECMSAG_23_0315_05 | RECCo to update CSS User Roles proposal document with the MHHS milestone for the start of migration and clarity on the decision relating to not including Data Services as CSS Users | SJ | 12/04/23 - Updated and shared with post paperes on 22/03 | Complete
RECMSAG_23_0315_06 | RECCo to confirm the rationale from MHHS design discussions for limiting access to the identity of the agent that set the Customer Direct Contract Flag - EES Data Access. | SJ | 12/04/23 - On agenda for 19/04/23 | Complete
RECMSAG_23_0315_07 | RECCo to confirm with MHHS Programme if design issue required to extend access to include the identity of the agent that set the Customer Direct Contract Flag. | SJ | 12/04/23 - On agenda for 19/04/23 | Complete
RECMSAG_23_0315_08 | RECCO to bring updated EES DAM being brought back to a future meeting. | SJ | 12/04/23 - On agenda for 19/04/23 | Complete
RECMSAG_23_0315_09 | RECCo to confirm whether the old Supplier will know about an MPAN migrating or if they have to check in EES. | SJ | 22/03/23 - The outgoing supplier will receive a D0010 with the Meter Reading Reason Code populated with '29' - Forward Migration COS following agent appointment by the new supplier. This information will likely be received too late to help populate the D0311. This only applies to MPANs currently settled NHH. | Complete
RECMSAG_23_0315_10 | RECCo to consider whether the existing rule that the time of the last reading should be set to 00:00:00 should be removed and make sure that it's clear in the proposal how it should be managed during transition. | JH | 19/04/23 - MHHS design does not take into account the time of a register reading therefore there is no clear requirement to change this rule. Therefore the proposal is to leave the rule as is. | Complete
RECMSAG_23_0315_11 | The Code Manager to send out the invite for the next meeting for the morning of Wednesday 19 April 2023. | HT |  | Complete
RECMSAG_23_0419_01 | New/Additional MPANs: RECCo/Code Manager to raise and progress the REC issue to consider the potential requirement to add the Expected Connection Type in the current SDES New/Additional MPAN request from June 2023 under the standard Code Manager processes. | JH/HT | 15/06/23 - No comments received at RIG. RECCo/Code Manager to consider next steps. 08/06/23 - Issue raised at the REC Issues Group (RIG) on 12/05. RIG attendess requested time to consider this internally and will bring any comments back to the next RIG on 09/06. | Open
RECMSAG_23_0419_02 | Amendments to DTN flows: Slides to be updated to reflect the removal of the D0313 changes and to update the D0302 changes. | JH | 26/04/23 - included in post meeting papers | Complete
RECMSAG_23_0419_03 | Missing Meter Technical Details request: SJ to update the proposal and draft legal text to clarify applicability to Traditional and Advanced assets only and the queries are to be raised to the Losing Supplier where the Losing MEM does not have the MTDs to share. | SJ | 08/06/23 - Updates made and captured in MHHS Consequential Change - Meter Technical Details Request v2.0. This was published with the post meeting papers on 26/04. | Complete
RECMSAG_23_0419_04 | Members to contact the REC MHHS team if they are able to volunteer for industry review of approach for reflection of Interface and ECS Reporting Catalogues in EMAR. | SJ | 08/06/23 - Volunteers have come forward | Complete
RECMSAG_23_0419_05 | Members to contact the REC MHHS team if they are able to volunteer for industry review on EES development. | JH | 08/06/23 - Volunteers have come forward | Complete