## Slide 1: APPROACH to deferred programme change

## Slide 2: MHHS Programme Change
On Hold Change Requests
Deferred Design Issue Notifications (DINs)

## Slide 3: OHCRs rec approach
On Hold Change Requests
Programme Change Requests that were placed on hold as they didn't meet the requirements of the Change Freeze (fix a defect in the design, or critical to Milestone 10 (M10)).
Programme Change Board confirmed closure and for the changes to be progressed under BAU on 28 January 2025.
Seven change requests
  One REC change in flight;
  Three potential REC changes on Code Manager internal log
  Three where no REC change required
Where REC change required, OHCRs to be progressed through the BAU change process
Prioritisation in line with others on Change Register, which includes consideration of SCR/MHHS
Cross code dependencies managed through Cross Code Steering Group and REC engagement in Elexon’s MHHS Expert Group

## Slide 4: On hold change Requests
Date Raised | On Hold Change Request Number | Change Request Narne | Raised by | MHHS CR Number | Reason for postponement | Change Board Decision | REC change requirement
Jun-23 | OHCR001 | Data Item Names and Descriptions | RECCO | CR024 | Deferred to a post-M10 implementation at DAG 13 Mar-24. | Closure of On-Hold Change request. Recommendation for raiser to go through BAU process. | No REC change required - REC drafting already reflects updates
Jun-23 | OHCR002 | DIP Interface Name Changes | RECCO | CR025 | Deferred to a post-M10 implementation at DAG 13 Mar-24. | Closure of On-Hold Change request. Recommendation for raiser to go through BAU process. | No REC change required - REC drafting already reflects updates
Feb-24 | OHCR003 | Implementation Of 'Data Refresh' Message IF-051 | MHHSP | CR044 | PPIR issued to gather views on whether solution is implementable pre-M10. Rejected at PSG on 05-Jun-24 based on PPIR responses. Recommended tor post-M10 implementation. | Closure of On-Hold Change request. Recommendation for raiser to go through BAU process. | Potential REC change required - BSC CP 1607 raised. IA required to understand REC impact.
Feb-24 | OHCR004 | Supply Start Date (SSD) correction Tool | MHHSP & SCS | CR045 | PPIR issued to gather views on whether solution is implementable pre-M10. Rejected at PSG on 03-Jul-24 based on PPIR responses. Recommended tor post-M10 implementation. | Closure of On-Hold Change request. Going through BAU process as R0201, IA response submitted by Programme. Implementation target date of February 2026 (or after Early Life Support). | R0201 progressing, BSC CP 1606 raised and at consultation. Cross code alignment agreed. Suggested implementation date by BSC March 2026.

## Slide 5: On hold change Requests
Date Raised | On Hold Change Request Number | Change Request Narne | Raised by | MHHS CR Number | Reason for postponement | Change Board Decision | REC change requirement
Jul-24 | OHCR005 | Validation of Service Provider COS Appointments | British Gas | N/A | CR raised to Programme in July 2024. PPIR issued to all Participants, responses confirmed pre-M10 implementation is not feasible. CR not eligible for pre-M10 Change Control process as post-M 10 implementation does not meet the Change Freeze criteria. | Closure of On-Hold Change request. Recommendation for raiser to go through BAU process. | BSC CP expected. REC change impact to be understood. On BSC's agenda for MHHS Expert Group 18/06/2025.
Jul-24 | OHCR006 | Advanced Register Read and Meter Configuration Inclusion | LSC | N/A | CR not eligible for pre-M10 Change Control process as implementation not required until after M10, as stated by Change Raiser. | Closure of On-Hold Change request. Recommendation for raiser to go through BAU process. | BSC Issue 118 raised (Requirement to send D0149 for some Advanced MPANs, SSC to be mandatory for some Advanced MPANs). REC changes expected. CCSG to confirm lead code.
Nov-24 | OHCR007 | Remove requirement to respond to DIP With a JSON body | Helix | CR057 | Rejected by PSG due to not meeting the pre-M10 Change Freeze criteria, with the alternative solution recommended for implementation. | Closure Of On-Hold Change request. Alternate solution for CR057 undergoing testing. Recommendation for change raiser to go through BAU process if the proposed solution from OHCR007 is required post-M10. | No REC change required

## Slide 6: Deferred DINs
Deferred DINs
DINs raised, confirmed as needing a change BUT NOT updated in the MHHS design
Change to be progressed via BAU change processes
DIN log
Live, DINs still being raised and going through process to be confirmed as required and deferred
Current status 16/06/2025
100 Deferred DINs = Assessment Complete / Implementation Deferred
2 aligned to REC – both confirmed as need design/Swagger updates but REC change already captured
Further 55 DINs added to DIN log
  11 = Assessment Complete / Implementation Deferred
  1 known REC change required:
MHHS-DIN-1191 | D0383 requirement to send to supplier | Documentation published by the MHHS programme and the REC say that the flow does go to the supplier, we believe this documentation is incorrect and needs to be updated to remove any reference to the supplier receiving the D0383 data flow |  | Open - awaiting assessment | Error/correction

## Slide 7: Deferred DINs rec approach
Where REC change required, deferred DINs to be progressed through the BAU change process
Known potential REC changes on Code Manager internal log
Opportunities for grouping to be considered
Prioritisation in line with others on Change Register, which includes consideration of SCR/MHHS
Cross code dependencies managed through Cross Code Steering Group and REC engagement in Elexon’s MHHS Expert Group