## Slide 1: I0296 – CSS REGISTRATION ID required for mhhs Agent appointments
Background
An issue has been identified through MHHS Early Life Support that if the DI-849 ‘Central Switching Service (CSS) Registration Id’ data item is not provided by the Supplier in the IF-031 ‘Supplier Agent Appointment Request’ Market Message, the appointment request is rejected by SMRS (Supplier Meter Registration Service). Where the item is not known and so not able to be populated, this is preventing Suppliers from appointing MHHS Agents and initiating MHHS Migrations.
The item DI-849 itself is currently optional within the IF-031, but the SMRS system design does require the CSS Registration Id in order to identify the Suppliers registration.
It is apparent that not all Suppliers know the CSS Registration Id for all their Metering Points, especially for Metering Points that haven’t been switched via CSS processes.
The item is available to Suppliers via Electricity Enquiry Service (EES), but only for Metering Points that have switched via CSS.
As the item is required to appoint MHHS Agents as part of the MHHS Migration process, Suppliers not being able to access the item could impact Suppliers being able to meet their MHHS Migration plans and put the MHHS Migration Milestone (M15) at risk.
This Issue has been raised to investigate options to provide Suppliers the CSS Registration Id where it is not known to allow MHHS Agent Appointments to be progressed.
Elexon are progressing a separate BSC CP to make the CSS Registration Id mandatory within the IF-031.

## Slide 2: I0296 – CSS REGISTRATION ID required for mhhs Agent appointments
Resolution Options
Two potential options have initially been identified:
A Code Manager process where CSS Registration Ids for Metering Points not having been through a CSS managed switch are provided to Suppliers.
  This would be quick to implement but would be a short-term exercise to provide the CSS Registration ID for MHHS Migration to Suppliers on request.
An EES solution to publish the CSS Registration Id for all Meter Points and not just those having been through a CSS managed swich.
  This would require technical changes to the EES solution and require a longer implementation time (subject to an impact assessment). However, it would be an enduring solution.
Given that the MHHS Migration is under way and this issue is currently preventing Metering Points from Migrating, it is felt that the Code Manager solution would be the best to progress in order to quickly mitigate the MHHS Migration Risk.
The Change Issue Group is asked for comment on:
  Are there alternate options that should be considered; and
  Do they agree that the Code Manager managed solution is the preferred option given the MHHS Migration timescales.