## Live CP Register
Change Proposal Reference | Change Proposal Title | Link to CP page | Proposer Name | Proposer Company | Lead Analyst | Date Submitted | Change Category | Priority Status | Change Path | Responsible Committee | Proposed Implementation Date | Fuel | Impacted Parties | Process Stage | Next Activity | Next Activity Due Date | On Track (RAG)
R0006 | Missing Meter Technical Details | Link | Diane Lyon | Scottish Power Energy Retail | Ann Perry | 2021-09-07 | 1 | Low | Self-Governance | Change Panel | TBC | Elec | Energy Suppliers Metering Equipment Managers Data Collectors | Solution Development | Performance Assurance Activity concludes | 2022-06-30
R0008 | Consequential New and Amended Market Messages for BSC Modification P375 | Link | Gemma Dixon | Code Manager | Gemma Dixon | 2021-09-08 | 2 | High | Self-Governance | Technical Expert Panel | 2022-06-30 | Elec | Energy Suppliers Distribution Network Operators Metering Equipment Managers Data Collectors Data Aggregators | Awaiting Implementation | Implementation | 2022-06-30
R0009 | Introduction of SDEP and EES User Maintenance API | Link | Jonathan Holland | Code Manager | Jonathan Holland | 2021-09-08 | 2 | Low | Self-Governance | Technical Expert Panel | TBC | Elec and Gas | Energy Suppliers Distribution Network Operators Metering Equipment Managers EES Users | Impact Assessment | Party Impact Assessment completed | 2022-06-15
R0010 | New Meter Types for Auxiliary Proportional Controllers (APCs) | Link | David Morton | EDF Energy | Jonathan Holland | 2021-09-08 | 1 | Low | Self-Governance | Technical Expert Panel | TBC | Elec | Energy Suppliers Distribution Network Operators Metering Equipment Managers DCC Data Collectors EES Users Prepayment Meter Infrastructure Provider Meter Point Administration Service | Preliminary Assessment | Preliminary Change Report published | 2022-06-27
R0011 | Reporting of additional EMR Backing Data to Suppliers | Link | Gemma Dixon | Code Manager | Gemma Dixon | 2021-09-08 | 2 | Low | Self-Governance | Technical Expert Panel | 2022-11-04 | Elec | Energy Suppliers | Awaiting Implementation | Implementation approved for 4/11/22 however R0039 has been raised to review the implementation date. | 2022-11-04
R0014 | Cable Colour Identification | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2021-11-01 | 2 | Low | Self-Governance | Metering Expert Panel | TBC | Elec and Gas | Distribution Network Operators Metering Equipment Managers | Awaiting Implementation | Implementation | 2022-06-30
R0015 | Remote communication obligations for Advanced Meters | Link | David Brown | Association of Meter Operators | Ann Perry | 2021-11-17 | 1 | High | Self-Governance | Metering Expert Panel | TBC | Elec and Gas | Energy Suppliers Metering Equipment Managers Data Collectors | Preliminary Assessment | MEP review of PCR | 2022-06-08
R0016 | Resolution of Bilateral Erroneous Transfers | Link | Ben Atkinson | British Gas | Gemma Dixon | 2021-11-17 | 1 | Low | Self-Governance | Change Panel | TBC | Elec and Gas | Energy Suppliers | Solution Development | Aligned to SDEP review activity | 2022-06-21
R0017 | Invalid Requests for Site Technical Details | Link | Elaine Carr | Scottish Power Energy Networks | Harriet Truss | 2021-11-22 | 1 | Low | Self-Governance | Metering Expert Panel | TBC | Elec | Energy Suppliers Distribution Network Operators Metering Equipment Managers | Solution Development | Engagement with BSC issue group and analysis | 2022-07-08
R0018 | Complex Sites process improvements | Link | Ann Perry | Code Manager | Jonathan Holland | 2021-11-25 | 1 | Low | Self-Governance | Metering Expert Panel | 2022-11-04 | Elec | Energy Suppliers Distribution Network Operators Metering Equipment Managers | Awaiting Implementation | Implementation | 2022-11-04
R0019 | Consequential REC Changes for BSC CP1532 | Link | Ann Perry | Code Manager | Ann Perry | 2021-11-26 | 1 | Low | Self-Governance | Metering Expert Panel | 2022-06-30 | Elec | Energy Suppliers Metering Equipment Managers | Awaiting Implementation | Implementation | 2022-06-30
R0021 | Allowing REC accredited MEMs to de-energise and re-energise supply points independent of the Supplier | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2021-12-09 | 1 | Medium | Authority Determined | Metering Expert Panel | TBC | Elec | Energy Suppliers Distribution Network Operators Metering Equipment Managers | Preliminary Assessment | MEP review of interim PCR and plan for re-baselining the CPP | 2022-06-08
R0022 | Amendment to REC Data Access Matrix | Link | Harriet Truss | Code Manager | Harriet Truss | 2021-12-15 | 2 | Medium | Self-Governance | Change Panel | TBC | Elec and Gas | EES Users | Preliminary Assessment | PCR published | 2022-07-22
R0023 | Prepayment Unallocated Transactions | Link | Jonathan Holland | Code Manager | Jonathan Holland | 2021-12-15 | 1 | Low | Self-Governance | Change Panel | 2022-06-30 | Elec and Gas | Energy Suppliers Prepayment Meter Infrastructure Provider | Final Assessment | Change Panel decision on FCR | 2022-06-07
R0024 | EAC information in the EES API | Link | Andrew Long | Switchcraft | Jonathan Holland | 2021-12-10 | 2 | Low | Self-Governance | Technical Expert Panel | TBC | Elec | Energy Suppliers EES Users | Solution Development | Solution development activity completed and legal text changes defined | 2022-05-31
R0025 | Service Provider Performance Charges (ERDS, GRDS, DCC) | Link | Eliana Campbell | Code Manager | Gemma Dixon | 2022-01-04 | 1 | High | Self-Governance | Performance Assurance Board | 2022-06-30 | n/a | Distribution Network Operators Gas Transporters DCC | Initial Assessment | RECCo consultation response consideration | 2022-06-06
R0026 | Whole current (WC)/Current Transformer (CT) certificates | Link | Courtney Campbellwood | Code Manager | Courtney Campbellwood | 2022-01-06 | 1 | Low | Self-Governance | Metering Expert Panel | TBC | Elec | Metering Equipment Managers | Solution Development | Solution development activity re-starts | 2022-09-30
R0030 | Erroneous Transfer Cancellations | Link | Lorna Mallon | Scottish Power Energy Retail | Gemma Dixon | 2022-01-14 | 1 | Low | Self-Governance | Change Panel | TBC | Elec and Gas | Energy Suppliers | Impact Assessment | Party Impact Assessment completed | 2022-05-30
R0031 | DNO LV CT Commissioning Trigger Points & Timescales | Link | Colette Baldwin | Code Manager | Colette Baldwin | 2022-02-01 | 2 | Low | TBC | Metering Expert Panel | 2022-11-04 | Elec | Energy Suppliers Distribution Network Operators Metering Equipment Managers | Final Assessment | MEP deccision on FCR | 2022-06-08
R0032 | New Registration data items and processes to support the transition to Market-wide Half-Hourly Settlement (MHHS) | Link | Colette Baldwin | Code Manager | Gemma Dixon | 2022-02-03 | 2 | High | Self-Governance | Change Panel | TBC | Elec | Energy Suppliers Distribution Network Operators Metering Equipment Managers EES Users | Impact Assessment | SP and REC Party Impact Assessent completed | 2022-06-14
R0033 | Micro-business Smart Meter Installation Reports | Link | Kelly Austin | EDF | Ann Perry | 2022-01-31 | 1 | Low | Self-Governance | Change Panel | TBC | Elec and Gas | Energy Suppliers | Impact Assessment | Service Provider Impact Assessment completed | 2022-06-14
R0035 | Market Stabilisation Charge - Administration | Link | Jon Dixon | RECCo | Ann Perry | 2022-02-21 | 1 | High | Authority Determined | Change Panel | 2022-06-30 | Elec and Gas | Energy Suppliers | Consultation | Consultation completion | 2022-06-01
R0036 | Housekeeping amendments | Link | Ann Perry | Code Manager | Ann Perry | 2022-03-04 | 1 | High | TBC | Change Panel | Change Panel | n/a | Energy Suppliers Distribution Network Operators Gas Transporters Metering Equipment Managers DCC Shippers Data Collectors Data Aggregators Green Deal Providers Green Deal Finance Parties Meter Asset Providers AMR Service Providers EES Users GES Users GDCC Users | Solution Development | Legal text review completed (Gowlings) | 2022-06-14
R0037 | Prepayment Credit Balance & Debt Transfer Processes | Link | Andy Knowles | Utilita | Harriet Truss | 2022-03-10 | 1 | Low | Authority Determined | Change Panel | TBC | Elec and Gas | Energy Suppliers | Solution Development | Initial Analysis to be completed and DAP performance assurance activity to be completed | 2022-06-30
R0038 | Performance Assurance Report Catalogue Changes as a consequence of REC V3.0 | Link | Lewis Williams | Code Manager | Gemma Dixon | 2022-03-23 | 2 | TBC | Self-Governance | Change Panel | TBC | n/a | Energy Suppliers Metering Equipment Managers | Preliminary Assessment | PCR published | 2022-05-31
R0039 | Revised Implementation Date for R0011 | Link | Patrick Bibby | LCCC | Gemma Dixon | 2022-03-25 | 2 |  | Self-Governance | Change Panel | 2023-06-30 | Elec | Energy Suppliers | Awaiting Implementation | Awaiting Implementation | 2022-06-01
R0040 | CSS Switch Synchronisation to ERDA at SecuredActive | Link | Daniel Tadecicco | St Clements Services | Courtney Campbellwood | 2022-03-16 | TBC | TBC | TBC | TBC | TBC | Elec | TBC | Initial Assessment | Development of CPP and IAR | 2022-06-10
R0041 | REC V3.0 | Link | Alasdair MacMillan | Ofgem | Ann Perry | 2022-04-07 | 1 | High | Authority Determined | Change Panel | 2022-07-18 | Elec and Gas | Energy Suppliers Distribution Network Operators Gas Transporters Metering Equipment Managers DCC EES Users GES Users | Final Assessment | Change Panel decision on FCR | 2022-06-07
R0042 | Performance Assurance Board Terms of Reference | Link | Eliana Campbell | Code Manager | TBC | 2022-04-14 | 2 | High | Self-Governance | Change Panel | 2022-07-18 | n/a | Central Switching Service Provider Electricity Enquiry Service Provider Gas Enquiry Service Provider Electricity Ratal Data Service Gas Retail Data Service | Preliminary Assessment | Consultation completion | 2022-06-08
R0043 | Commissioning of Works using shared Meter Operator services by the Crowded Meter Room Co-ordinator (CMRC) | Link | David Jones | Alt Han Company | TBC | 2022-04-21 | TBC | TBC | TBC | TBC | TBC | TBC | TBC | Initial Assessment | Development of CPP and IAR | 2022-06-10
R0044 | MHHS Programme Changes required to Central Switching Service | Link | Jason Brogden | MHHS Programme | Harriet Truss | 2022-04-29 | 2 | Critical | Authority Determined | TBC | TBC | Elec | Distribution Network Operators DCC | Solution Development | Analysis and requirements gathering | 2022-06-21
R0045 | Changes to SDEP Messages for REC V3.0 | Link | Jon Hawkins | RECCo | TBC | 2022-05-06 | 2 | High | Self-Governance | Technical Expert Panel | 2022-07-18 | Elec and Gas | Energy Suppliers Distribution Network Operators | Preliminary Assessment | Consultation completion | 2022-06-14
R0046 | Governance of Data under the REC | Link | Brian O'Shea | RECCo | Jonathan Holland | 2022-05-20 | 1 | High | Self-Governance | Change Panel | 2022-07-18 | n/a | DCC | Initial Assessment | Change Panel review of IAR and CPP | 2022-06-07
R0047 | Metering Code of Practice Consolidation Review | Link |  |  | Ann Perry | 2022-05-20 | 1 | High | Self-Governance | Change Panel | TBC | Elec and Gas | Energy Suppliers Distribution Network Operators Metering Equipment Managers | Initial Assessment | Change Panel review of IAR and CPP | 2022-06-07
R0048 | DCC Service Organisation Control 2 (SOC2) Assessments | Link | Cordelia Grey | DCC | TBC | 2022-05-20 | TBC | TBC | TBC | TBC | TBC | n/a | TBC | Initial Assessment | Code Manager's Initial Assessment | 2022-06-14
R0049 | Intellectual Property Rights and Services Data Main Body changes | Link | Cordelia Grey | DCC | TBC | 2022-05-20 | TBC | TBC | TBC | TBC | TBC | n/a | TBC | Initial Assessment | Code Manager's Initial Assessment | 2022-06-07

## CP priority heatmap
Urgency | 3
2
1
0
|  | 0 | 1 | 2 | 3
Significance
| R06 | R0006 - Missing Meter Technical Details
| R09 | R0009 - Introduction of SDEP and EES User Maintenance API
| R10 | R0010 - New Meter Types for Auxiliary Proportional Controllers (APCs)
| R15 | R0015 - Remote communication obligations for Advanced Meters
| R16 | R0016 - Resolution of Bilateral Erroneous Transfers
| R17 | R0017 - Invalid Requests for Site Technical Details
| R21 | R0021 - Allowing REC accredited MEMs to de-energise and re-energise supply points independent of the Supplier
| R22 | R0022 - Amendment to REC Data Access Matrix
| R23 | R0023 - Prepayment Unallocated Transactions
| R24 | R0024 - EAC information in the EES API
| R25 | R0025 - Service Provider Performance Charges (ERDS, GRDS, DCC)
| R26 | R0026 - Whole current (WC)/Current Transformer (CT) certificates
| R30 | R0030 - Erroneous Transfer Cancellations
| R31 | R0031 - DNO LV CT Commissioning Trigger Points & Timescales
| R32 | R0032 - New Registration data items and processes to support the transition to Market-wide Half-Hourly Settlement (MHHS)
| R33 | R0033 - Micro-business Smart Meter Installation Reports
| R35 | R0035 - Market Stabilisation Charge - Administration
| R36 | R0036 - Housekeeping amendments
| R37 | R0037 - Housekeeping amendments - Prepayment Credit Balance & Debt Transfer Processes
| R38 | R0038 - Performance Assurance Report Catalogue Changes as a consequence of REC V3.0
| R40 | R0040 - CSS Switch Synchronisation to ERDA at SecuredActive |  |  |  | Awaiting Initial Assessment
| R41 | R0041 - REC V3.0
| R42 | R0042 - Performance Assurance Board Terms of Reference
| R43 | R0043 - Commissioning of Works using shared Meter Operator services by the Crowded Meter Room Co-ordinator (CMRC) |  |  |  | Awaiting Initial Assessment
| R44 | R0044 - MHHS Programme Changes required to Central Switching Service
| R45 | R0045 - Changes to SDEP Messages for REC V3.0
| R46 | R0046 - Governance of Data under the REC
| R47 | R0047 - Metering Code of Practice Consolidation Review
| R48 | R0048 - DCC Service Organisation Control 2 (SOC2) Assessments |  |  |  | Awaiting Initial Assessment
| R49 | R0049 - Intellectual Property Rights and Services Data Main Body changes |  |  |  | Awaiting Initial Assessment
R06
R10
R09
R16
R15
R23
R25
R26
R17
R22
R21
R24
R30
R32
R31
R33
R37
R35
R36
R38
R41
R42
R45
R44
R46
R47

## Withdrawn CPs
Change Proposal Reference | Date Submitted | Date Proposer withdrew support | Fully Withdrawn from Process | Change Proposal Title | Proposer Name | Proposer Company
R0005 | 2021-09-06 | 2021-10-04 | 2021-10-18 | Access to EES (Energy Enquiry Service) and GDCC API for CSS Interface Providers | Karen Lee | ESG Global Ltd
R0007 | 2021-09-08 | 2021-12-10 | 2021-12-24 | Changes to message ownership in SDEP | Rachel Norberg | Utilita
R0013 | 2021-10-08 | 2021-01-14 | 2021-01-31 | Electricity Enquiry Service API Service Status | Andrew Long | Switchcraft
R0004 | 2021-09-02 | 2022-01-21 | 2022-02-07 | Electricity Enquiry Service (EES) Master Administration User (MAU) Access | Diane Lyon | Scottish Power Energy Retail
R0029 | 2022-01-11 | 2022-02-18 | 2022-03-04 | Mandating Timely Meter Product Data (MPD) Updates | Rosalind Timperley | Code Manager
R0027 | 2022-01-06 | 2022-04-14 | 2022-04-14 | Minimum identification requirements in the Meter Operation Code of Practice | Courtney Campbellwood | Code Manager

## Rejected CPs
Date Raised | Date Rejected | Change Proposer | Change Proposer's company | Change Proposal Title | Change Proposal Description | Rejection Reason | Next steps / Actions taken
2021-09-08 | 2021-09-08 | Richard Hill | British Gas | Cross Polarity Reporting Guidance | Guidance has previously been discussed and developed under MOCOPA on cross polarity reporting, to ensure Meter Operators (on behalf of Suppliers) inform the relevant party of a cross polarity incident when they are NOT the incumbent Supplier. At present the reporting is ad-hoc on a bi-lateral basis between Meter Operators, Suppliers or DNOs A one page flow diagram had previously been discussed and approved by affected parties at MOCOPA and DCUSA and accepted as useful guidance. | The submission was proposing the introduction of guidance. The REC was drafted under the principle that guidance would not be included in Schedules alongside obligations. Therefore, the standard change process is not the appropriate mechanism for the introduction of guidance. At present the reporting is ad-hoc on a bi-lateral basis between Meter Operators, Suppliers or DNOs A one page flow diagram had previously been discussed and approved by affected parties at MOCOPA and DCUSA and accepted as useful guidance. | In agreement with the Change Proposer, the Change Proposal has been rejected and a Category 3 Change Proposal has been raised. A paper will be presented to the Metering Expert Panel, to review the previously prepared guidance and agree appropriate next steps for the introduction of the guidance.
2021-10-06 | 2021-10-07 | David Harper | Gastech Engineering Limited | Addition of a new meter model to Market Domain Data (MDD) | A new meter model has been specified for a non-standard site. The meter model and attributes need to be added to the MDD. A standard Change Proposal was raised to update the MDD Meter Product Table. | The standard Change Proposal is not the appropriate mechanism for progressing changes to Market Domain Data. The Meter Product data is part of the REC Data Specification and a separate, proportionate, process has been defined (similar to that utilised under SPAA). | In agreement with the Proposer, the Change Proposal has been rejected and the Proposer has been provided with the Meter Product Change Request Form. The Proposer will submit the completed form, to progress the change to MDD.
2021-11-10 | 2021-11-11 | Douglas Alexander | Elexon | Amendment to RECMEP Terms of Reference to allow Elexon Representative voting rights | The Elexon attendee at the REC Metering Expert Group has no voting rights. Although Elexon have been proactive in providing feedback based on our expertise of SVA Metering, we are just observers and committee would lose out on the technical knowledge and practical experience if we reverted to merely observing. With no vote it is effectively providing free consultancy and a lack of recognition of Elexon reps expertise in SVA Metering. | This submission proposes a potential change to the REC Metering Expert Panel Terms of Reference - this is a Category 3 document under responsibility of the REC Change Panel. The standard Change Proposal process is not the appropriate mechanism for the progression of this change. | This issue has been discussed with the proposer, RECCo and the Code Manager. No changes to the Metering Expert Panel ToR are proposed at this time.
2021-12-03 | 2021-12-06 | Liam Gatens | South Tyneside Homes | Relying on using Electrical Suppliers for Emergency and Planned Double pole isolator works | Allowing the previous accredited MOCOPA approved companies to be able to install new and repair existing Double pole isolators in domestic and communal properties, without the inclusion of the associated electrical supplier. This would also allow a emergency response service for high priority works by using procured companies. | This submission is covered by DCP 394 and the related REC change which the Code Manager is due to raise. Proposed agreed for this submission to be rejected and a REC Change raised that covers all elements required. | R0021 has been raised to progress the REC changes
2022-05-03 | 2022-05-06 | Greg Wedge | E.ON | SMICoP Microbusiness Quarterly Performance Reporting | To introduce the production of the SMICoP MB quarterly performance reports like what is currently done for Residential. | This is a duplication of a Change Proposal that is already in flight, R0033 | No further action - R0033 will progress

## Implemented CPs
Change Proposal Reference | Change Proposal Title | Link to CP Page | Proposer Name | Proposer Company | Lead Analyst | Date Submitted | Change Category | Priority Status | Change Path | Responsible Committee | Fuel | Impacted Parties | Implementation Date | Process Stage
R0001 | Amendment to DCC Service Flag (DI51130) Data Item | Link | Jonathan Hawkins | Code Manager | Jonathan Hawkins | 2021-09-01 | 2 |  | Self-Governance | Change Panel | Elec and gas | n/a | 2021-11-04 | Implemented
R0002 | Review of Data Specification Category in REC Baseline Statement | Link | Jonathan Hawkins | Code Manager | Jonathan Hawkins | 2021-09-01 | 2 |  | Self-Governance | Change Panel | n/a | n/a | 2021-11-04 | Implemented
R0003 | Market-wide Half-Hourly Settlement Implementation | Link | Abid Sheikh | Ofgem | Jonathan Hawkins | 2021-09-01 | 1 |  | Authority-Approval | Change Panel | Elec | n/a | 2021-11-04 | Implemented
R0012 | Housekeeping amendments to REC V2 | Link | Jonathan Hawkins | Code Manager | Jonathan Hawkins | 2021-10-04 | 1 |  | Self-Governance | Change Panel | n/a | n/a | 2022-01-31 | Implemented
R0020 | ETTOS Report Dissemination | Link | Aiyesha Andrade | RECCo | Ann Perry | 2021-11-29 | 1 |  | Self-Governance | Change Panel | n/a | n/a | 2022-01-31 | Implemented
R0028 | Review of Category 3 documents in the REC Baseline Statement | Link | Anton Moden | Code Manager | Ann Perry | 2022-01-07 | 2 | Medium | Self-Governance | Change Panel | n/a | n/a | 2022-04-14 | Implemented
R0034 | Market Stabilisation Charge | Link | Henry Kemp | Ofgem | Ann Perry | 2022-02-17 | 1 | High | Authority Determined | Change Panel | Elec and gas | n/a | 2022-04-14 | Implemented