## Sheet1
Reference | Action | Owner | Progress | Status
MSAG03-01; 30/09/22 | RECCo to confirm with the MHHSP that the D0300 will not be sent to the NHHDC / SDS following agreement of the read and instead the Supplier will enact a consumption correction. | JH | 15/03/23 - ongoing and being addressed under the Registration tranche of the MHHS Code Drafting | Open
MSAG05-05; 18/01/23 | RECCo to confirm the approach and timeline for engaging with industry on the changes to the EES API technical specification. | JM | 15/03/23 - ongoing | Open
MSAG06-03; 18/01/23: | Members to provide comments on redlined CFSB drafting. | SJ | 15/03/23 - ongoing and that the latest drafting of Schedule 30 will be shared with the post meeting papers | Open
RECMSAG_23_0315_01 | Committee Secretary to upload new actions log to REC MSAG Committee page on the REC Portal. | HT |  | Complete
RECMSAG_23_0315_02 | HT to look into options for easily identifying MHHS related Change Proposals on the REC Portal. | HT |  | Open
RECMSAG_23_0315_03 | JB to gather input from DNO community as to whether the Expected Connection Type would be required in the New/Additional MPAN request in SDES in order for the DNOs to process the request. | JB |  | Open
RECMSAG_23_0315_04 | RECCo to bring back analysis on ETs and the impact on the current processes for anything not NHH to a future meeting. | SJ |  | Open
RECMSAG_23_0315_05 | RECCo to update CSS User Roles proposal document with the MHHS milestone for the start of migration and clarity on the decision relating to not including Data Services as CSS Users | SJ |  | Open
RECMSAG_23_0315_06 | RECCo to confirm the rationale from MHHS design discussions for limiting access to the identity of the agent that set the Customer Direct Contract Flag - EES Data Access. | SJ |  | Open
RECMSAG_23_0315_07 | RECCo to confirm with MHHS Programme if design issue required to extend access to include the identity of the agent that set the Customer Direct Contract Flag. | SJ |  | Open
RECMSAG_23_0315_08 | RECCO to bring updated EES DAM being brought back to a future meeting. | SJ |  | Open
RECMSAG_23_0315_09 | RECCo to confirm whether the old Supplier will know about an MPAN migrating or if they have to check in EES. | SJ | 22/03/23: The outgoing supplier will receive a D0010 with the Meter Reading Reason Code populated with '29' - Forward Migration COS following agent appointment by the new supplier. This information will likely be received too late to help populate the D0311. This only applies to MPANs currently settled NHH. | Open
RECMSAG_23_0315_10 | RECCo to consider whether the existing rule that the time of the last reading should be set to 00:00:00 should be removed and make sure that it's clear in the proposal how it should be managed during transition. | JH |  | Open
RECMSAG_23_0315_11 | The Code Manager to send out the invite for the next meeting for the morning of Wednesday 19 April 2023. | HT |  | Complete