## Cover sheet and stats
This document is classified as WHITE. Information is for public, unrestricted dissemination and publication.
REFERENCE | RECPAB_24_0625_12
STATUS | FOR INFORMATION
CHANGE MANAGEMENT OPERATIONAL UPDATE
AUTHORED BY ELISE HANDY - CHANGE ANALYST - REC CODE MANAGER
REVIEWED BY LORNA MALLON - PRINCIPAL REGULATORY CONSULTANT - REC CODE MANAGER
FOR INFORMATION | This paper provides the regular update on REC changes to the PAB
CHANGE PROPOSALS |  | Live Changes (In Play) | Nov'23 | 2024-06-01 |  | Awaiting Implementation | Remaining Changes/Issues in Progress
|  |  | 78 | 69 |  | 14 | 55
RELEVANT TO PAB |  |  | 39 | 53
Type |  |  |  |  | Number |  | Total
PAB is or is likely to be the Responsible Committee |  |  |  |  | 4 |  | 53
Changes that affect data access or data quality |  |  |  |  | 11
Changes that directly affect Performance Assurance |  |  |  |  | 17
Changes relevant to SDEP |  |  |  |  | 7
Changes to metering accreditation |  |  |  |  | 1
Performance improvements |  |  |  |  | 10
Related to a derogation |  |  |  |  | 1
For information |  |  |  |  | 2
Note on F17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This includes implemented Change Proposals.
Note on G20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This breakdown doesn't entirely match the detailed table: PAB is or likely to be the Responsible Committee 6 Added at PAB request 1 Changes that directly affect Performance Assurance 17 Changes that affect data access or data quality 11 Performance Improvements 10 Changes relevant to SDEP 7 Changes to metering accreditation 1 Related to a derogation 1 For information 2

## Table
Ref. | Title | Relevance to PAB | Status (June 24) | Background | Update | New status since last update to PAB
R0092 | DCC Service Level Agreements for the Switching Incentive Regime | PAB is or likely to be the Responsible Committee | Awaiting Authority decision | Requirements for the Central Switching Service (CSS) were identified during the Design, Build and Test Phase of the Ofgem-led Switching Programme as a basis for the procurement of Switching systems. These requirements were later baselined in the REC Service Definitions as Service Level Agreements (SLAs). | Awaiting timetable for expected decisions following the General Election. | Yes
R0092A | DCC Service Level Agreements for the Switching Incentive Regime (Alternative) | PAB is or likely to be the Responsible Committee | Awaiting Authority decision | Requirements for the Central Switching Service (CSS) were identified during the Design, Build and Test Phase of the Ofgem-led Switching Programme as a basis for the procurement of Switching systems. These requirements were later baselined in the REC Service Definitions as Service Level Agreements (SLAs). | Awaiting timetable for expected decisions following the General Election. | Yes
R0148 | Introduction of classification-based access model into the REC in support of Open Data | Added at PAB request | Solution Development | Currently Enquiry Services Data is only available to users whose roles and purposes for access are detailed within the Data Access Matrix (DAM). RECCo has undertaken a project to look at REC controlled data sources and created a Metadata Catalogue based on a Data Classification Model. This details the data items along with descriptions, identification of the associated data, roles, responsibilities, and classification. The output of this work will be utilised to improve access to Enquiry Services Data by making certain data items (defined as Always Open) easily available to everyone and simplifying the approval process for data items which can be made available if certain conditions have been met. | Initial Assessment Report and Change Proposal Plan approved by the Change Panel. This Change is currently in the solution development phase and intends to begin Service Provider Impact Assessments with Xoserve and C&C in July 2024. | Yes
I0173 | Improvements to the Theft Detection Incentive Scheme | PAB is or likely to be the Responsible Committee |  | The TDIS exists to incentivise Suppliers to resolve Energy Theft. The current TDIS was inherited from legacy codes and has proved challenging for impacted Parties. The following challenges have been identified. - It has a complex methodology - It results in unpredictable outcomes - The debits/credits payable are dependent on the relative performance of each Supplier - The determination of credits and debits is not directly linked to theft targets - The value per theft varies dependent on overall market performance - Scheme participants can "buy-out" of the scheme - It only rewards confirmed thefts - It assumes theft is evenly distributed - The scheme pot of funds is never fully distributed - Results are skewed for smaller parties. | New Issue raised. Solution to be developed through the Theft Issues Group. | Yes
I0174 | Mandating ETTOS Follow up | PAB is or likely to be the Responsible Committee |  | It has been identified that not all ETTOS leads are flowing through into the theft outcome files and is uncertain to what degree these leads are being investigated. | New Issue raised. Solution to be developed through the Theft Issues Group. | Yes
I0175 | Introducing a Reasonable Endeavours Scheme within the REC | PAB is or likely to be the Responsible Committee |  | There is a current disincentive for a Supplier to pursue a particularly complex energy theft investigation where there is both little prospect of costs being recovered directly from the Consumer and those costs materially exceeding the Theft Detection Value under the TDIS. This Issue seeks to consider whether a Reasonable Endeavours scheme would work in the REC. | New Issue raised. Solution to be developed through the Theft Issues Group. | Yes
I0176 | Creation of an Energy Theft Detection and Resolution Body | PAB is or likely to be the Responsible Committee |  | There is currently a lack of consistent standards of investigation and good quality data across GB. This Issue seeks to consider whether a Energy Theft Detection and Resolution Body would work in the REC. | New Issue raised. Solution to be developed through the Theft Issues Group. | Yes
R0072 | Introduction of a new Meter Asset Condition Code | Changes that directly affect Performance Assurance | Initial Assessment | This change seeks to introduce a new Asset Condition Code where further investigation is required by a DNO where there is suspected asbestos in the metal encased cut-out. | In discussions with Ofgem on the Code Manager's recommendation to withdraw this Change. If it were to progress, DCUSA would need to be the lead code and supplier would need to raise a request if required. | Yes
R0080 | Improvements to ‘Failed to Deliver’ CSS Messages | Changes that directly affect Performance Assurance | Final Assessment | Since Go-Live a large number of messages have been unsuccessfully delivered due to failures of CSS Users gateways, resulting in CSS exhausting the 12-hour retry period. This Change Proposal has been raised to explore and address this issue. | The Consultation window has closed and responses were broadly positive to progress the Change. The Code Manager is considering moving the decision date forwards so that the Service Provider would have more time for mobilisation and implementation. | Yes
R0100 | Update to Error Handling Documents | Changes that directly affect Performance Assurance | Solution Development | There are duplications between the CSS Message Business Data Validation Rules document (a Category 2 document) and the CSS Error Processing guide (a Category 3 guidance document), which is resulting in confusion and complications within the error handling process. This Change Proposal has been raised to update the Business Data Validation Rules document, to capture the appropriate information that is removed from the CSS Error Processing guide and to ensure alignment with newly created knowledge articles. | To be reviewed by St Clements prior to plan for progression of the change. | No
R0108 | Enabling Electricity Enquiry Service searches using a Unique Property Reference Number | Changes that directly affect Performance Assurance | Awaiting implementation | This Change Proposal seeks to add functionality to the EES, to return meter point details for one or multiple meter points (MPANs) from a search of UPRN. | Awaiting Implementation on 23/08/2024. | No
R0115 | Frequency and content of CSS reports on switching via the DCC portal | Changes that directly affect Performance Assurance | Awaiting implementation | Changes to the frequency a specific CSS report which is used for assurance by the Code Manager and by Ofgem. | The Authority has approved R0115 for implementation 08/11/2024. | No
R0119 | Annulment Definition | Changes that directly affect Performance Assurance | Consultation | The performance assurance team have identified Parties using annulments when they should use other processes. The lack of a clear definition of what an annulment is could be a contributing factor to this. | The Preliminary Change Report and Consultation was published 31/05/2024. The Consultation will close 21/06/2024. | Yes
R0137 | Introducing Third Party Intermediary (energy broker) assurance and accreditation | Changes that directly affect Performance Assurance | Initial Assessment | Introducing Third Party Intermediary (energy broker) assurance and accreditation. | The Code Manager is waiting on further updates from RECCo prior to progressing this Change Proposal. | No
R0142 | Amendment to Multiplication Factor Enumerations to support hydrogen trials | Changes that directly affect Performance Assurance | Awaiting implementation | If the enumerations of the Multiplication Factor are not amended then any consumer in the Hydrogen Trials would be disadvantaged in that they would be charged more for the energy that they are consuming. | Awaiting Implementation on 28/06/2024. | No
R0144 | Allowing different Metering Equipment Managers (MEMs) to be appointed to Import and Export Metering Points | Changes that directly affect Performance Assurance | Solution Development | Cross-code Change relating to BSC P459, relating to management of Import and Export MEMs. | The withdrawal of the Change Proposal Plan was approved at Change Panel on 04/06/2024. A new plan will be submitted once a timetable is available from the BSC. | Yes
R0153 | Catering for Registration Events | Changes that directly affect Performance Assurance | Withdrawn | In some instances, the incumbent Supplier is withdrawing prior to the ‘Supply Effective from Date’ which causes the accepted Switch to fail at Gate Closure (17:00hrs). | This Change Proposal has been withdrawn and will be incorporated into R0178 - Improvements to CSS Business Logic. Adoption window for R0153 to close 21/06/2024. | Yes
R0155 | Change of Tenancy: Evidentiary Standards and Timescales | Changes that directly affect Performance Assurance | Solution Development | Non-domestic energy contracts commit the consumer to a fixed duration and unlike domestic consumers, they are less able to change supplier mid-term. However, there are instances where a non-domestic premises undergoes a Change of Tenancy (CoT), and the incoming tenant/owner who inherits the supply point and its relationship to the predecessors chosen energy supplier may wish to make alternative arrangements that best matches their needs. In these circumstances, the incoming tenant may choose to enter a new contract with the same supplier or take up a wholly new contract with a new supplier. | Solution Development Working Groups now complete and legal text being developed. Solution development workgroups will be formally disbanded at the end of June 2024. | Yes
R0163 | Theft Detection Incentive Scheme (TDIS) Reporting Periods | Changes that directly affect Performance Assurance | Preliminary Assessment | This Change Proposal seeks to alter the Theft Detection Incentive Scheme (TDIS) reporting cycle from annual to a quarterly cycle. This alteration is limited the administration of the scheme and will have no impact on how Suppliers submit their reports. | Following consultation, this Change Proposal has been re-baselined. It has been deferred to the Theft Issues Group to refine and develop the benefits case. | No
R0177 | Change Smart Meter Installation Consumer Survey Specification survey questions to a REC Category 2 document | Changes that directly affect Performance Assurance | Initial Assessment | Adding the Smart Meter Installation Consumer Survey Specification questions to the REC list of documents will allow any amendments to follow the REC change process and allow anyone to propose such amendments. | Code Manager Initial Assessment in progress. | Yes
R0178 | Improvements to CSS Business Process Logic | Changes that directly affect Performance Assurance | New | This change proposal is aimed towards rectifying a collection of issues that were identified with the CSS Business Process Logic. These have been identified as follows: 1. Deactivation of an active reg. whilst in-flight switch in progress 2. Deactivation of a prior cancelled registration 3. OFAF switch containing multiple MPxN - To replace R0153. | New | Yes
I0172 | New Build - Commissioning Process Review | Changes that directly affect Performance Assurance |  | End-to-end review of the new connections process. This will be a cross-code change. | New Issue raised. Code Manager to conduct initial review. | Yes
I0179 | Proposal for Limiting Queries in EES API Calls (Single API Call With Multiple Queries) | Changes that directly affect Performance Assurance |  | RECCo is proposing the establishment of a limit on the number of queries permitted within a single API call. There could be a potential performance degradation and system instability that can occur when a large number of queries are made in a single API call to Electricity Enquiry Services (EES) API. | New | Yes
I0180 | Clarity on use of on hold for switching issues, including the obligations of CSS Users | Changes that directly affect Performance Assurance |  | Clarity on use of on hold for switching issues, including the obligations of CSS Users | New | Yes
C3-0081 | Data Access Request Tenants Save Money | Changes that affect data access or data quality | Implemented | N/A | Implemented on 20/05/2024. | Yes
R0006 | Missing Meter Technical Details | Changes that affect data access or data quality | Awaiting implementation | When a Switch occurs, with a concurrent change of Metering Equipment Manager (MEM), and the Meter Technical Details (MTD) are not received by the Gaining Supplier’s MEM, they are unable to provide them to the Gaining Supplier. Lack of MTDs can impact Consumers, Suppliers, and other industry Parties. | This Change Proposal was addressed through R0121 and approved for implementation 23/08/2024. Proposer discussion on withdrawal. | No
R0056 | EES/GES Additional Service Request for Housing Associations to be added to the Data Access Matrix | Changes that affect data access or data quality | Solution Development | This change has been raised to enable Housing Associations to have access to data in EES and GES, to understand and confirm which of their properties contain live supply points, the meter locations, asset data and last inspection checks. This will also enable Housing Associations to update the industry where gas safety information is not accurate against their site data. | This Change Proposal is progressing through the R0118. The data access request approval is to be requested at the PAB on 25/06/2024. | Yes
R0069 | Amendments to Sample Access Agreement | Changes that affect data access or data quality | Impact Assessment (Party) | Non-Party REC Service Users have entered into an Access Agreement with RECCo under the Code’s Qualification and Maintenance Schedule to obtain access to the CSS and become CSS Users. These Access Agreements are based on the Sample Access Agreement appended to Schedule 9 to the Code, which DCC believes should be revised to address the issues which DCC have identified. | Party Impact Assessment open and will close on 17/06/2024. | Yes
R0087 | MAP - GES Portfolio Dashboard | Changes that affect data access or data quality | Solution Development | This Change Proposal is to look at the feasibility of providing a portfolio view for the MAP. | Confirmation from MAP on whether or not they want to progress the solution via a brand new API or existing reports. | No
R0116 | TPI access to the Meter Asset Manager data via the GES | Changes that affect data access or data quality | Withdrawn | TPIs do not currently have access to the MAM via GES. Provision of the MAM will allow TPIs to identify and contact the relevant MAM to arrange direct MAM agreements for clients on their behalf. | This is being progressed through the R0118 route and has been withdrawn. Adoption window closed. | Yes
R0130 | Updates to the Data Access Matrix | Changes that affect data access or data quality | Withdrawn | There are organisations that are named in Schedule 12 - Data Access that are not recorded in the gas and/or electricity Data Access Matrix (DAM). This means it is not possible for the Code Manager to provision them access. All organisations listed in Schedule 12 to access data in the REC should have an entry in the Data Access Matrices. This Change Proposal has been raised to review the Schedule and DAMs and take forward the necessary changes. | The UKRPA has stopped its fraud reporting service in Great Britain and this Change Proposal has been withdrawn. Adoption window closed. | Yes
R0131 | Creation of new Enquiry Service User Category | Changes that affect data access or data quality | Withdrawn | This change has been raised to introduce a new User Category to the Data Access Schedule, for organisations offering services that provide insight on CO2 emissions and energy consumption, to support reporting for regulatory and certifications purposes. | This Change Proposal has been withdrawn at the request of the Proposer. Adoption window to close 14/06/2024. | Yes
R0146 | Data Specification Update for Refresh Functionality | Changes that affect data access or data quality | Consultation | This change has been raised to update the Data Specification to align with the technical changes that will be implemented as part of Change Proposal R0067. | Consultation window closed 10/06/2024. Final Change Report due to be published 16/06/2024 for decision 26/06/2024. | Yes
R0158 | Amendment to the ‘Supplier Registration Report (MAP)’ report methodology | Changes that affect data access or data quality | Awaiting implementation | Following a query into the report methodology initiated by the CDSP as part of their reporting checks it was identified that reports were being issued to MAPs that contained Supply Meter Points that did not have the requesting MAP recorded in the UK Link system as the MAP for that Supply Meter Point. | Approved and awaiting implementation on 28/06/2024. | No
R0164 | Removing the Enumerations from Communications Method Data Item (J0386) to align with BSC CP 1594 | Changes that affect data access or data quality | Consultation | BSC has raised Change Proposal CP1594 which seeks to create an approvals process and a valid set for communications method. This change is proposing to create an approvals process to allow for the managed end dating of older technologies, such as Public switched telephone network (PSTN), Circuit Switched Data (CSD) and later 2G, and the assessment of the validity of newer communications technologies, such as (but not exclusively) Narrow Band-Intern of Things (NBIoT) and Category M (CAT-M). The evolution of metering communication systems underscores the need for timely updates. Legacy systems risk inefficiencies and potential security vulnerabilities. Implementing an approval process, modelled on BSCP601, ensures a standardised approach to introducing new technologies and managing the exit of old ones. Further justifications include: • To allow for the centrally managed end-dating of redundant communications technologies in line with known deadlines for those technologies to become redundant and unreliable. • To allow for the wider industry education of newer types of communication technologies. • To create and expand the already existing central knowledge base of the evolution and attributes of newer communication technologies as they relate to Settlement Metering Equipment. • To ensure transparency for all industry participants on the newer communications types available and the dates for which legacy communications must be removed. CP1594 will create a valid set, linked to the new approval process and using Data Item J0386 as a conduit to detail the approved communication methods as well as end dates for communication methods which are becoming redundant and unreliable. | Consultation to close 16/06/2024. Final Change Report to be published 20/06/2024 for decision 02/07/2024. | Yes
R0037 | Prepayment Credit Balance & Debt Transfer Processes - Vulnerable customers and the poor performance of the debt assignment protocol | Performance Improvements | On hold | This Change Proposal seeks to develop an agile, efficient, Consumer-centric solution for the transfer of credit or debt balances as part of a smart prepayment Switch, with aligned improvements to non-smart processes. | This Change Proposal has been placed on hold due to the MHHS Change Freeze. Some aspects of the Change Proposal will continue to be progressed where possible, a Request for Information closed 21/05/2024. | Yes
R0060 | ERDS Service Definition time zone correction | Performance Improvements | Initial Assessment | This change seeks to specify time zones within the ERDS Service Definition. For example: Data received by the ERDA shall be included within the ERDS Total Daily Processing on the basis that all data received prior to 23:00hrs is made available to the SMRA, EES Provider or CSS Provider (as applicable) by 06:00hrs the following Working Day. Data received after 23:00hrs will be made available to the SMRA, EES Provider or CSS Provider (as applicable) by the second Working Day. | Initial Assessment Report and Change Proposal Plan published on 06/06/2024 for approval by the Change Panel on 18/06/2024. | Yes
R0064 | Creating a Meter Operator Agent and MOCoP Installer | Performance Improvements | Awaiting implementation | This Change Proposal seeks to clarify the obligations of each type of metering provider by reintroducing this distinction. Prior to Retail Code Consolidation, electricity metering providers were either classified as Meter Operator Agent or MOCOPA Meter Installers. At Retail Code Consolidation these organisations were merged into a new category, Metering Equipment Managers, which also included gas metering providers. Whilst both types of organisations can provide metering services, not all MEM obligations in the REC apply to both organisations. | Awaiting Implementation on 28/06/2024. | No
R0076 | DNOs notifying Suppliers about Crossed Meters | Performance Improvements | Withdrawn | This Change seeks to introduce a way for the DNOs to raise a crossed meter issue with the supplier, in a way that directly feeds into the supplier’s list of crossed meter issues. The supplier will be required to feedback progress to the DNO who has raised the issue with them, this should be defined as a process within the REC. | This Change was addressed through R0121 and approved for implementation on 23/08/2024. The proposer has agreed to withdraw the Change. Adoption window closed 24/05/2024. | Yes
R0094 | Clarify obligations on gas meter exchanges that occur close to CoS | Performance Improvements | Final Assessment | This change has been raised to address an issue with the 'Switch with a Concurrent Change of MEM process'. MEMs are obliged to issue ONJOBs to the CDSP as part of a meter exchange. However, this would not be issued if the MEM has received a de- Appointment flow as part of the Switch. This change proposes to obligate MEMs to issue ONJOBs for any completed meter exchanges, even after receiving a de- Appointment flow. This will ensure accurate Meter Technical Details are available to the gaining Supplier and MEM. | Final Change Report published 05/06/2024 for decision 12/06/2024. | Yes
R0096 | CSS Message Regeneration Functionality | Performance Improvements | Impact Assessment (Service Provider) | Since CSS Go-Live there have been incidents whereby messages have been unsuccessfully generated by CSS and therefore are not delivered to the intended recipient. When CSS does not generate a message, it results in a failure of the Switching process and can cause significant complications for the intended recipient, who is required to manually intervene to re-synchronise messages This change has been raised to enable CSS to identify and regenerate messages that failed initial generation, such that the message recipient is not impacted. | 25 Working Day Impact Assessment due 18/06/2024. | No
R0105 | Review of ONAGE SLAs | Performance Improvements | Solution Development | In light of the changes introduced as part of the Switching Programme, this change seeks to review the SLAs and lead times around the sending and receiving/processing the ONAGE. | Re-baselined Change Proposal Plan. Solution Development window ongoing until 28/06/2024 and Party Impact Assessment due to be published 04/07/2024. | Yes
R0167 | Change Process Improvements following Code Manager review | Performance Improvements | Final Assessment | This Change Proposal has been raised to make the required changes to Schedule 5, to enable process enhancements to be made to support Change Process Improvements project. | Consultation has closed and responses are being reviewed. | Yes
R0169 | Introduction of Gate Closure Notifications | Performance Improvements | Impact Assessment (Service Provider) | Currently the completion of a gate closure event is not reported to CSS Users (at the time), and CSS Users which require to complete downstream processing must assume when the gate closure event has completed in order to initiate any downstream processing they require to complete. | Service Provider Preliminary Impact Assessment commenced 10/06/2024. | Yes
I0168 | Clarify and strengthen CRS Provider’s Requirements | Performance Improvements |  | Following the P1 incident, a clear need for improvement in the arrangements for managing switching services and response to major incidents was identified. An end-to-end incident review was undertaken, and this Issue seeks to deliver 54 review recommendations. | Change Issue was disussed at the Change Issues Group on 06/06/2024. | Yes
R0121 | SDEP Review Improvements (1) - Process Types | Changes relevant to SDEP | Awaiting implementation | This change will improve (Process Types and escalations) operational efficiency for users of the SDEP system, which offers opportunities for REC Parties to enhance how consumer- related queries are dealt with (time and accuracy). | Approved and awaiting implementation on 23/08/2024. | No
R0122 | SDEP Review Improvements (2) - Usability | Changes relevant to SDEP | On hold | This change will improve (Usability) operational efficiency for users of the SDEP system, thereby allowing consumer issues to be addressed sooner / more accurately. | On hold until Post MHHS M10 due to technical code freeze. | No
R0123 | SDEP Review Improvements (3) - Look and feel | Changes relevant to SDEP | On hold | This change will improve (Look and Feel) operational efficiency for users of the SDEP system and therefore give more opportunity for timely rectification of consumer issues. | On hold until Post MHHS M10 due to technical code freeze. | No
R0124 | SDEP Review Improvements (4) - Reporting | Changes relevant to SDEP | On hold | This change will improve (Reporting) operational efficiency for users of the SDEP system. | On hold until Post MHHS M10 due to technical code freeze. | No
R0125 | SDEP Review Improvements (5) – multilateral Erroneous Switches | Changes relevant to SDEP | On hold | This change will improve (multilateral Erroneous Switches) operational efficiency for users of the SDEP system. | On hold until Post MHHS M10 due to technical code freeze. | No
R0126 | SDEP Review Improvements (6) – SDEP User Guide and Obligations | Changes relevant to SDEP | Solution Development | This change will improve (SDEP User Guide and Obligations) operational efficiency for users of the SDEP system. | Requirements to be refined. | No
R0162 | Access to SDES for Gas Networks | Changes relevant to SDEP | On hold | Raising on behalf of the Gas Networks, who currently struggle to find who to email queries to within suppliers organisation. Suppliers and Electricity DNO's moved to SDES to ensure all communications were in a secure portal, with SLA's and for GDPR reasons, but Gas Networks do not have access to this portal, and not considered during the implementation of the system. They also obtain photo's when out on site to help resolve queries and would like somewhere to upload them to send to suppliers. | On hold until Post MHHS M10 due to technical code freeze. | No
R0152 | Revision to the Consolidated Metering Code of Practice (CoMCoP) | Changes to metering accreditation | Solution Development | The new consolidated Metering Code of Practice was implemented on 01 April 2023. Since its implementation several issues have been identified and some have been raised to RECCo and the Code Manager by REC Parties where they are unable to meet their obligations. The Code Manager has reviewed these and determined changes are required. | Weekly working groups and solution development window open until October 2024. | No
R0161 | Enabling Robotics for SDEP | Related to a derogation | On hold | The Secure Data Exchange Portal (SDEP) is a mailbox that enables the transfer of sensitive customer related data in a way that ensures data is safe and secure. Suppliers are obliged to send and receive queries and escalations via the SDEP. Unfortunately, the SDEP has issues in bulk resolving processes which could be solved by the removal of the prohibition of the use of robotics. For example, there is no function to be able to retrieve cases specific to each team, work these and then automatically issue a response. Currently, to get the same kind of functionality, an agent or team lead would need to manually process. In another scenario, under REC schedule 30, as part of each of the processes, we are obliged to issue an escalation where there has been no response within set timeframes. Prior to SDEP implementation, we would be able to issue email escalations automatically where there was an absence of a response flow. With the SDEP this process is now manual: an agent will need to sign in to ECOES, navigate to the appropriate module, and input the data. | On hold until Post MHHS M10 due to technical code freeze. | No
R0170 | Withdrawal of Service Termination Issue Reporting Guidance (STIRG) from REC Governance | For information | Initial Assessment | REC MEP has decided that the current governance for the STIRG is unsuitable for this type of document. | The Initial Assessment Report and Change Proposal Plan was published on 06/06/2024 for decision 18/06/2024. | Yes
R0181 | Schedule 14 - Metering Operations Footnote Review | For information | Initial Assessment | The footnotes need to be reviewed so they are correct and referenced in the right places within process tables and are easier to follow. | Initial Assessment Report and Change Proposal Plan published on 11/06/2024 for approval by the Change Panel on 18/06/2024. | Yes

## Data validation (hidden)
Type | New status since last PAB update
PAB is or likely to be the Responsible Committee | Yes
Changes that affect data access or data quality | No
Changes that directly affect Performance Assurance
Changes relevant to SDEP
Changes to metering accreditation
Performance Improvements
Related to a derogation
For information
Process Stage
New
On hold
Initial Assessment
Impact Assessment (Service Provider)
Impact Assessment (Party)
Solution Development
Preliminary Assessment
Consultation
Final Assessment
Awaiting Authority decision
Awaiting implementation
Implemented
Withdrawn
Rejection