## Cover sheet and stats
This document is classified as WHITE. Information is for public, unrestricted dissemination and publication.
REFERENCE | RECPAB_25_0225_11a
STATUS | FOR INFORMATION
CHANGE MANAGEMENT OPERATIONAL UPDATE
AUTHORED BY LORNA MALLON - PRINCIPAL REGULATORY CONSULTANT - REC CODE MANAGER
REVIEWED BY ELISE HANDY - CHANGE ANALYST - REC CODE MANAGER
FOR INFORMATION | This paper provides the regular update on REC changes to the PAB
CHANGE PROPOSALS |  | Live Changes (In Play) | 2025-02-14 |  | Awaiting Implementation | Remaining Changes/Issues in Progress
|  |  | 78 |  | 12 | 66
RELEVANT TO PAB |  |  | 64
Type |  |  |  | Number |  |  | Total
PAB is or is likely to be the Responsible Committee |  |  |  | 4 |  |  | 64
Changes that affect data access or data quality |  |  |  | 9
Changes that directly affect Performance Assurance |  |  |  | 24
Changes relevant to SDEP |  |  |  | 4
Changes to metering accreditation |  |  |  | 1
Performance improvements |  |  |  | 10
Related to a derogation |  |  |  | 2
For information |  |  |  | 10

## Table
Ref. | Title | Relevance to PAB | Status (Dec 24) | Background | Update | New status since last update to PAB
R0168 | Clarify and strengthen CRS Provider’s Requirements | Performance Improvements | Awaiting implementation | Following the P1 incident, a clear need for improvement in the arrangements for managing switching services and response to major incidents was identified. An end-to-end incident review was undertaken, and this Issue seeks to deliver 54 review recommendations. | Approved for implementation on 28 Feb. Progressed from Issue to Change. | Yes
I0172 | New Build - Commissioning Process Review | Changes that directly affect Performance Assurance | Initial Assessment | End-to-end review of the new connections process. This will be a cross-code change. | Issue to be discussed at REC Change Issues Group in March | No
I0174 | Mandating ETTOS Follow up | Performance Improvements | Solution Development | It has been identified that not all ETTOS leads are flowing through into the theft outcome files and is uncertain to what degree these leads are being investigated. | Solution being developed through the Theft Issues Group. | No
I0175 | Introducing a Reasonable Endeavours Scheme within the REC | PAB is or likely to be the Responsible Committee | Solution Development | There is a current disincentive for a Supplier to pursue a particularly complex energy theft investigation where there is both little prospect of costs being recovered directly from the Consumer and those costs materially exceeding the Theft Detection Value under the TDIS. This Issue seeks to consider whether a Reasonable Endeavours scheme would work in the REC. | Solution being developed through the Theft Issues Group. - please see further update given as part of Party Assurance Paper. | No
I0176 | Creation of an Energy Theft Detection and Resolution Body | PAB is or likely to be the Responsible Committee | Solution Development | There is currently a lack of consistent standards of investigation and good quality data across GB. This Issue seeks to consider whether a Energy Theft Detection and Resolution Body would work in the REC. | Solution being developed through the Theft Issues Group. | No
I0179 | Proposal for Limiting Queries in EES API Calls (Single API Call With Multiple Queries) | Changes that directly affect Performance Assurance | Solution Development | RECCo is proposing the establishment of a limit on the number of queries permitted within a single API call. There could be a potential performance degradation and system instability that can occur when a large number of queries are made in a single API call to Electricity Enquiry Services (EES) API. | Reviewing Service Provider Impact Assemsent reponse. | No
I0180 | Clarity on use of on hold for switching issues, including the obligations of CSS Users | Changes that directly affect Performance Assurance | Impact Assessment (Service Provider) | Clarity on use of on hold for switching issues, including the obligations of CSS Users | Service Provider IA. | No
I0186 | Non dual-fuel Gas PSR customer | For information | Solution Development | Non dual-fuel customers who register upon the PSR, will have their PSR data flow across energy industry data flows to mean that all parties are aware of any PSR Needs Codes, allowing us all to provide equal access to our services and support. This will be achieved via the utilisation of existing processes and systems. | to be developed through working group. | Yes
I0187 | Schedule 8 Review and Best Practice Guidance Development | For information | Initial Assessment | Schedule 8 Unbilled Energy Code of Practice has not been reviewed since its development for REC go-live. | Being progressed via Theft Issues Group. | No
I0189 | Voice of the Consumer | For information | Solution Development | There is currently a gap in our understanding of the effectiveness of the retail systems and processes in delivering positive outcomes for customers. While we do conduct customer surveys on certain areas and assess some aspects of customer satisfaction, it may be necessary to expand our evaluation methods to gain a more comprehensive understanding of the issue. | Code Manager to review output of Working Group 2 | No
I0190 | Related Meter Point RMP status rules | Performance Improvements | Initial Assessment | MPANs can be related inconsistent with the current code drafting. Note that initial analysis suggests this issue is limited in the current market, with c. 20 MPAN relationships current impacted. It has been identified that allowing MPANs with different RMP statuses to be related may cause issues with the auto registration processes that will operate under MHHS. There may be an impact on switching as disconnected MPANs cannot be switched which needs to be confirmed. | Currently being reviewed by the Code Manager and will be tabled at Change Issues Group | No
I0191 | De-energisation of disconnected meters | Performance Improvements | Initial Assessment | Parties identified that there are a number of meters (NG alone have 5k in this state) that are showing as terminated but energised. Discussion at RIG identified that REC Is potentially lacking detail/obligations/timescales on suppliers/DNOs to report/update/respond to disconnection queries. These MPRNs are still showing as secured active in CSS and can be switched/updated etc even if the MPRN is disconnected. | Currently being reviewed by the Code Manager and will be tabled at Change Issues Group | No
I0194 | CSS Change to Allow Prevent of Registration by Market Segment | Changes that directly affect Performance Assurance | Impact Assessment (Service Provider) | To prevent a Supplier with exemptions in place that were approved, in BSC and REC PAB for Smart and Unmetered, from registering meter points other than those that they are Qualified in. | Service Provider IA ongoing. | No
I0196 | Requiring the Supplier/Shipper to validate and enrich the data from the MEM prior to updating this in CDSP | Changes that affect data access or data quality | Initial Assessment | This will help support inaccurate information being updated in the CDSP. | Information request open. | No
I0197 | Introduce a maximum timeframe Fault Resolution deadline | Changes that directly affect Performance Assurance | Initial Assessment | We believe this issue impacts both electricity and gas and would therefore assume that any change in this space would be dual fuel. Ensure that Performance Assurance are able to monitor that the maximum timeframes are being met | REC Performance Assurance to review Information Request responses. | No
I0198 | GAS MEMs move towards a single interface for key market messages | Changes that affect data access or data quality | Solution Development | This will help support and improve communication channels to reduce missing messages and rejections not being worked whilst developing the process for customer appointed MEMs and ultimately simplify. | Was presented to Feb CHIG. Party IA to begin in March. | No
I0200 | Improving address management targets | Changes that directly affect Performance Assurance | Initial Assessment | Address management is the responsibility of DCC, with support from REC Parties. There has been progress resolving address data issues, but there is no mechanism to clearly establish code level targets for address improvement, or overall market performance. | The Code Manager is working with industry and DCC to understand what information is available to better understand the issue, for example if any types of addresses can be tackled, including being excluded, in bulk. This could result in several changes or other activity. If PAB members have other questions please raise these in advance of the meeting, so that we can have relevant team members attend to answer these questions. | No
I0205 | Provision of HH consumption data for Advanced Meter ETs | Changes that affect data access or data quality | Initial Assessment | As part of the MHHS REC code change activity, a change has been made to REC Schedule 30 to remove the half hourly meter exemption from the Erroneous Transfer provisions. Whilst this is necessary from an MHHS perspective with all sites becoming half hourly settled, the application of ET obligations in the Advanced Meter segment creates some additional challenges. To be able to accurately bill an Advanced Meter site, following repatriation of that customer to their correct supplier after an ET has been raised / agreed, the supplier needs to have access to half hourly consumption data for the ET period when they were not the registered supplier. With ETs potentially taking up to 2 years to be identified and resolved, the only place that the supplier could reliably source that HH consumption data would be from the other (losing) supplier. | Code Manager Initial Assessment. | No
I0212 | Protecting Crimestoppers and their Contacts | Changes that directly affect Performance Assurance | Solution Development | We are seeking to clarify how the information we pass on to suppliers, DNOs, GNOs and Transporters can be used and shared. The aim of which is to protect our charity's reputation, our anonymity guarantee and the welfare of those who contact Crimestoppers/Stay Energy Safe. | Solution developemnt to end and due to go out for consultation in March. | Yes
I0213 | Creation of a mechanism to allow third parties to report objection activity that is not compliant with code or licence conditions for energy supply. | Changes that directly affect Performance Assurance | Initial Assessment | Presently only industry parties can raise the matter of non-compliant or unwarranted objections activity that a supplier may be participating in. We believe that RECCo needs to consider accepting notice and evidence (that can be acted upon) from qualifying 'non industry' parties, from third party consultants and brokers. | Code Manager Initial Assessment | No
I0214 | Multiple Switch Requests Increasing Objection Rate | Changes that directly affect Performance Assurance | Solution Development | REC Parties have told the Code Manager that they are seeing multiple registrations attempts (10 plus attempts on consecutive days in some instances) on individual MPxNs. They are concerned about Consumer detriment as those trying to switch are not getting time to review objection related communications from their current Supplier to allow them to act and resolve the issue. This was initially presented as a non-domestic issue, but initial Code Manager investigations have also highlighted potential concern around proposed domestic transfers as well. There is also a risk of Party Performance impacts with initial analysis flagging potential impacts on Performance Assurance Risk Drivers, 8.9, 8.10 & 8.11. | Has been discussed at TCW, devloping business case. | No
I0215 | Schedule 30 Switch Meter Reading Problems - Rejections and Timings | Changes that directly affect Performance Assurance | Solution Development | The Switch Meter Reading Problems processes do not appropriately describe the use of rejections. This inhibits Parties from operating the process as intended and may cause unnecessary delay to the production of an accurate and agreed Switching Meter Reading. Additionally, the Performance Assurance Reporting Catalogue (PARC) is missing key data items to allow Performance Assurance to more accurately assure Party performance against Risk Drivers 5.6 and 5.8. Rejection reasons do not appear to be being reviewed, nor are they understood to be end statuses for the process. | Change plan at 18 Feb Change Panel. IA due to start in Feb- March. | No
I0216 | REC Changes to tie in with DCP419 | For information | Initial Assessment | DCP419 is looking to place obligations on any Party or agent to update the DNO before any planned de-energisation or comms interruptions on sites with a smart meter. This is to allow DNOs to be able to manage any off supply notifications (via AD1 alters) | Working on feedback from change issues group and determining next steps | No
R0217 | Amending contractual obligations for SIPs at Non-Domestic Premises | For information | Final Assessment | The contractual obligations in section 21 of Schedule 14 are too restrictive or not relevant to Non-Domestic Premises making delivering isolators to Non-Domestic Premises more complex than it needs to be. | Progressed to CP. Consultation closed on 15/02 and final determination due on 12 March. | Yes
I0218 | Proposal to Enable Broader Use of Retail Energy Location (REL) Data for Non-Switching Applications | Changes that affect data access or data quality | Solution Development | The problem being addressed is the current restriction within the Retail Energy Code (REC) that limits the use of Retail Energy Location (REL) data solely to switching purposes. This restriction prevents the full utilisation of REL data, which could be valuable for a broader range of operational, regulatory, and industry applications. Key Issues: - Currently, REL data, enriched with Unique Property Reference Numbers (UPRNs), is available via the Electricity and Gas Enquiry Services. However, Schedule 29 (Address Management) of the REC restricts its use to switching purposes only, preventing its use in other important industry initiatives. - Various industry stakeholders, including REC and non-REC data requestors as well as Ofgem (the regulator), have expressed a strong interest in utilising REL data for non-switching purposes. The restriction is seen as a limitation, especially for initiatives that require accurate property data to support wider operational and regulatory functions. - By restricting the use of REL data to switching, stakeholders are unable to fully leverage it for improving operational efficiency, regulatory compliance, and overall service delivery. Lifting this restriction would enable the wider use of REL data, allowing stakeholders to benefit from its full potential across various non-switching applications. | Change Report (Proposal Plan) approved at Jan Change Panel. Solution development ongoing. | Yes
I0219 | Stranded RMPs in Defunct Suppliers | Related to a derogation | Initial Assessment | Currently within Schedule 23 a Registration can only be undertaken on RMPs with an Operational or Dormant RMP Status, and not Terminated. Terminated is a status that the RMP is set to when the Meter Point Status is no longer operational or the site is isolated. It is right that these sites are not able to be Registered as there is a risk that Suppliers could inadvertently Register such Meter Points. We do have instances where such sites are stranded in defunct Supplier portfolios - and the Supplier no longer has the capability to take the relevant action to Deactivate the Registrations. This may because the operational staff have left and the business is in administration. | Discuss with Proposer if change should be withdrawn/merged with I0178. | No
I0222 | ESME ID Update Rejections | Changes that affect data access or data quality | Solution Development | Inability to update ESME IDs as part of Data Cleanse and Metering Activities | Change plan approved, solution development and IA to be completed Feb- May. | Yes
I0223 | Reconciliation of Unallocatable Transactions Review | For information | Solution Development | The process for Reconciliation of Unallocatable Transactions is set out in Section 10 of Schedule 11. During the most recent reconciliation delivery (the gas process from July 2024) several areas of improvement were identified, critically a lack of clarity regarding historic Supplier Licences and how to include or exclude them from the calculations. The Code Manager believes that this lack of clarity and past precedent would lead to material impact on one or more Party. | Solution to be developed through CHIG. | Yes
I0224 | Agile Reporting within CSS | Performance Improvements | Impact Assessment (Service Provider) | As part of the impact assessment process for R0115, it was identified that it is very costly and time consuming to make reporting changes within the CSS architecture. As such, we would like to explore enabling agile reporting within the CSS ecosystem, by creating a functionality that consolidates all necessary data into a single, centralised database. | Service Provider IA. | Yes
R0225 | Clarification on TDIS portfolio transfers on sale | Changes that directly affect Performance Assurance | Initial Assessment | The current wording of the Energy Theft Reduction Schedule has wording on the transfer of theft targets on portfolio sale, however which sales would qualify is ambiguous. | Issue progressed to CP. Solution development complete, next step consultation. | Yes
I0227 | Domestic Elective HH Switching | For information | Solution Development | Customers are struggling to leave their suppliers as on EHH, measurement class F and profile class 00 are used, and as 00 is also associated with HH Business Supplies, some suppliers have issues registering the sites. They then request the old supplier changes the PC before they switch supply, whereas the old supplier believes the new supplier should be able to accept them as is. And this step shouldn't be necessary. There is nothing on the REC Schedules on best practice around this. A recent study by Perse Technology, that made use of Electralink switching Data, indicated a steep increase in the number of Domestic EHH switches, with a corresponding potential saving in excess of 100m pounds | Solition development due to be complete by April. | Yes
I0228 | ECOES API for Export MPAN Creation at Scale | Changes that affect data access or data quality | Initial Assessment | We want to exponentially scale our export portfolio and offer several new export products and low-carbon tech to new and existing customers, at present, we average 5k export MPAN creation requests per month but expect to scale this to 10k per month over the next six months. Under the current ECOES export MPAN creation architecture (MPAN Requests), a user can create an export MPAN on a one-to-one level which prohibits scaling of new export products for our customers. We have explored batch processes with the DNOs but have been categorically told 'No' from the largest DNO (23.78% of our export MPAN requests) to a batch process as they have batch capability on their side of ECOES. Therefore, we require an API to ECOES that enables an energy supplier to create an export MPAN at scale | Code Manager Initial Assessment | No
I0230 | Meter Asset Providers may not receive effective from settlement date (J0049) in the D0303 flow following MHHS design changes. | For information | New | As part of Market Wide Half Hourly Settlement (MHHS) design, the requirement to provide a data item (J0049) in the D0303 flow is being changed from mandatory (as now) to optional. This means Meter Asset Providers (MAP) and other agents who use the information in this flow may not receive it. | New. | No
I0231 | Shared Sites in Electricity Enquiry Service (EES) | Changes that affect data access or data quality | Initial Assessment | There is a concern regarding shared sites (as defined by BSCP550) that have multiple suppliers linked to them. The investigation revealed a lack of visibility of these sites, and it appears that the industry is similarly uninformed. Elexon, the REC, and the wider industry do not have a consistent way of identifying these shared sites. Therefore, there is a good chance that agents are holding shared sites within their portfolio without knowing it. We would like to explore whether the EES Online Portal has any flags or mechanisms that could help identify these shared sites. If not could these be added? | Code Manager initial assessment. | No
I0232 | Non-Domestic Change of Occupier SDEP Screens (R0155 Solution) | Changes relevant to SDEP | Solution Development | This Issue has been raised to develop the dedicated Non-Domestic Change of Occupier SDEP screens that were not possible as part of R0155 – Change of Occupier: Evidentiary Standards and Timescales. Should this Issue progress with a developed solution, the new dedicated Non-Domestic Change of Occupier screens would replace the temporary work around provided as a temporary workaround in the R0155 solution. | Soltion development through CHIG | Yes
I0233 | Introduction of an Energy Theft Unit (ETU) under the REC | Changes that directly affect Performance Assurance | Solution Development | This proposal is seeking to introduce the Energy Theft Unit (ETU) under the REC. This unit would be provisioned by the City of London Police to investigate and prosecute identified organised Energy Theft and associated crime. | Solution developemnt to end and due to go out for consultation in March. | Yes
I0234 | Introduction of an energy theft Referral Assessment Service under the REC | Changes that directly affect Performance Assurance | Solution Development | This proposal seeks to establish a Referral Assessment Service (RAS) as a new REC service and embedding it within REC governance. | Solution developemnt to end and due to go out for IA in March. | Yes
I0236 | REC Party Auto de-accession proposal | Changes that directly affect Performance Assurance | Solution Development | Update the REC to allow the option of any Party who has not proceeded to pursue Certification within 12 months of accession, and has not contacted the REC Code Manager in at least 6 months to indicate they wish to do so/remain acceded, to be removed without further contact or confirmation with that Party. | Solition development- Legal review. | Yes
I0237 | Erroneous Switch Review | Changes that directly affect Performance Assurance | New | The current solution for Erroneous Switch (ES) resolution is failing some Consumers, there are gaps in the process and several areas that could be considered for improvement. It has been a number of years since the process has been reviewed end to end. Since then, Faster Switching has been introduced and MHHS is on the horizon. | Code Manager initial assessment. | No
R0037 | Prepayment Credit Balance & Debt Transfer Processes - Vulnerable customers and the poor performance of the debt assignment protocol | Performance Improvements | On hold | This Change Proposal seeks to develop an agile, efficient, Consumer-centric solution for the transfer of credit or debt balances as part of a smart prepayment Switch, with aligned improvements to non-smart processes. | This Change Proposal has been placed on hold due to the MHHS Change Freeze. Some aspects of the Change Proposal will continue to be progressed where possible. | No
R0060 | ERDS Service Definition time zone correction | Performance Improvements | Awaiting implementation | This change seeks to specify time zones within the ERDS Service Definition. For example: Data received by the ERDA shall be included within the ERDS Total Daily Processing on the basis that all data received prior to 23:00hrs is made available to the SMRA, EES Provider or CSS Provider (as applicable) by 06:00hrs the following Working Day. Data received after 23:00hrs will be made available to the SMRA, EES Provider or CSS Provider (as applicable) by the second Working Day. | Approved by Technical Expert Panel on 28/08/2024. Pending implementation on 27/06/2025 | No
R0080 | Improvements to ‘Failed to Deliver’ CSS Messages | Changes that directly affect Performance Assurance | Awaiting implementation | Since Go-Live a large number of messages have been unsuccessfully delivered due to failures of CSS Users gateways, resulting in CSS exhausting the 12-hour retry period. This Change Proposal has been raised to explore and address this issue. | On 31/07/2024, the Technical Expert Panel voted to approve R0080 for implementation 27/06/2025. | No
R0096 | CSS Message Regeneration Functionality | Performance Improvements | Impact Assessment (Service Provider) | Since CSS Go-Live there have been incidents whereby messages have been unsuccessfully generated by CSS and therefore are not delivered to the intended recipient. When CSS does not generate a message, it results in a failure of the Switching process and can cause significant complications for the intended recipient, who is required to manually intervene to re-synchronise messages This change has been raised to enable CSS to identify and regenerate messages that failed initial generation, such that the message recipient is not impacted. | There are ongoing conversations on technical design funds being brought forward within the change process. The outcome of these conversations will determine the next steps. | No
R0100 | Update to Error Handling Documents | Changes that directly affect Performance Assurance | Solution Development | There are duplications between the CSS Message Business Data Validation Rules document (a Category 2 document) and the CSS Error Processing guide (a Category 3 guidance document), which is resulting in confusion and complications within the error handling process. This Change Proposal has been raised to update the Business Data Validation Rules document, to capture the appropriate information that is removed from the CSS Error Processing guide and to ensure alignment with newly created knowledge articles. | To be reviewed by St Clements prior to plan for progression. | No
R0122 | SDEP Review Improvements (2) - Usability | Changes relevant to SDEP | On hold | This change will improve (Usability) operational efficiency for users of the SDEP system, thereby allowing consumer issues to be addressed sooner / more accurately. | On hold until Post MHHS M10 due to technical code freeze. | No
R0125 | SDEP Review Improvements (5) – multilateral Erroneous Switches | Changes relevant to SDEP | On hold | This change will improve (multilateral Erroneous Switches) operational efficiency for users of the SDEP system. | On hold until Post MHHS M10 due to technical code freeze. | No
R0137/ A | Introducing Third Party Intermediary (energy broker) assurance and accreditation | Changes that directly affect Performance Assurance | Awaiting Authority decision | Introducing Third Party Intermediary (energy broker) assurance and accreditation. | On 03 December 2024, REC Change Panel voted to recommend that the Authority reject R0137 Introducing Third Party Intermediary (Energy Broker) Assurance and Accreditation and approve R0137A Introducing Third Party Intermediary (Energy Broker) Assurance and Accreditation (Alternate) in line with the Code Manager recommendation. | No
R0144 | Allowing different Metering Equipment Managers (MEMs) to be appointed to Import and Export Metering Points | Changes that directly affect Performance Assurance | Solution Development | Cross-code Change relating to BSC P459, relating to management of Import and Export MEMs. | On hold while R0207 progresses and due to MHHS | No
R0148 | Introduction of classification-based access model into the REC in support of Open Data | Changes that affect data access or data quality | Solution Development | Currently Enquiry Services Data is only available to users whose roles and purposes for access are detailed within the Data Access Matrix (DAM). RECCo has undertaken a project to look at REC controlled data sources and created a Metadata Catalogue based on a Data Classification Model. This details the data items along with descriptions, identification of the associated data, roles, responsibilities, and classification. The output of this work will be utilised to improve access to Enquiry Services Data by making certain data items (defined as Always Open) easily available to everyone and simplifying the approval process for data items which can be made available if certain conditions have been met. | planning in SP IA. | No
R0152 | Revision to the Consolidated Metering Code of Practice (CoMCoP) | Changes to metering accreditation | Consultation | The new consolidated Metering Code of Practice was implemented on 01 April 2023. Since its implementation several issues have been identified and some have been raised to RECCo and the Code Manager by REC Parties where they are unable to meet their obligations. The Code Manager has reviewed these and determined changes are required. | Extended consultation period open for 8 weeks. | Yes
R0155 | Change of Tenancy: Evidentiary Standards and Timescales | Changes that directly affect Performance Assurance | Awaiting implementation | Non-domestic energy contracts commit the consumer to a fixed duration and unlike domestic consumers, they are less able to change supplier mid-term. However, there are instances where a non-domestic premises undergoes a Change of Tenancy (CoT), and the incoming tenant/owner who inherits the supply point and its relationship to the predecessors chosen energy supplier may wish to make alternative arrangements that best matches their needs. In these circumstances, the incoming tenant may choose to enter a new contract with the same supplier or take up a wholly new contract with a new supplier. | Authority Approval recived in line with Code Manager recommendation for implementation in June 2025. | Yes
R0161 | Enabling Robotics for SDEP | Related to a derogation | On hold | The Secure Data Exchange Portal (SDEP) is a mailbox that enables the transfer of sensitive customer related data in a way that ensures data is safe and secure. Suppliers are obliged to send and receive queries and escalations via the SDEP. Unfortunately, the SDEP has issues in bulk resolving processes which could be solved by the removal of the prohibition of the use of robotics. For example, there is no function to be able to retrieve cases specific to each team, work these and then automatically issue a response. Currently, to get the same kind of functionality, an agent or team lead would need to manually process. In another scenario, under REC schedule 30, as part of each of the processes, we are obliged to issue an escalation where there has been no response within set timeframes. Prior to SDEP implementation, we would be able to issue email escalations automatically where there was an absence of a response flow. With the SDEP this process is now manual: an agent will need to sign in to ECOES, navigate to the appropriate module, and input the data. | On hold until Post MHHS M10 due to technical code freeze. | No
R0162 | Access to SDES for Gas Networks | Changes relevant to SDEP | On hold | Raising on behalf of the Gas Networks, who currently struggle to find who to email queries to within suppliers organisation. Suppliers and Electricity DNO's moved to SDES to ensure all communications were in a secure portal, with SLA's and for GDPR reasons, but Gas Networks do not have access to this portal, and not considered during the implementation of the system. They also obtain photo's when out on site to help resolve queries and would like somewhere to upload them to send to suppliers. | On hold until Post MHHS M10 due to technical code freeze. | No
R0169 | Introduction of Gate Closure Notifications | Performance Improvements | Impact Assessment (Service Provider) | Currently the completion of a gate closure event is not reported to CSS Users (at the time), and CSS Users which require to complete downstream processing must assume when the gate closure event has completed in order to initiate any downstream processing they require to complete. | Detailed Service Provider Impact Assessment to take place, timing dependent upon progression of R0096 | No
R0173 | Improvements to the Theft Detection Incentive Scheme | Performance Improvements | Awaiting Authority decision | The TDIS exists to incentivise Suppliers to resolve Energy Theft. The current TDIS was inherited from legacy codes and has proved challenging for impacted Parties. The following challenges have been identified. - It has a complex methodology - It results in unpredictable outcomes - The debits/credits payable are dependent on the relative performance of each Supplier - The determination of credits and debits is not directly linked to theft targets - The value per theft varies dependent on overall market performance - Scheme participants can "buy-out" of the scheme - It only rewards confirmed thefts - It assumes theft is evenly distributed - The scheme pot of funds is never fully distributed - Results are skewed for smaller parties. | Change Panel Recommended that the Authority approve R0173 Improvements to the Theft Detection Incentive Scheme (TDIS), in line with the Code Manager recommendation. | No
R0178 | Improvements to CSS Business Process Logic | Changes that directly affect Performance Assurance | Impact Assessment (Service Provider) | This change proposal is aimed towards rectifying a collection of issues that were identified with the CSS Business Process Logic. These have been identified as follows: 1. Deactivation of an active reg. whilst in-flight switch in progress 2. Deactivation of a prior cancelled registration 3. OFAF switch containing multiple MPxN - To replace R0153. | Service Provider Detailed Impact Assessment to be reviewed, and next steps decided, by the Code Manager following completion by the Service Provider. | No
R0183 | DPI Extract from CSS | Changes that directly affect Performance Assurance | Impact Assessment (Service Provider) | The Domestic Premises Indicator was introduced through the faster switching programme and is mastered within the Central Switching Service. It is used to determine whether an MPxN is domestic or non-domestic for a variety of purposes. The indicator can be updated on switching or when the registered supplier becomes aware it is incorrect. Anecdotal evidence has emerged that there are data quality issues within the data. Current this data is not available for the majority of meter points within the enquiry services which prevents action to monitor and/or correct errors in the data. | Service Provider IA to be completed. | No
R0201 | Creation of a Tool to Manually Correct ERDS / CSS Discrepancies | Changes that affect data access or data quality | Solution Development | There is currently a tool utilised by DNOs to manually correct registration data to align the Registered Supplier in ERDS with the data held in CSS. The Market-Wide Half Hourly Settlement (MHHS) Design does not allow for retrospective amendment of Supplier Registration i.e. there is no equivalent tool for manual correction post MHHS go live (M10). Therefore, post MHHS implementation, any issues which prevent CSS data being reflected in ERDS cannot be corrected. This will prevent the Supplier from appointing agents and will lead to errors in settlement data under the BSC. A change is required to address this. | Re baseline approved on 10/01/2025. This is to allow the BSC consultation period to close. | No
R0202 | Performance Assurance Report Catalogue Updates | PAB is or likely to be the Responsible Committee | Impact Assessment (Party) | The Performance Assurance Report Catalogue has been updated following an impact assessment of changes being introduced by MHHS. | A rebaseline plan was approved and agreed to amend scope of the change. | No
R0207 | Import / Export MOA Charging Clarification | Changes that directly affect Performance Assurance | Final Assessment | BSC Mod 459 and REC CP R0144 were raised to allow different MOAs to be appointed for the import and export MPANs on a shared meter. One of the justifications for this was to stop export suppliers being charged inflated rates. Both changes have been placed on hold due to the MHHS Programme so this change has been raised to specifically resolve the charging issue. | The consultation has closed. The Code Manager is reviewing responses, and the Change Report (Final Recommendation) will be published by 05 March 2025, for voting at the March Metering Expert Panel. | Yes
R0209 | Implementation of MHHS Arrangements | Changes that directly affect Performance Assurance | Awaiting implementation | Implementation of Market-wide Half Hourly Settlement (MHHS) is being delivered through Ofgem’s Electricity Settlement Reform Significant Code Review (SCR). This Authority Change Proposal will ensure that the appropriate obligations, processes and provisions are defined within the REC, enabling a successful transition to enduring governance and operational arrangements. | Authoroty Approval received for implementation at MHHS M8. | No
R0210 | Evolution of the CRS Performance Charge | PAB is or likely to be the Responsible Committee | Awaiting implementation | R0025 established a new performance charge for DCC, which linked its performance against its Service Definition with financial incentives. During the R0025 PAB members noted the need to further develop the methodology, including reviewing it periodically. The RPA has worked with the PAB to develop proposals to enhance the performance charge. | Approved by the Performance Assurance Board for implementation in the Feb 2025 Release. | No
R0221 | Increase Smart capability of SMETS2 Twin Element ESME to support solar and storage use cases | For information | Initial Assessment | SEC schedule 9 Smart Metering Equipment Technical Specifications (SMETS) defines how a Twin Element Electricity Smart Metering Equipment (ESME) captures and records electricity consumption on a per element basis. The Proposer would like to enable Twin Element meters to record exported energy on the secondary element to allow innovative use cases. | Code Manager Initial Assessment | No
I0241 | MHHS Incremental Changes for Go Live | For information | Initial Assessment | This issue looks to assess and confirm the scope to be taken forward into the Change Proposal that will deliver critical updates to the REC MHHS Code Drafting. | NEW since last month | Yes

## Data validation (hidden)
Type | New status since last PAB update
PAB is or likely to be the Responsible Committee | Yes
Changes that affect data access or data quality | No
Changes that directly affect Performance Assurance
Changes relevant to SDEP
Changes to metering accreditation
Performance Improvements
Related to a derogation
For information
Process Stage
New
On hold
Initial Assessment
Impact Assessment (Service Provider)
Impact Assessment (Party)
Solution Development
Preliminary Assessment
Consultation
Final Assessment
Awaiting Authority decision
Awaiting implementation
Implemented
Withdrawn
Rejection