## Cover
REC Performance Assurance Operating Plan
2025-07-22
Version 6.0 [DRAFT]

## Version History
Version | Status | Issue Date | Author | Comments
1.0 | Final | 2021-07-19 | REC Code Manager | N/A
2.0 | Final | 2021-10-18 | REC Code Manager | Updated following Performance Assurance Framework (PAF) product review.
3.0 | Final | 2022-09-20 | REC Code Manager | Updated for Year 2.
3.0 | Final | 2022-11-01 | REC Code Manager | Finalised following consultation.
4.0 | Final | 2023-08-30 | REC Code Manager | Updated for Year 3.
5.0 | Final | 2024-08-27 | REC Code Manager | Updated for Year 4.
6.0 | Draft | 2025-07-22 | REC Code Manager | Updated draft for Year 5.

## Operating Plan 2025-26
REC Performance Assurance Operating Plan 2025-26
Ref | Activity | Objective | Retail Risk Mapping | Indicative Impact | Code Requirement | Contractually Agreed | PAB Determined | Beneficiary Party | Responsible Party | Task | Expected Output | Time Effort Estimate | Status | Schedule
[14 empty] | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01
PAB Deep Dives Focusing on Emerging Risks
1 | Review of Escalations and SDEP under the REC | To determine effectivenes of escalations and SDEP to efficiently resolve issues faced by consumers. To identify opportunities to reduce the need for escalations through process improvement. | I, II | ●● |  |  | ü | Energy Suppliers | RECCo / REC Code Manager, Energy Suppliers | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | 2.5% | Planned | 2025-09-01: 1.1, 1.2 ◊; 2025-10-01: Contigency for data provision (if required); 2026-05-01: 1.3; 2026-06-01: 1.3; 2026-07-01: 1.3; 2026-08-01: 1.4 ◊
2 | Driving REC Data Quality Improvements | To refine the data cleanse methodology to ensure it is cost beneficial. | II | ● |  |  | ü | All REC Parties, Consumers | All REC Parties | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | 2.5% | Planned | 2025-09-01: 2.1, 2.2 ◊; 2025-10-01: 2.3; 2025-11-01: 2.3; 2025-12-01: 2.3; 2026-01-01: 2.4 ◊
3 | Better Cross-Code Integration | To establish better mechanisms for cross-code collaboration whilst managing underperforming Parties. | IV | ● |  |  | ü | RECCo / REC Code Manager, Other Energy Codes | RECCo / REC Code Manager, Other Energy Codes | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | 2.5% | Planned | 2025-11-01: 3.1, 3.2 ◊; 2025-12-01: 3.3; 2026-01-01: 3.3; 2026-02-01: 3.3; 2026-03-01: 3.4 ◊
4 | Assessment of Critical REC Changes (such as R0155) Delivered | To assure whether critical REC Changes have delivered the intended benefits and outcomes. | IV | ●● |  |  | ü | All REC Parties, Consumers | RECCo / REC Code Manager | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | 2.5% | Planned | 2025-10-01: Contigency for data collection to inform scope (if required); 2026-01-01: 4.1, 4.2 ◊; 2026-02-01: 4.3; 2026-03-01: 4.3; 2026-04-01: 4.3; 2026-05-01: 4.4 ◊
Recurring Activities
5 | Qualification / Maintenance of Qualification / Metering accreditation scheme | To ensure REC Parties meet and maintain the necessary standards to operate reliably, compliantly and efficiently within the competitive retail energy market. | II, III | ●● | ü |  |  | Consumers, All REC Parties and Non-Party Service Users | All REC Parties and Non-Party Service Users | Assessment | Quarterly update to PAB | 36% | Planned | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊
6 | Theft Detection Incentive Scheme (TDIS) and associated Theft Target Methodology (TTM) | To ensure TDIS is operated and associated TTM maintained in line with REC requirements. | II | ● | ü |  |  | Consumers, Energy Suppliers | RECCo / REC Code Manager, Energy Suppliers | 1. TTM development 2. TTM consultation and publication 3. TDIS Target publication 4. Analyse final submission for the reporting year 5. TDIS Credits and Debits communication 6. TDIS Reporting | - Publication of TTM - Publication of TDIS Targets - Publication of TDIS Credits and Debits - Periodic updates to PAB | 2% | Planned | 6.1, 6.6 | 6.1, 6.6 | 6.1, 6.2, 6.6 | 6.2, 6.6 | 6.2, 6.6 | 6.2, 6.3, 6.6 ◊ | 6.6 | 6.6 | 6.6 | 6.4, 6.6 | 6.4, 6.6 | 6.5, 6.6 ◊
7 | TDIS Verification | To validate Supplier reporting and provide market confidence on the integrity of the scheme. | II | ● |  |  | ü | Energy Suppliers | Energy Suppliers | Sample-based verification | Paper to PAB | 1% | Planned | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊
8 | Annual Rating – a multi-year PAB priority | To incentivise Parties to prioritise their performance in key areas of the REC through publication of Party ratings. | II | ● |  |  | ü | Consumers, All REC Parties and Non-Party Service Users | Energy Suppliers | 1. Publish approach 2. Develop scoring criteria 3. Consultation and refinement 4. Draft rating publication and query window 5. Finalise and publish annual rating | Public paper to PAB | 2% | Planned | 2026-02-01: 8.1 ◊; 2026-04-01: 8.2 ◊; 2026-05-01: 8.3 ◊; 2026-06-01: 8.3 ◊; 2026-07-01: 8.4 ◊; 2026-08-01: 8.5 ◊
9 | Monthly data review, response and PATs | To monitor health various REC systems and processes whilst also measuring Party performance. | All | ●● | ü |  |  | Consumers, All REC Parties and Non-Party Service Users | All REC Parties | Monthly publication of dashboards | Quarterly update to PAB | 10% | Planned | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊
10 | Recurring data provision | To provide Parties information on their performance as well as the performance of their peers to incentivise improvement. | II | ●● |  |  | ü | Consumer, Energy Suppliers | Energy Suppliers | 1. Erroneous Switch Peer Comparison | Part of Party performance update | 2% | Planned | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊
[8 empty] | Consumer | Energy Suppliers | 2. Smart Meter Installation Survey Peer Comparison | Part of Party performance update |  | Planned | 2025-11-01: 10.2 ◊; 2026-02-01: 10.2 ◊; 2026-05-01: 10.2 ◊; 2026-08-01: 10.2 ◊
11 | Data cleanse | To improve quality of REC data to improve performance of REC processes and reduce | II | ●● |  |  | ü | Consumers, All REC Parties and Non-Party Service Users | Energy Suppliers | 1. Sprint 4 close 2. Sprint 5 planning 3. Sprint 5 start 4. Sprint 5 mid-sprint review 5. Sprint 5 close 6. Sprint 6 planning 7. Sprint 6 start 8. Sprint 6 mid-sprint review | - Sprint proposals - Mid-sprint reviews - Sprint closure update | 3% | Planned | 2025-09-01: 11.1, 11.2 ◊; 2025-10-01: 11.3; 2026-01-01: 11.4 ◊; 2026-03-01: 11.5, 11.6 ◊; 2026-04-01: 11.7; 2026-07-01: 11.8
12 | CDSP reconciliation | To improve quality of Gas Meter Portfolio data. | II | ●● | ü |  |  | Consumers, Suppliers, MEMs | MEMs | 1. CDSP-led activities 2. Code Manager Analysis 3. Reporting to PAB 4. Application of PATs | Paper to PAB | 1% | Planned | 2026-04-01: 12.1; 2026-05-01: 12.1; 2026-06-01: 12.1; 2026-07-01: 12.2, 12.3; 2026-08-01: 12.3, 12.4 ◊
13 | Monitoring of REC Services | To monitor performance of REC Services to build industry trust as well as identify opportunities for intervention early on. | I | ● |  | ü |  | All REC Service Users | All REC Service Providers | REC Service SLA Monitoring | Publication of monthly SLA dashboard Quarterly update to PAB | 4% | Planned | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊
14 | Assessment of accuracy of REC Service reporting | To drive accountability and assure integrity of performance information reported by REC Service Providers. | I | ● |  | ü |  | REC CRS Users | CRS Provider | 1. Assurance of CRS for FY25/26 Q2. 2. Assurance of CRS for FY25/26 Q3. 3. Assurance of CRS for FY25/26 Q4. 4. Assurance of CRS for FY26/27 Q1. | Publication of Final Report (Restricted Distribution) | 7% | Planned |  | 14.1 | 14.1 ◊ |  | 14.2 | 14.2 ◊ |  | 14.3 | 14.3 ◊ |  | 14.4 | 14.4 ◊
[8 empty] | REC EES Users | EES Provider | 5. Annual assurance of EES | Publication of Final Report (Restricted Distribution) |  | Planned | 2026-02-01: 14.5; 2026-03-01: 14.5 ◊
[8 empty] | REC GES Users | GES Provider | 6. Annual assurance of GES | Publication of Final Report (Restricted Distribution) |  | Planned | 2026-03-01: 14.6; 2026-04-01: 14.6 ◊
[8 empty] | REC Parties | REC Code Manager Professional Service Provider | 7. Annual assurance of RPS | Publication of Final Report (Restricted Distribution) |  | Planned | 2026-05-01: 14.7; 2026-06-01: 14.7; 2026-07-01: 14.7 ◊
[8 empty] | REC Parties | REC Code Manager Technical Service Provider | 8. Annual assurance of RTS | Publication of Final Report (Restricted Distribution) |  | Planned | 2026-05-01: 14.8; 2026-06-01: 14.8; 2026-07-01: 14.8 ◊
15 | CRS Performance Charge | To incentivise high performance from CRS. | I | ● | ü |  |  | REC CRS Users | CRS Provider | 1. Quarterly CRS Performance Charge calculation 2. Approval of 2026-27 CRS Performance Charge | Paper to PAB | 1% | Planned | 2025-11-01: 15.1 ◊; 2026-02-01: 15.1 ◊; 2026-03-01: 15.2 ◊; 2026-05-01: 15.1 ◊; 2026-08-01: 15.1 ◊
16 | Maintaining our Framework documents | To maintain the Performance Assurance Framework. | N/A - operational | ● | ü |  |  | Consumers, All REC Parties and Non-Party Service Users | Performance Assurance | 1. Retail Risk Register 2. Performance Assurance Methodology & Techniques 3. Performance Assurance Report Catalogue 4. PAB Procedures 5. REC Entry Assessment documents 6. REC Service User Categorisation | Publication of reviewed PAF product | 1% | Planned | 2025-09-01: 16.1; 2025-10-01: 16.2, 16.3; 2025-11-01: 16.3 ◊; 2026-01-01: 16.5, 16.6; 2026-02-01: 16.5, 16.6; 2026-03-01: 16.5, 16.6 ◊; 2026-06-01: 16.4 ◊
17 | Supporting other RECCo / REC Code Manager initiatives | To support REC arrangements. | IV | ●● |  | ü |  | RECCo / Code Manager | Performance Assurance | 1. Helpdesk service and query management 2. Supporting REC Change Impact Assessment and Solution Development 3. Managing instances of issues and/or non-compliance 4. Supporting RECCo Operations, including with contract management and reporting 5. Committee management 6. Support Code Manager Collaboration | N/A | 20% | Planned | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
Key: |  |  |  |  | Consumer Impacting
[5 empty] | ● | ● | ●
[5 empty] | Low | Medium | High
System / Process Impacting
[5 empty] | ● | ● | ●
[5 empty] | Low | Medium | High
Planned activities
Recurring activities
[5 empty] | ◊ | Output / deliverable due
Externally led activities