## Cover
REC Performance Assurance Operating Plan
2025-08-18
Version 6.0

## Version History
Version | Status | Issue Date | Author | Comments
1.0 | Final | 2021-07-19 | REC Code Manager | N/A
2.0 | Final | 2021-10-18 | REC Code Manager | Updated following Performance Assurance Framework (PAF) product review.
3.0 | Final | 2022-09-20 | REC Code Manager | Updated for Year 2.
3.0 | Final | 2022-11-01 | REC Code Manager | Finalised following consultation.
4.0 | Final | 2023-08-30 | REC Code Manager | Updated for Year 3.
5.0 | Final | 2024-08-27 | REC Code Manager | Updated for Year 4.
6.0 | Final | 2025-08-18 | REC Code Manager | Updated draft for Year 5.

## Operating Plan 2025-26
REC Performance Assurance Operating Plan 2025-26
Ref | Activity | Objective | Intended Outcome / Benefit | Retail Risk Mapping | Indicative Impact | Code Requirement | Contractually Agreed | PAB Determined | Beneficiary Party | Responsible Party | Task | Expected Output | Time Effort Estimate | Status | Schedule
[15 empty] | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01
PAB Deep Dives Focusing on Emerging Risks led by Code Manager
1 | Review of Escalations and SDEP under the REC | To determine effectiveness of escalations and SDEP to efficiently resolve issues faced by consumers. To identify opportunities to reduce the need for escalations through process improvement. | Recurring feedback from REC Parties highlights escalation processes and SDEP are inconsistently used across industry. We currently don’t have good quality information on the effectiveness of these processes. If implemented and operated effectively, it can minimise consumer and market participant detriment by providing swift resolution for processes where escalation is required. Assurance work would provide a measurement of how effective this process is and identify opportunities for improvement. | I, II | ●● |  |  | ü | Energy Suppliers | RECCo / REC Code Manager, Energy Suppliers | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | 2.5% | Planned | 2025-09-01: 1.1, 1.2 ◊; 2025-10-01: Contingency for data provision (if required); 2026-05-01: 1.3; 2026-06-01: 1.3; 2026-07-01: 1.3; 2026-08-01: 1.4 ◊
2 | Driving REC Data Quality Improvements | To refine the data cleanse methodology to ensure it is cost beneficial. | Minimise downstream impact of poor data quality on REC as well as cross-code processes, thus improving both consumer and market participant outcomes. It is also worth noting that since its introduction, data cleanse under the REC and our approach to sprints has been well regarded within the industry as it has helped coordinate and focus participant effort across the industry. We would estimate the expected benefits from data cleanse as part of the scoping of data sprints. | II | ● |  |  | ü | All REC Parties, Consumers | All REC Parties | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | 2.5% | Planned | 2025-09-01: 2.1, 2.2 ◊; 2025-10-01: 2.3; 2025-11-01: 2.3; 2025-12-01: 2.3; 2026-01-01: 2.4 ◊
3 | Better Cross-Code Integration | To establish better mechanisms for cross-code collaboration whilst managing underperforming Parties. | Recent experiences with managing a Party’s performance has demonstrated an urgent need for better cross-code collaboration and integrated Code Manager action. We currently don’t have good quality information on the effectiveness of these processes. We would seek to resolve the identified issues as part of this process. | IV | ● |  |  | ü | RECCo / REC Code Manager, Other Energy Codes | RECCo / REC Code Manager, Other Energy Codes | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | 2.5% | Planned | 2025-11-01: 3.1, 3.2 ◊; 2025-12-01: 3.3; 2026-01-01: 3.3; 2026-02-01: 3.3; 2026-03-01: 3.4 ◊
4 | Assessment of Critical REC Changes (such as R0155) Delivered | To assure whether critical REC Changes have delivered the intended benefits and outcomes. | Recent Change Process reviews indicated challenges identifying, delivering and realising benefits. This would be based on the net benefits derived through the change process to date, focusing on the changes which are complex, highly beneficial or highly important to delivering the REC objectives. This crucially would identify areas where issues have been addressed or further work is needed, for example, the effectiveness of the R0155 solution in resolving challenges associated with non-domestic Change of Occupier objections. Through this review, we aim to give stakeholders confidence that the REC is operating effectively and meetings its objective of achieving sustainable innovation and continuous improvement. | IV | ●● |  |  | ü | All REC Parties, Consumers | RECCo / REC Code Manager | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | 2.5% | Planned | 2025-10-01: Contingency for data collection to inform scope (if required); 2026-01-01: 4.1, 4.2 ◊; 2026-02-01: 4.3; 2026-03-01: 4.3; 2026-04-01: 4.3; 2026-05-01: 4.4 ◊
Recurring Activities led by Code Manager
5 | Qualification / Maintenance of Qualification / Metering accreditation scheme | To ensure REC Parties meet and maintain the necessary standards to operate reliably, compliantly and efficiently within the competitive retail energy market. | Protect the consumer, other market participants and REC data by only approving qualification for organisations capable of meeting their REC obligations. | II, III | ●● | ü |  |  | Consumers, All REC Parties and Non-Party Service Users | All REC Parties and Non-Party Service Users | Assessment | Quarterly update to PAB | 36% | Planned | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊
6 | Theft Detection Incentive Scheme (TDIS) and associated Theft Target Methodology (TTM) | To ensure TDIS is operated and associated TTM maintained in line with REC requirements. | Incentivise Suppliers to take steps to reduce Energy Theft. | II | ● | ü |  |  | Consumers, Energy Suppliers | RECCo / REC Code Manager, Energy Suppliers | 1. TTM development 2. TTM consultation and publication 3. TDIS Target publication 4. Analyse final submission for the reporting year 5. TDIS Credits and Debits communication 6. TDIS Reporting | - Publication of TTM - Publication of TDIS Targets - Publication of TDIS Credits and Debits - Periodic updates to PAB | 2% | Planned | 6.1, 6.6 | 6.1, 6.6 | 6.1, 6.2, 6.6 | 6.2, 6.6 | 6.2, 6.6 | 6.2, 6.3, 6.6 ◊ | 6.6 | 6.6 | 6.6 | 6.4, 6.6 | 6.4, 6.6 | 6.5, 6.6 ◊
7 | TDIS Verification | To validate Supplier reporting and provide market confidence on the integrity of the scheme. | Increase stakeholder confidence in TDIS. | II | ● |  |  | ü | Energy Suppliers | Energy Suppliers | Sample-based verification | Paper to PAB | 1% | Planned | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊
8 | Annual Rating – a multi-year PAB priority | To incentivise Parties to prioritise their performance in key areas of the REC through publication of Party ratings. | Incentivise REC Party to improve their performance, especially in area prioritised by PAB. | II | ● |  |  | ü | Consumers, All REC Parties and Non-Party Service Users | Energy Suppliers | 1. Publish approach 2. Develop scoring criteria 3. Consultation and refinement 4. Draft rating publication and query window 5. Finalise and publish annual rating | Public paper to PAB | 2% | Planned | 2026-02-01: 8.1 ◊; 2026-04-01: 8.2 ◊; 2026-05-01: 8.3 ◊; 2026-06-01: 8.3 ◊; 2026-07-01: 8.4 ◊; 2026-08-01: 8.5 ◊
9 | Monthly data review, response and PATs | To monitor health various REC systems and processes whilst also measuring Party performance. | REC Parties meet the standard expected under the Code, and provide stakeholders confidence that REC processes are operating effectively. | All | ●● | ü |  |  | Consumers, All REC Parties and Non-Party Service Users | All REC Parties | Monthly publication of dashboards | Quarterly update to PAB | 10% | Planned | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊
10 | Recurring data provision | To provide Parties information on their performance as well as the performance of their peers to incentivise improvement. | Incentivise Suppliers to reduce the occurrence of Erroneous Switches. | II | ●● |  |  | ü | Consumer, Energy Suppliers | Energy Suppliers | 1. Erroneous Switch Peer Comparison | Part of Party performance update | 2% | Planned | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊
|  |  | Incentivise Suppliers to improve the quality of service delivered to consumers during Smart Meter Installations. | [5 empty] | Consumer | Energy Suppliers | 2. Smart Meter Installation Survey Peer Comparison | Part of Party performance update |  | Planned | 2025-11-01: 10.2 ◊; 2026-02-01: 10.2 ◊; 2026-05-01: 10.2 ◊; 2026-08-01: 10.2 ◊
11 | Data cleanse | To improve quality of REC data to improve performance of REC processes and reduce | Reduce downstream impacts of poor quality data on consumers and/or market participants. | II | ●● |  |  | ü | Consumers, All REC Parties and Non-Party Service Users | Energy Suppliers | 1. Sprint 4 close 2. Sprint 5 planning 3. Sprint 5 start 4. Sprint 5 mid-sprint review 5. Sprint 5 close 6. Sprint 6 planning 7. Sprint 6 start 8. Sprint 6 mid-sprint review | - Sprint proposals - Mid-sprint reviews - Sprint closure update | 3% | Planned | 2025-09-01: 11.1, 11.2 ◊; 2025-10-01: 11.3; 2026-01-01: 11.4 ◊; 2026-03-01: 11.5, 11.6 ◊; 2026-04-01: 11.7; 2026-07-01: 11.8
12 | CDSP reconciliation | To improve quality of Gas Meter Portfolio data. | Reduce downstream impacts of poor quality data on consumers and/or market participants. | II | ●● | ü |  |  | Consumers, Suppliers, MEMs | MEMs | 1. CDSP-led activities 2. Code Manager Analysis 3. Reporting to PAB 4. Application of PATs | Paper to PAB | 1% | Planned | 2026-04-01: 12.1; 2026-05-01: 12.1; 2026-06-01: 12.1; 2026-07-01: 12.2, 12.3; 2026-08-01: 12.3, 12.4 ◊
13 | Monitoring of REC Services | To monitor performance of REC Services to build industry trust as well as identify opportunities for intervention early on. | REC Services meet the standard expected under the Code, and provide REC Service Users confidence in the level of service they receive. | I | ● |  | ü |  | All REC Service Users | All REC Service Providers | REC Service SLA Monitoring | Publication of monthly SLA dashboard Quarterly update to PAB | 4% | Planned | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊
14 | Assessment of accuracy of REC Service reporting | To drive accountability and assure integrity of performance information reported by REC Service Providers. | Data reported by Service Providers on their performance against key REC obligations is verified. | I | ● |  | ü |  | REC CRS Users | CRS Provider | 1. Assurance of CRS for FY25/26 Q2. 2. Assurance of CRS for FY25/26 Q3. 3. Assurance of CRS for FY25/26 Q4. 4. Assurance of CRS for FY26/27 Q1. | Publication of Final Report (Restricted Distribution) | 7% | Planned |  | 14.1 | 14.1 ◊ |  | 14.2 | 14.2 ◊ |  | 14.3 | 14.3 ◊ |  | 14.4 | 14.4 ◊
[9 empty] | REC EES Users | EES Provider | 5. Annual assurance of EES | Publication of Final Report (Restricted Distribution) |  | Planned | 2026-02-01: 14.5; 2026-03-01: 14.5 ◊
[9 empty] | REC GES Users | GES Provider | 6. Annual assurance of GES | Publication of Final Report (Restricted Distribution) |  | Planned | 2026-03-01: 14.6; 2026-04-01: 14.6 ◊
[9 empty] | REC Parties | REC Code Manager Professional Service Provider | 7. Annual assurance of RPS | Publication of Final Report (Restricted Distribution) |  | Planned | 2026-05-01: 14.7; 2026-06-01: 14.7; 2026-07-01: 14.7 ◊
[9 empty] | REC Parties | REC Code Manager Technical Service Provider | 8. Annual assurance of RTS | Publication of Final Report (Restricted Distribution) |  | Planned | 2026-05-01: 14.8; 2026-06-01: 14.8; 2026-07-01: 14.8 ◊
15 | CRS Performance Charge | To incentivise high performance from CRS. | Provide incentives for the CRS provider to provide a high quality service. | I | ● | ü |  |  | REC CRS Users | CRS Provider | 1. Quarterly CRS Performance Charge calculation 2. Approval of 2026-27 CRS Performance Charge | Paper to PAB | 1% | Planned | 2025-11-01: 15.1 ◊; 2026-02-01: 15.1 ◊; 2026-03-01: 15.2 ◊; 2026-05-01: 15.1 ◊; 2026-08-01: 15.1 ◊
16 | Maintaining our Framework documents | To maintain the Performance Assurance Framework (PAF). | The PAF remains up to date and Parties have access to the latest information on the PAF. | N/A - operational | ● | ü |  |  | Consumers, All REC Parties and Non-Party Service Users | Performance Assurance | 1. Retail Risk Register 2. Performance Assurance Methodology & Techniques 3. Performance Assurance Report Catalogue 4. PAB Procedures 5. REC Entry Assessment documents 6. REC Service User Categorisation | Publication of reviewed PAF product | 1% | Planned | 2025-09-01: 16.1; 2025-10-01: 16.2, 16.3; 2025-11-01: 16.3 ◊; 2026-01-01: 16.5, 16.6; 2026-02-01: 16.5, 16.6; 2026-03-01: 16.5, 16.6 ◊; 2026-06-01: 16.4 ◊
17 | Supporting other RECCo / REC Code Manager initiatives | To support REC arrangements. | Parties receive a seamless experience when interacting with the REC. | IV | ●● |  | ü |  | RECCo / Code Manager | Performance Assurance | 1. Helpdesk service and query management 2. Supporting REC Change Impact Assessment and Solution Development 3. Managing instances of issues and/or non-compliance 4. Supporting RECCo Operations, including with contract management and reporting 5. Committee management 6. Support Code Manager Collaboration | N/A | 20% | Planned | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
Other reporting to PAB led by RECCo [Schedule to be agreed with RECCo]
18 | REC Service Security – confirming key security activities are taking place | To ensure REC Services are secure and meet the standard expected within the Code. | Build stakeholder confidence whilst identifying opportunities for improvement, if any. | I, III | ●● |  |  | ü | All REC Service Users | RECCo, DCC/ C&C / Xoserve/ Code Manager Service Providers | Semi-annual update to PAB | Paper to PAB | - | Planned | bar: 2026-02-01; 2026-08-01
19 | IT capacity and performance management for REC Services – assessing how capacity requirements are identified and services planned for | To ensure REC Services are adequately planned for. | Build stakeholder confidence whilst identifying opportunities for improvement, if any. | I | ● |  |  | ü | All REC Service Users | RECCo, DCC/ C&C / Xoserve/ Code Manager Service Providers | Semi-annual update to PAB | Paper to PAB | - | Planned | bar: 2025-11-01; 2026-05-01
20 | CRS Improvement Plan – are benefits being realised? | To review progress against the CRS Improvement Plan and its effectiveness in addressing challenges. | Build stakeholder confidence whilst identifying opportunities for improvement, if any. | I, IV | ●● |  |  | ü | All REC Service Users | RECCo, DCC | Quarterly update to PAB, frequency to be reviewed based on PAB requirement | Paper to PAB | - | Planned | bar: 2025-10-01; 2026-01-01; 2026-04-01; 2026-07-01
21 | Incident and Problem Management Deep Dive | To prioritise resolution and ensure REC Services evolve and introduce mechanisms to prevent reoccurrence. | Build stakeholder confidence whilst identifying opportunities for improvement, if any. | I, IV | ●● |  |  | ü | All REC Service Users | RECCo, DCC/ C&C / Xoserve/ Code Manager Service Providers | Ad-hoc, event-driven update to PAB | Paper to PAB, if required. | - | Planned | 2025-09-01: As required
22 | Project to improve switching objection processes – to enhance consumer clarity earlier in the journey. | To track progress made against PAB's recommendation within the Annual Report, accepted by RECCo Board. | Promote continuous improvement. | IV | ●● |  |  | ü | Suppliers, Consumers | Suppliers, RECCo, Code Manager | Covered as part of activity 4 above | - | - | Planned | 2025-09-01: Covered as part of activity 4 above
23 | Strategic focus on digitalisation of meter data – aligned with REC changes and major industry programmes. | To track progress made against PAB's recommendation within the Annual Report, accepted by RECCo Board. | Promote continuous improvement. | IV | ●● |  |  | ü | All REC Parties, Consumers | RECCo, Code Manager | Annual update to PAB | Paper to PAB | - | Planned | bar: 2026-01-01
24 | Use consumer data (I0189) to inform the Forward Work Plan and assess the impact of initiatives. | To track progress made against PAB's recommendation within the Annual Report, accepted by RECCo Board. | Promote continuous improvement. | IV | ●● |  |  | ü | Consumer | RECCo, Code Manager | Annual update to PAB | Paper to PAB | - | Planned | bar: 2026-01-01
25 | Mechanism to respond to complex consumer issues outside the formal FWP structure. | To track progress made against PAB's recommendation within the Annual Report, accepted by RECCo Board. | Promote continuous improvement. | IV | ●● |  |  | ü | Consumer | RECCo, Code Manager | Annual update to PAB | Paper to PAB | - | Planned | bar: 2026-01-01
26 | Leverage Digital Services rollout to improve assurance and market participant experiences. | To track progress made against PAB's recommendation within the Annual Report, accepted by RECCo Board. | Promote continuous improvement. | IV | ● |  |  | ü | All REC Parties | RECCo, Code Manager | Annual update to PAB | Paper to PAB | - | Planned | bar: 2026-01-01
Key: | [5 empty] | Consumer Impacting
[6 empty] | ● | ● | ●
[6 empty] | Low | Medium | High
System / Process Impacting
[6 empty] | ● | ● | ●
[6 empty] | Low | Medium | High
Planned activities
Recurring activities
[6 empty] | ◊ | Output / deliverable due
Externally led activities