## Operating Plan 2025-26
REC Performance Assurance Operating Plan 2025-26
Ref | Activity | Task | Expected Output | Status | Schedule
[5 empty] | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | Updates
PAB Deep Dives Focusing on Emerging Risks led by Code Manager
1 | Review of Escalations and SDEP under the REC | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | Delivery in-progress | 2025-09-01: 1.1, 1.2 ◊; 2025-10-01: Contingency for data provision (if required); 2026-05-01: 1.3; 2026-06-01: 1.3; 2026-07-01: 1.3; 2026-08-01: 1.4 ◊ | October PAB: RPA prepared a proposed scope and discussed this at the PA Webinar on 09 Oct with Parties. A more comprehensive update is provided in RECPAB_25_1028_13.
2 | Driving REC Data Quality Improvements | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | Delivery in-progress | 2025-09-01: 2.1, 2.2 ◊; 2025-10-01: 2.3; 2025-11-01: 2.3; 2025-12-01: 2.3; 2026-01-01: 2.4 ◊ | October PAB: RPA presented a proposed scope to the PAB last month in RECPAB_25_0930_03. This proposed scope and methodology were discussed at the PA Webiar on 09 Oct.. Next steps: RPA to prepare a breakdown into sub activities to track Sprint 6. This assessment needs to be complete before May 2026 (expected date for Sprint 6 kick-off).
3 | Better Cross-Code Integration | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | Planned | 2025-11-01: 3.1, 3.2 ◊; 2025-12-01: 3.3; 2026-01-01: 3.3; 2026-02-01: 3.3; 2026-03-01: 3.4 ◊ | October PAB: Discussion planned at the Code Manager Collaboration session in October before we kick off the work. 1:1 will be arranged with BSC, SEC, UNC PAB Representatives in November. An update and input session for REC stakeholders is planned at the December PA webinar.
4 | Assessment of Critical REC Changes (such as R0155) Delivered | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | Planned | 2025-10-01: Contingency for data collection to inform scope (if required); 2026-01-01: 4.1, 4.2 ◊; 2026-02-01: 4.3; 2026-03-01: 4.3; 2026-04-01: 4.3; 2026-05-01: 4.4 ◊
Recurring Activities led by Code Manager
5 | Qualification / Maintenance of Qualification / Metering accreditation scheme | Assessment | Quarterly update to PAB | Delivery in-progress | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊
6 | Theft Detection Incentive Scheme (TDIS) and associated Theft Target Methodology (TTM) | 1. TTM development 2. TTM consultation and publication 3. TDIS Target publication 4. Analyse final submission for the reporting year 5. TDIS Credits and Debits communication 6. TDIS Reporting | - Publication of TTM - Publication of TDIS Targets - Publication of TDIS Credits and Debits - Periodic updates to PAB | Delivery in-progress | 6.1, 6.6 | 6.1, 6.6 | 6.1, 6.2, 6.6 | 6.2, 6.6 | 6.2, 6.6 | 6.2, 6.3, 6.6 ◊ | 6.6 | 6.6 | 6.6 | 6.4, 6.6 | 6.4, 6.6 | 6.5, 6.6 ◊ | October PAB: No information request being proposed this year, so we will proceed to consultation. Discussion underway with RECCo to agree resources.
7 | TDIS Verification | Sample-based verification | Paper to PAB | Scoping in-progress | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊ | October PAB: An update was provided to Parties at the PA Webinar in October.
8 | Annual Rating – a multi-year PAB priority | 1. Publish approach 2. Develop scoring criteria 3. Consultation and refinement 4. Draft rating publication and query window 5. Finalise and publish annual rating | Public paper to PAB | Planned | 2026-02-01: 8.1 ◊; 2026-04-01: 8.2 ◊; 2026-05-01: 8.3 ◊; 2026-06-01: 8.3 ◊; 2026-07-01: 8.4 ◊; 2026-08-01: 8.5 ◊
9 | Monthly data review, response and PATs | Monthly publication of dashboards | Quarterly update to PAB | Delivery in-progress | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊
10 | Recurring data provision | 1. Erroneous Switch Peer Comparison | Part of Party performance update | Delivery in-progress | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊
|  | 2. Smart Meter Installation Survey Peer Comparison | Part of Party performance update | Planned | 2025-11-01: 10.2 ◊; 2026-02-01: 10.2 ◊; 2026-05-01: 10.2 ◊; 2026-08-01: 10.2 ◊
11 | Data cleanse | 1. Sprint 4 close 2. Sprint 5 planning 3. Sprint 5 start 4. Sprint 5 mid-sprint review 5. Sprint 5 close 6. Sprint 6 planning 7. Sprint 6 start 8. Sprint 6 mid-sprint review | - Sprint proposals - Mid-sprint reviews - Sprint closure update | Delivery in-progress | 2025-09-01: 11.1 ◊; 2025-10-01: 11.2; 2025-11-01: 11.3; 2026-01-01: 11.4 ◊; 2026-03-01: 11.5, 11.6 ◊; 2026-04-01: 11.7; 2026-07-01: 11.8 | October PAB: Sprint 5 proposal is contained in RECPAB_25_1028_10 for PAB approval based on PA webinar and RIG feedback.
12 | CDSP reconciliation | 1. CDSP-led activities 2. Code Manager Analysis 3. Reporting to PAB 4. Application of PATs | Paper to PAB | Planned | 2026-04-01: 12.1; 2026-05-01: 12.1; 2026-06-01: 12.1; 2026-07-01: 12.2, 12.3; 2026-08-01: 12.3, 12.4 ◊
13 | Monitoring of REC Services | REC Service SLA Monitoring | Publication of monthly SLA dashboard Quarterly update to PAB | Planned | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊
14 | Assessment of accuracy of REC Service reporting | 1. Assurance of CRS for FY25/26 Q2. 2. Assurance of CRS for FY25/26 Q3. 3. Assurance of CRS for FY25/26 Q4. 4. Assurance of CRS for FY26/27 Q1. | Publication of Final Report (Restricted Distribution) | Planned |  | 14.1 | 14.1 ◊ |  | 14.2 | 14.2 ◊ |  | 14.3 | 14.3 ◊ |  | 14.4 | 14.4 ◊ | October PAB: Information Request for Q2 assurance has been sent to the Service Provider.
|  | 5. Annual assurance of EES | Publication of Final Report (Restricted Distribution) | Planned | 2026-02-01: 14.5; 2026-03-01: 14.5 ◊
|  | 6. Annual assurance of GES | Publication of Final Report (Restricted Distribution) | Planned | 2026-03-01: 14.6; 2026-04-01: 14.6 ◊
|  | 7. Annual assurance of RPS | Publication of Final Report (Restricted Distribution) | Planned | 2026-05-01: 14.7; 2026-06-01: 14.7; 2026-07-01: 14.7 ◊
|  | 8. Annual assurance of RTS | Publication of Final Report (Restricted Distribution) | Planned | 2026-05-01: 14.8; 2026-06-01: 14.8; 2026-07-01: 14.8 ◊
15 | CRS Performance Charge | 1. Quarterly CRS Performance Charge calculation 2. Approval of 2026-27 CRS Performance Charge | Paper to PAB | Planned | 2025-11-01: 15.1 ◊; 2026-02-01: 15.1 ◊; 2026-03-01: 15.2 ◊; 2026-05-01: 15.1 ◊; 2026-08-01: 15.1 ◊
16 | Maintaining our Framework documents | 1. Retail Risk Register 2. Performance Assurance Methodology & Techniques 3. Performance Assurance Report Catalogue 4. PAB Procedures 5. REC Entry Assessment documents 6. REC Service User Categorisation | Publication of reviewed PAF product | Delivery in-progress | 2025-09-01: 16.1; 2025-10-01: 16.2, 16.3; 2025-11-01: 16.3 ◊; 2026-01-01: 16.5, 16.6; 2026-02-01: 16.5, 16.6; 2026-03-01: 16.5, 16.6 ◊; 2026-06-01: 16.4 ◊ | October PAB: Updated Risk Register is contained within RECPAB_1028_12A for PAB approval. PAM&T review is ongoing, and is contained within RECPAB_25_1028_12C and 12D for PAB approval. The PARC review has been kicked off, however, please note that the PARC has been through several iterations during the year and therefore, no major changes are expected.
17 | Supporting other RECCo / REC Code Manager initiatives | 1. Helpdesk service and query management 2. Supporting REC Change Impact Assessment and Solution Development 3. Managing instances of issues and/or non-compliance 4. Supporting RECCo Operations, including with contract management and reporting 5. Committee management 6. Support Code Manager Collaboration | N/A | Delivery in-progress | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
Other reporting to PAB led by RECCo
18 | REC Service Security – confirming key security activities are taking place | Semi-annual update to PAB | Paper to PAB | Planned | bar: 2026-02-01; 2026-08-01
19 | IT capacity and performance management for REC Services – assessing how capacity requirements are identified and services planned for | Semi-annual update to PAB | Paper to PAB | Planned | bar: 2025-11-01; 2026-05-01
20 | CRS Improvement Plan – are benefits being realised? | Quarterly update to PAB, frequency to be reviewed based on PAB requirement | Paper to PAB | Planned | [12 empty] | October PAB: RECCo and DCC presented at Sep PAB. DCC are presenting a further update following the re-baselining exercise as requested by the PAB and is contained within RECPAB_25_1028_05. | bar: 2025-10-01; 2026-01-01; 2026-04-01; 2026-07-01
21 | Incident and Problem Management Deep Dive | Ad-hoc, event-driven update to PAB | Paper to PAB, if required. | Planned | 2025-09-01: As required | October PAB: RECCo are presented to the PAB on GES latency issues (RECPAB_25_1028_04).
22 | Project to improve switching objection processes – to enhance consumer clarity earlier in the journey. | Covered as part of activity 4 above | - | Planned | 2025-09-01: Covered as part of activity 4 above
23 | Strategic focus on digitalisation of meter data – aligned with REC changes and major industry programmes. | Annual update to PAB | Paper to PAB | Planned | bar: 2026-01-01
24 | Use consumer data (I0189) to inform the Forward Work Plan and assess the impact of initiatives. | Annual update to PAB | Paper to PAB | Planned | bar: 2026-01-01
25 | Mechanism to respond to complex consumer issues outside the formal FWP structure. | Annual update to PAB | Paper to PAB | Planned | bar: 2026-01-01
26 | Leverage Digital Services rollout to improve assurance and market participant experiences. | Annual update to PAB | Paper to PAB | Planned | bar: 2026-01-01
Key: |  | Planned activities
Recurring activities
| ◊ | Output / deliverable due
Externally led activities
Completed activities