## Operating Plan 2025-26
REC Performance Assurance Operating Plan 2025-26
Ref | Activity | Task | Expected Output | Status | Schedule
[5 empty] | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | Updates
PAB Deep Dives Focusing on Emerging Risks led by Code Manager
1 | Review of Escalations and SDEP under the REC | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | Delivery in-progress | 2025-09-01: 1.1, 1.2 ◊; 2025-10-01: Contingency for data provision (if required); 2026-05-01: 1.3; 2026-06-01: 1.3; 2026-07-01: 1.3; 2026-08-01: 1.4 ◊ | [26/05/2026] Review now underway.
2 | Driving REC Data Quality Improvements | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | Delivery in-progress | 2025-09-01: 2.1, 2.2 ◊; 2025-10-01: 2.3; 2025-11-01: 2.3; 2025-12-01: 2.3; 2026-01-01: 2.3; 2026-02-01: 2.4 ◊ | [26/05/2026] At the April PAB two actions were taken: (1) RPA to raise a REC issue around meter data quality, (2) RPA to bring an updated strategy on MTD inconsistencies to PAB.
3 | Better Cross-Code Integration | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | Planned | 2025-11-01: 3.1, 3.2 ◊; 2025-12-01: 3.3; 2026-01-01: 3.3; 2026-02-01: 3.4 ◊ | [26/05/2026] RPA attended UNC, SEC and BSC PABs. Next step is for Code Bodies to be consulted on the next PAOP.
4 | Assessment of Critical REC Changes (such as R0155) Delivered | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | Planned | 2025-10-01: Contingency for data collection to inform scope (if required); 2026-01-01: 4.1, 4.2 ◊; 2026-02-01: 4.3; 2026-03-01: 4.3; 2026-04-01: 4.3; 2026-05-01: 4.4 ◊ | [26/05/2026] An interim update will be provided at May PAB, including plans to drive further participation. Final recommendations will taken to June PAB.
Recurring Activities led by Code Manager
5 | Qualification / Maintenance of Qualification / Metering accreditation scheme | Assessment | Quarterly update to PAB | Delivery in-progress | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊
6 | Theft Detection Incentive Scheme (TDIS) and associated Theft Target Methodology (TTM) | 1. TTM development 2. TTM consultation and publication 3. TDIS Target publication 4. Analyse final submission for the reporting year 5. TDIS Credits and Debits communication 6. TDIS Reporting | - Publication of TTM - Publication of TDIS Targets - Publication of TDIS Credits and Debits - Periodic updates to PAB | Delivery in-progress | 6.1, 6.6 | 6.1, 6.6 | 6.1, 6.2, 6.6 | 6.2, 6.6 | 6.2, 6.6 | 6.2, 6.3, 6.6 ◊ | 6.6 | 6.6 | 6.6 | 6.4, 6.6 | 6.4, 6.6 | 6.5, 6.6 ◊ | [26/05/2026] Summary of key outcomes of TDIS Scheme 25/26 being taken to May PAB.
7 | TDIS Verification | Sample-based verification | Paper to PAB | Scoping in-progress | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊ | [26/05/2026] All TDIS verification evidence received and being reviewed. Interim update to be taken to May PAB and final update including lessons learned will be taken to June PAB.
8 | Annual Rating – a multi-year PAB priority | 1. Publish approach 2. Develop scoring criteria 3. Consultation and refinement 4. Draft rating publication and query window 5. Finalise and publish annual rating | Public paper to PAB | Planned | 2026-02-01: 8.1 ◊; 2026-04-01: 8.2 ◊; 2026-05-01: 8.3 ◊; 2026-06-01: 8.3 ◊; 2026-07-01: 8.4 ◊; 2026-08-01: 8.5 ◊ | [26/05/2026] PAB approved methodology at April PAB. Now these have been approved, RPA will apply draft methodology to Parties.
9 | Monthly data review, response and PATs | Monthly publication of dashboards | Quarterly update to PAB | Delivery in-progress | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊
10 | Recurring data provision | 1. Erroneous Switch Peer Comparison | Part of Party performance update | Delivery in-progress | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊
|  | 2. Smart Meter Installation Survey Peer Comparison | Part of Party performance update | Planned | 2025-11-01: 10.2 ◊; 2026-02-01: 10.2 ◊; 2026-05-01: 10.2 ◊; 2026-08-01: 10.2 ◊
11 | Data cleanse | 1. Sprint 4 close 2. Sprint 5 planning 3. Sprint 5 start 4. Sprint 5 mid-sprint review 5. Sprint 5 close 6. Sprint 6 planning 7. Sprint 6 start 8. Sprint 6 mid-sprint review | - Sprint proposals - Mid-sprint reviews - Sprint closure update | Delivery in-progress | 2025-09-01: 11.1 ◊; 2025-10-01: 11.2; 2025-11-01: 11.3; 2026-02-01: 11.4 ◊; 2026-05-01: 11.5, 11.6 ◊; 2026-06-01: 11.7; 2026-07-01: 11.8 | [26/05/2026] Sprint 6 now completed and an update to be provided at May PAB.
12 | CDSP reconciliation | 1. CDSP-led activities 2. Code Manager Analysis 3. Reporting to PAB 4. Application of PATs | Paper to PAB | Planned | 2026-04-01: 12.1; 2026-05-01: 12.1; 2026-06-01: 12.1; 2026-07-01: 12.2, 12.3; 2026-08-01: 12.3, 12.4 ◊
13 | Monitoring of REC Services | REC Service SLA Monitoring | Publication of monthly SLA dashboard Quarterly update to PAB | Planned | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊
14 | Assessment of accuracy of REC Service reporting | 1. Assurance of CRS for FY25/26 Q2. 2. Assurance of CRS for FY25/26 Q3. 3. Assurance of CRS for FY25/26 Q4. 4. Assurance of CRS for FY26/27 Q1. | Publication of Final Report (Restricted Distribution) | Planned |  | 14.1 | 14.1 | 14.1 ◊ | 14.2 | 14.2 | 14.2 ◊ | 14.3 | 14.3 ◊ |  | 14.4 | 14.4 ◊ | [26/05/2026] Fieldwork underway for Q4 assurance and Service Provider will be contacted w/c 18 May for follow-up questions.
|  | 5. Annual assurance of EES | Publication of Final Report (Restricted Distribution) | Planned | 2026-01-01: 14.5; 2026-02-01: 14.5; 2026-03-01: 14.5 ◊ | [26/05/2026] Report has been approved by the Service Provider and shared with RECCo.
|  | 6. Annual assurance of GES | Publication of Final Report (Restricted Distribution) | Planned | 2026-03-01: 14.6; 2026-04-01: 14.6 ◊ | [26/05/2026] Report has been shared with the Service Provider for approval and then will be shared with RECCo.
|  | 7. Annual assurance of RPS | Publication of Final Report (Restricted Distribution) | Planned | 2026-05-01: 14.7; 2026-06-01: 14.7; 2026-07-01: 14.7 ◊ | [26/05/2026] Initial evidence request shared with the service provider.
|  | 8. Annual assurance of RTS | Publication of Final Report (Restricted Distribution) | Planned | 2026-05-01: 14.8; 2026-06-01: 14.8; 2026-07-01: 14.8 ◊ | [26/05/2026] Initial evidence request shared with the service provider.
15 | CRS Performance Charge | 1. Quarterly CRS Performance Charge calculation 2. Approval of 2026-27 CRS Performance Charge | Paper to PAB | Planned | 2025-11-01: 15.1 ◊; 2026-02-01: 15.1 ◊; 2026-03-01: 15.2 ◊; 2026-05-01: 15.1 ◊; 2026-08-01: 15.1 ◊ | [26/05/2026] Final CRS Performance Charge paper drafted and will be discussed at the May PAB.
16 | Maintaining our Framework documents | 1. Retail Risk Register 2. Performance Assurance Methodology & Techniques 3. Performance Assurance Report Catalogue 4. PAB Procedures 5. REC Entry Assessment documents 6. REC Service User Categorisation | Publication of reviewed PAF product | Delivery in-progress | 2025-09-01: 16.1; 2025-10-01: 16.2, 16.3; 2025-11-01: 16.3, 16.5 ◊; 2026-01-01: 16.6; 2026-02-01: 16.6 ◊; 2026-06-01: 16.4 ◊ | [26/05/2026] RPA currently in the process of developing updates to REC Service Categorisation document and PAB Terms of Reference. The other PAF Products (Risk Register, PATs, PAOP) are currently being updated by RECCo inline with IPAS project and will be coming to a future PAB.
17 | Supporting other RECCo / REC Code Manager initiatives | 1. Helpdesk service and query management 2. Supporting REC Change Impact Assessment and Solution Development 3. Managing instances of issues and/or non-compliance 4. Supporting RECCo Operations, including with contract management and reporting 5. Committee management 6. Support Code Manager Collaboration | N/A | Delivery in-progress | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
Other reporting to PAB led by RECCo
18 | REC Service Security – confirming key security activities are taking place | Semi-annual update to PAB | Paper to PAB | Planned | bar: 2026-02-01; 2026-08-01
19 | IT capacity and performance management for REC Services – assessing how capacity requirements are identified and services planned for | Semi-annual update to PAB | Paper to PAB | Planned | bar: 2025-11-01; 2026-08-01
20 | CRS Improvement Plan – are benefits being realised? | Quarterly update to PAB, frequency to be reviewed based on PAB requirement | Paper to PAB | Planned | bar: 2025-10-01; 2026-01-01; 2026-04-01; 2026-07-01
21 | Incident and Problem Management Deep Dive | Ad-hoc, event-driven update to PAB | Paper to PAB, if required. | Planned | 2025-09-01: As required
22 | Project to improve switching objection processes – to enhance consumer clarity earlier in the journey. | Covered as part of activity 4 above | - | Planned | 2025-09-01: Covered as part of activity 4 above
23 | Strategic focus on digitalisation of meter data – aligned with REC changes and major industry programmes. | Annual update to PAB | Paper to PAB | Planned | bar: 2026-01-01
24 | Use consumer data (I0189) to inform the Forward Work Plan and assess the impact of initiatives. | Annual update to PAB | Paper to PAB | Planned | bar: 2026-01-01
25 | Mechanism to respond to complex consumer issues outside the formal FWP structure. | Annual update to PAB | Paper to PAB | Planned | bar: 2026-01-01
26 | Leverage Digital Services rollout to improve assurance and market participant experiences. | Annual update to PAB | Paper to PAB | Planned | bar: 2026-01-01
Key: |  | Planned activities
Recurring activities
| ◊ | Output / deliverable due
Externally led activities
Completed activities