## Operating Plan 2025-26
REC Performance Assurance Operating Plan 2025-26
Ref | Activity | Task | Expected Output | Status | Schedule
[5 empty] | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | Updates
PAB Deep Dives Focusing on Emerging Risks led by Code Manager
1 | Review of Escalations and SDEP under the REC | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | Delivery in-progress | 2025-09-01: 1.1, 1.2 ◊; 2025-10-01: Contingency for data provision (if required); 2026-05-01: 1.3; 2026-06-01: 1.3; 2026-07-01: 1.3; 2026-08-01: 1.4 ◊ | [14/08/2026] Is being concluded as part of August PAB.
2 | Driving REC Data Quality Improvements | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | Delivery in-progress | 2025-09-01: 2.1, 2.2 ◊; 2025-10-01: 2.3; 2025-11-01: 2.3; 2025-12-01: 2.3; 2026-01-01: 2.3; 2026-02-01: 2.4 ◊ | [14/08/2026] Activities handed over to RECCo as part of future PA Strategy.
3 | Better Cross-Code Integration | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | Planned | 2025-11-01: 3.1, 3.2 ◊; 2025-12-01: 3.3; 2026-01-01: 3.3; 2026-02-01: 3.4 ◊
4 | Assessment of Critical REC Changes Delivered (such as R0155) | 1. Identify Beneficiary and Responsible Party representatives to participate in this review. 2. Define the scope of this review. 3. Conduct review. 4. Publish report with findings and recommendations. | - Publication of Scope - Publication of Final Report | Planned | 2025-10-01: Contingency for data collection to inform scope (if required); 2026-01-01: 4.1, 4.2 ◊; 2026-02-01: 4.3; 2026-03-01: 4.3; 2026-04-01: 4.3; 2026-05-01: 4.4 ◊
Recurring Activities led by Code Manager
5 | Qualification / Maintenance of Qualification / Metering accreditation scheme | Assessment | Quarterly update to PAB | Delivery in-progress | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊ | 5 | 5 | 5 ◊
6 | Theft Detection Incentive Scheme (TDIS) and associated Theft Target Methodology (TTM) | 1. TTM development 2. TTM consultation and publication 3. TDIS Target publication 4. Analyse final submission for the reporting year 5. TDIS Credits and Debits communication 6. TDIS Reporting | - Publication of TTM - Publication of TDIS Targets - Publication of TDIS Credits and Debits - Periodic updates to PAB | Delivery in-progress | 6.1, 6.6 | 6.1, 6.6 | 6.1, 6.2, 6.6 | 6.2, 6.6 | 6.2, 6.6 | 6.2, 6.3, 6.6 ◊ | 6.6 | 6.6 | 6.6 | 6.4, 6.6 | 6.4, 6.6 | 6.5, 6.6 ◊ | [14/08/2026] Complete, see RECPAB_26_0825_08 – Party Assurance Update.
7 | TDIS Verification | Sample-based verification | Paper to PAB | Scoping in-progress | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊ | 7 | 7 | 7 ◊ | [14/08/2026] Complete, see RECPAB_26_0825_08 – Party Assurance Update.
8 | Annual Rating – a multi-year PAB priority | 1. Publish approach 2. Develop scoring criteria 3. Consultation and refinement 4. Draft rating publication and query window 5. Finalise and publish annual rating | Public paper to PAB | Planned | 2026-02-01: 8.1 ◊; 2026-04-01: 8.2 ◊; 2026-05-01: 8.3 ◊; 2026-06-01: 8.3 ◊; 2026-07-01: 8.4 ◊; 2026-08-01: 8.5 ◊ | [14/08/2026] Draft ratings have been published, and responding to Party queries. Final ratings on track to be published later this month.
9 | Monthly data review, response and PATs | Monthly publication of dashboards | Quarterly update to PAB | Delivery in-progress | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊ | 9 | 9 | 9 ◊
10 | Recurring data provision | 1. Erroneous Switch Peer Comparison | Part of Party performance update | Delivery in-progress | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊ | 10.1 | 10.1 | 10.1 ◊
|  | 2. Smart Meter Installation Survey Peer Comparison | Part of Party performance update | Planned | 2025-11-01: 10.2 ◊; 2026-02-01: 10.2 ◊; 2026-05-01: 10.2 ◊; 2026-08-01: 10.2 ◊
11 | Data cleanse | 1. Sprint 4 close 2. Sprint 5 planning 3. Sprint 5 start 4. Sprint 5 mid-sprint review 5. Sprint 5 close 6. Sprint 6 planning 7. Sprint 6 start 8. Sprint 6 mid-sprint review | - Sprint proposals - Mid-sprint reviews - Sprint closure update | Delivery in-progress | 2025-09-01: 11.1 ◊; 2025-10-01: 11.2; 2025-11-01: 11.3; 2026-02-01: 11.4 ◊; 2026-05-01: 11.5, 11.6 ◊; 2026-06-01: 11.7; 2026-07-01: 11.8
12 | CDSP reconciliation | 1. CDSP-led activities 2. Code Manager Analysis 3. Reporting to PAB 4. Application of PATs | Paper to PAB | Planned | 2026-04-01: 12.1; 2026-05-01: 12.1; 2026-06-01: 12.1; 2026-07-01: 12.2, 12.3; 2026-08-01: 12.3, 12.4 ◊
13 | Monitoring of REC Services | REC Service SLA Monitoring | Publication of monthly SLA dashboard Quarterly update to PAB | Planned | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊ | 13 | 13 | 13 ◊
14 | Assessment of accuracy of REC Service reporting | 1. Assurance of CRS for FY25/26 Q2. 2. Assurance of CRS for FY25/26 Q3. 3. Assurance of CRS for FY25/26 Q4. 4. Assurance of CRS for FY26/27 Q1. | Publication of Final Report (Restricted Distribution) | Planned |  | 14.1 | 14.1 | 14.1 ◊ | 14.2 | 14.2 | 14.2 ◊ | 14.3 | 14.3 ◊ |  | 14.4 | 14.4 ◊ | [14/08/2026] Report has been shared with the Service Provider for approval and then will be shared with RECCo.
|  | 5. Annual assurance of EES | Publication of Final Report (Restricted Distribution) | Planned | 2026-01-01: 14.5; 2026-02-01: 14.5; 2026-03-01: 14.5 ◊
|  | 6. Annual assurance of GES | Publication of Final Report (Restricted Distribution) | Planned | 2026-03-01: 14.6; 2026-04-01: 14.6 ◊
|  | 7. Annual assurance of RPS | Publication of Final Report (Restricted Distribution) | Planned | 2026-05-01: 14.7; 2026-06-01: 14.7; 2026-07-01: 14.7 ◊ | [14/08/2026] Report has been approved by the Service Provider and shared with RECCo.
|  | 8. Annual assurance of RTS | Publication of Final Report (Restricted Distribution) | Planned | 2026-05-01: 14.8; 2026-06-01: 14.8; 2026-07-01: 14.8 ◊ | [14/08/2026] Report has been approved by the Service Provider and shared with RECCo.
15 | CRS Performance Charge | 1. Quarterly CRS Performance Charge calculation 2. Approval of 2026-27 CRS Performance Charge | Paper to PAB | Planned | 2025-11-01: 15.1 ◊; 2026-02-01: 15.1 ◊; 2026-03-01: 15.2 ◊; 2026-05-01: 15.1 ◊; 2026-08-01: 15.1 ◊
16 | Maintaining our Framework documents | 1. Retail Risk Register 2. Performance Assurance Methodology & Techniques 3. Performance Assurance Report Catalogue 4. PAB Procedures 5. REC Entry Assessment documents 6. REC Service User Categorisation | Publication of reviewed PAF product | Delivery in-progress | 2025-09-01: 16.1; 2025-10-01: 16.2, 16.3; 2025-11-01: 16.3, 16.5 ◊; 2026-01-01: 16.6; 2026-02-01: 16.6 ◊; 2026-06-01: 16.4 ◊
17 | Supporting other RECCo / REC Code Manager initiatives | 1. Helpdesk service and query management 2. Supporting REC Change Impact Assessment and Solution Development 3. Managing instances of issues and/or non-compliance 4. Supporting RECCo Operations, including with contract management and reporting 5. Committee management 6. Support Code Manager Collaboration | N/A | Delivery in-progress | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
Other reporting to PAB led by RECCo
18 | REC Service Security – confirming key security activities are taking place | Semi-annual update to PAB | Paper to PAB | Planned | bar: 2026-02-01; 2026-08-01
19 | IT capacity and performance management for REC Services – assessing how capacity requirements are identified and services planned for | Semi-annual update to PAB | Paper to PAB | Planned | [12 empty] | [17/08/2026] Complete, see paper RECPAB_26_0825_FORINFO02 - RECCo Service Provider IT Performance and Capacity Assessment. | bar: 2025-11-01; 2026-08-01
20 | CRS Improvement Plan – are benefits being realised? | Quarterly update to PAB, frequency to be reviewed based on PAB requirement | Paper to PAB | Planned | [12 empty] | [18/08/2026] This will be tracked as a PAB action for October. | bar: 2025-10-01; 2026-01-01; 2026-04-01; 2026-07-01
21 | Incident and Problem Management Deep Dive | Ad-hoc, event-driven update to PAB | Paper to PAB, if required. | Planned | 2025-09-01: As required
22 | Project to improve switching objection processes – to enhance consumer clarity earlier in the journey. | Covered as part of activity 4 above | - | Planned | 2025-09-01: Covered as part of activity 4 above
23 | Strategic focus on digitalisation of meter data – aligned with REC changes and major industry programmes. | Annual update to PAB | Paper to PAB | Planned | bar: 2026-01-01
24 | Use consumer data (I0189) to inform the Forward Work Plan and assess the impact of initiatives. | Annual update to PAB | Paper to PAB | Planned | bar: 2026-01-01
25 | Mechanism to respond to complex consumer issues outside the formal FWP structure. | Annual update to PAB | Paper to PAB | Planned | bar: 2026-01-01
26 | Leverage Digital Services rollout to improve assurance and market participant experiences. | Annual update to PAB | Paper to PAB | Planned | bar: 2026-01-01
Key: |  | Planned activities
Recurring activities
| ◊ | Output / deliverable due
Externally led activities
Completed activities