## Change Proposal Tracker - TEP
Change Proposal Reference | Change Proposal Title | Proposer Name | Proposer Company | Lead Analyst | Date Submitted | Change Category | Priority Status | Change Path | Responsible Committee | Proposed Implementation Date | Process Stage | Next Activity | Next Activity Due Date | On Track (RAG)
R0008 | Consequential New and Amended Market Messages for BSC Modification P375 | Gemma Dixon | Code Manager | Gemma Dixon | 2021-09-08 | 2 | High | Self-Governance | Technical Expert Panel | 2022-06-30 | Awaiting Implementation | Implementation | 2022-06-30
R0009 | Introduction of SDEP and EES User Maintenance API | Jonathan Holland | Code Manager | Jonathan Holland | 2021-09-08 | 2 | Low | Self-Governance | Technical Expert Panel | TBC | Impact Assessment | Service Provider IA initiated | 2022-03-04
R0011 | Reporting of additional EMR Backing Data to Suppliers | Gemma Dixon | Code Manager | Gemma Dixon | 2021-09-08 | 2 | Low | Self-Governance | Technical Expert Panel | 2022-11-04 | Awaiting Implementation | Implementation | 2022-11-04
R0022 | Amendment to REC Data Access Matrix | Harriet Truss | Code Manager | Harriet Truss | 2021-12-15 | 2 | Medium | Self-Governance | Technical Expert Panel | TBC | Initial Assessment | Change Panel review of IAR and CPP | 2022-02-15
R0024 | EAC information in the EES API | Andrew Long | Switchcraft | Jonathan Holland | 2021-12-10 | 2 | Low | Self-Governance | Technical Expert Panel | TBC | Initial Assessment | Change Panel review of IAR and CPP | 2022-02-15