## Change Proposal Tracker - TEP
Change Proposal Reference | Change Proposal Title | Link to CP page | Proposer Name | Proposer Company | Lead Analyst | Date Submitted | Change Category | Priority Status | Change Path | Responsible Committee | Proposed Implementation Date | Fuel | Impacted Parties | Process Stage | Next Activity | Next Activity Due Date | On Track (RAG)
R0009 | Introduction of SDEP and EES User Maintenance API | Link | Jonathan Holland | Code Manager | Jonathan Holland | 2021-09-08 | 2 | Low | Self-Governance | Technical Expert Panel | TBD | Elec and Gas | Energy Suppliers Distribution Network Operators Metering Equipment Managers EES Users | Preliminary Assessment | TEP review of PCR | 2022-09-28
R0010 | New Meter Types for Auxiliary Proportional Controllers (APCs) | Link | David Morton | EDF Energy | Jonathan Holland | 2021-09-08 | 1 | Low | Self-Governance | Technical Expert Panel | 2023-06-30 | Elec | Energy Suppliers Distribution Network Operators Metering Equipment Managers DCC Data Collectors EES Users Prepayment Meter Infrastructure Provider Meter Point Administration Service | Awaiting Implementation | Awaiting Implementation | 2022-11-04
R0011 | Reporting of additional EMR Backing Data to Suppliers | Link | Gemma Dixon | Code Manager | Gemma Dixon | 2021-09-08 | 2 | Low | Self-Governance | Technical Expert Panel | 2022-11-04 | Elec | Energy Suppliers | Awaiting Implementation | Implementation | 2023-06-30
R0052 | GES Service Definition Document | Link | Cristina Bermudez Alvarez | The Code Manager | George Barnes | 2022-06-13 | 2 | TBD | TBD | TBD | TBD | Gas | GES Provider Metering Equipment Managers Metering Asset Providers | Party Impact Assessment | Impact Assessment Closure | 2022-09-23
R0054 | EES Access for Virtual Lead Parties | Link | Ann Perry | The Code Manager | George Barnes | 2022-06-17 | 2 | Medium | Self-Governance | Technical Expert Panel | TBD | Elec | EES Provider, Virtual Lead Parties | Final Assessment | Final Change Report published | 2022-10-14
R0055 | Switching Operator Outage Notification Lead time | Link | Cordelia Grey | DCC | George Barnes | 2022-07-06 | 2 | Medium | Self-Governance | Technical Expert Panel | TBD | Elec | DCC GRDS Provider ERDS Providers EES Provider GES Provider | Initial Assessment | Preliminary Change Report published | 2022-10-14