## REC Issues
RIG Issues Log
Issue No. | Date of Submission | Summary of Issue | Other related RIG Issue(s) | Related REC Change(s) | Impacted REC Area(s) | Party Roles Impacted | Date of RIG at which initially reviewed | Comments and/or actions | RIG recommendation | Issue Status
2 | 2022-11-02 | Reintroduction of a scheme lock out date. | N/A |  |  | Electricity Supplier;Gas Supplier; | 2022-11-11 | 11/11/2021 Action: RIG Members to understand whether their organisation is also being affected by this issue and feed back to the Code Manager. Action: The Code Manager to investigate why the scheme lock out date wasn’t transitioned from the MRA to the REC. 09/12/2021 comment: RECCo confirmed that they are in the process of developing a Change Propsal that will include the reintroduction of the scheme lock out date - target implementation date April 2023 | Code Manager to monitor the RECCo CP to ensure that scheme lock out date is included - once CP raised issue can be closed | LIVE
3 | 2022-11-02 | A list of gas non-dom suppliers that use SAR and RET flows was previously available under SPAA, however since the transition to REC the information is no longer available. This means we do not know who to send a flow to and who to send an email to. | N/A |  |  | Gas Supplier; | 2022-11-11 | 11/11/2021 Action: Code Manager to investigate as to whether this list is maintained elsewhere and to support the raising Party to progress this to a REC CP, which can include potential solutions. 09/12/2021 update: Current SAR process sits with ICOSS although is not actively maintained, suggested that a CP could be developed to move this into the REC. Code manager to work with issue raiser on options. | Agreement that this should be progressed to a Change Proposal, which can include potential solutions | LIVE
4 | 2022-11-03 | ET cancellations used to be done before post SSD when a switch cancellation had not be done on time or was not successful. Post SSD what is the general view of suppliers. Should we still be raising them or not,. For example some suppliers are raising them as the customer has changed their mind during the cooling off period, but is after SSD, I am not sure if this is being done for completeness to show it has been transferred back, I am assuming technically it is not needed. and it may still be habit for raising them, but then it falls into the ET GSOP process, when its not technically a valid ET, or is it acceptable to not apply GSOP to this, but some would be genuine where not cancelled in time. Would like some clarity on how these should be treated now | N/A |  |  | Electricity Supplier;Gas Supplier; | 2022-11-11 | 11/11/2021 Action: RIG Members agreed to understand if this was affecting their organisations and feedback at the next meeting. Action: Code Manager to add ET escalation process to the issues list of the next RIG meeting. 09/12/2022 Update: no feedback recieved from RIG members, agreed to keep this issue open for one further meeting |  | LIVE
5 | 2022-04-11 | CP seeks to address the following issues regarding the UTR files - 1. There is no REC requirement for PPMIPs to submit a monthly file to the Code Manager, 2. PPMIPs are currently submitting files in two differnet file formats, 3. C&C is only able to load one of the two file formats | N/A |  |  | PPMIP/Suppliers | 2022-11-11 |  | Change proposal to be progressed by the proposer. | Closed
6 | 2022-11-07 | The REC Code Manager is developing a change proposal that, if progressed, may impact this area of the code (Schedule 23 - Registration services). To help us understand how this process works in practice, we would appreciate help from Parties | N/A | R0051 | The REC Schedule 23 - Registration Services | Electricity Supplier;Gas Supplier; | 2022-11-11 | Action: RIG Members to provide feedback and examples of best practice to the change team to support CP0051. | CP 051 is now raised and going through the change process - parties are still able to provide feedback to the change through the consultation stage | Closed
7 | 25/11/2022 | EES API Specification - We believe the information in section 11 of the specification (GetRelatedMPANs) needs to be expanded to provided. Also looking at the specification, it looks like if a Secondary MPAN has been removed from a relationship this will still appear in the API response again this should be covered in the spec. more details of what will be provided in the response around deleted and amended relationships. This is because if you search for an MPAN that was previously in a deleted relationship and now in the same one again the API response returns both sets of data. Given the purpose of using the API is to get the latest data we queried if this was corrected with C&C and they said yes, therefore we think this should be documented in the spec along with details of how this can be identified. | N/A |  | REC Performance Assurance | Supplier | 2022-09-12 | 09/12/2022 Action: Code Maager to investigate whether EES API is providing the correct response and whether the data specification reflects this |  | LIVE

## Data Cleanse issues
Data cleanse Issues
Issue No. | Date of Submission | Summary of Issue | Other related RIG Issue(s) | Related REC Change(s) | Impacted REC Area(s) | Party Roles Impacted | Date of RIG at which initially reviewed | Comments and/or actions | RIG recommendation | Issue Status
DC1 | 2022-11-09 | Proposal to split the NoMeterMTC Report into two sub-reports | N/A |  | REC Performance Assurance | Supplier | 2022-11-11 | 11/11/2022 Action: The Code Manager will investigate the most appropriate REC change process to be followed for this issue to be progressed. 09/12/2022 update: Code Manager confirmed that the reporting specs will be classified as category 3 documents, so that the change process can be followed. |  | LIVE
DC2 | 2022-11-09 | The Domestic Premise Indicator is required to reflect whether the MPAN is determined by the Supplier to be a Domestic or Non-Domestic premises. The Supplier has an obligation to set the indicator correctly. Initially populate the Domestic Premises Indicator using existing industry data. The basis described in the Ofgem CP related to metered MPANs (as per BSCP516), unfortunately it was not recognised that NHH Unmetered MPANs are governed under BSCP520 rather than BSCP516. | N/A |  | REC Performance Assurance | Supplier | 2022-11-11 | 11/11/2022 Action: Suppliers to update/correct the DPI directly into the Central CSS. This data will then be replicated in other systems including EES. Action: Parties to provide feedback as to whether the use of the DPI is a concern across the board. Action: Code Manager to investigate these rules and to consider whether any reporting is required to monitor this, for example whether a single data offload of MPANs having a DPI would be sufficient, or if a more enduring process is needed. 09/12/2022 update: Code Manager continues to investigate most appropriate data provision approach |  | LIVE
DC3 | 25/11/2022 | PLOT address amendments - Looking through the plot address amendments we have found that we have EV lamppost charging points listed. The charging points do not have a Post office address. What is the best course of action to get these resolved or removed from the report. | N/A |  | REC Performance Assurance | Electricity Supplier;Gas Supplier; | 2022-09-12 | 09/12/2022 action: RIG parties to provide examples. |  | LIVE
DC4 | 2022-12-16 | Request from two Parties for exemptions to go back to being included in the individual supplier reports | N/A |  | REC Performance Assurance | Electricity Supplier;Gas Supplier; | 2023-01-13 |  |  | LIVE
DC5 | 2022-12-16 | New qualitative exemption scenario requests: Multiple unrestricted meters with same address do not need to be in a relationshop or have related MTCs. MPANs in valid relationship, yet addreses do not match as they serve as identifiers | N/A |  | REC Performance Assurance | Electricity Supplier;Gas Supplier; | 2023-01-13 |  |  | LIVE
DC6 | 2022-06-01 | Managing discrepancy between supplier for relationship and registered supplier for MPAN for active relationship reports | N/A |  | REC Performance Assurance | Electricity Supplier;Gas Supplier; | 2023-01-13 |  |  | LIVE

## _56F9DC9755BA473782653E2940F9 (hidden)
wLs9iDSjVEuHzwT6lK6vuIsTg8IU4_9Ev834X1fhCSRUNDkxQk0zRllQU1BYQTJaSUhSM0YxVkdUSyQlQCN0PWcu
Form1
{f9c668d3-36bc-42ca-ad01-3da2dbdf3e2f}