## REC Issues
Issue No. | Date of Submission | Summary of Issue | Other related RIG Issue(s) | Related REC Change(s) | Impacted REC Area(s) | Party Roles Impacted | Date of RIG at which initially reviewed | Comments and/or actions | RIG recommendation | Issue Status
2 | 2022-11-02 | Reintroduction of a scheme lock out date. | N/A |  |  | Electricity Supplier;Gas Supplier; | 2022-11-11 | 11/11/2021 Action: RIG Members to understand whether their organisation is also being affected by this issue and feed back to the Code Manager. Action: The Code Manager to investigate why the scheme lock out date wasn’t transitioned from the MRA to the REC. 09/12/2021 comment: RECCo confirmed that they are in the process of developing a Change Propsal that will include the reintroduction of the scheme lock out date - target implementation date April 2023 | Code Manager to monitor the RECCo CP to ensure that scheme lock out date is included - once CP raised issue can be closed 10/02/2023 - CP0091 has been raised | CLOSED
3 | 2022-11-02 | A list of gas non-dom suppliers that use SAR and RET flows was previously available under SPAA, however since the transition to REC the information is no longer available. This means we do not know who to send a flow to and who to send an email to. | N/A |  |  | Gas Supplier; | 2022-11-11 | 11/11/2021 Action: Code Manager to investigate as to whether this list is maintained elsewhere and to support the raising Party to progress this to a REC CP, which can include potential solutions. 09/12/2021 update: Current SAR process sits with ICOSS although is not actively maintained, suggested that a CP could be developed to move this into the REC. Code manager to work with issue raiser on options. 13/01/2023 - A CP will be considered to bring this under the REC. No timescales were given for the draft of this Change Proposal, the Code Manager will work with the issue raiser on this. | Agreement that this should be progressed to a Change Proposal, which can include potential solutions | CLOSED
4 | 2022-11-03 | ET cancellations used to be done before post SSD when a switch cancellation had not be done on time or was not successful. Post SSD what is the general view of suppliers. Should we still be raising them or not,. For example some suppliers are raising them as the customer has changed their mind during the cooling off period, but is after SSD, I am not sure if this is being done for completeness to show it has been transferred back, I am assuming technically it is not needed. and it may still be habit for raising them, but then it falls into the ET GSOP process, when its not technically a valid ET, or is it acceptable to not apply GSOP to this, but some would be genuine where not cancelled in time. Would like some clarity on how these should be treated now | N/A |  |  | Electricity Supplier;Gas Supplier; | 2022-11-11 | 11/11/2021 Action: RIG Members agreed to understand if this was affecting their organisations and feedback at the next meeting. Action: Code Manager to add ET escalation process to the issues list of the next RIG meeting. 09/12/2022 Update: no feedback recieved from RIG members, agreed to keep this issue open for one further meeting | 13/01/2023 - no further feedback received at the January'23 RIG. Issue can be closed. | CLOSED
5 | 2022-04-11 | CP seeks to address the following issues regarding the UTR files - 1. There is no REC requirement for PPMIPs to submit a monthly file to the Code Manager, 2. PPMIPs are currently submitting files in two differnet file formats, 3. C&C is only able to load one of the two file formats | N/A |  |  | PPMIP/Suppliers | 2022-11-11 |  | Change proposal to be progressed by the proposer. | CLOSED
6 | 2022-11-07 | The REC Code Manager is developing a change proposal that, if progressed, may impact this area of the code (Schedule 23 - Registration services). To help us understand how this process works in practice, we would appreciate help from Parties | N/A | R0051 | The REC Schedule 23 - Registration Services | Electricity Supplier;Gas Supplier; | 2022-11-11 | Action: RIG Members to provide feedback and examples of best practice to the change team to support CP0051. | CP 051 is now raised and going through the change process - parties are still able to provide feedback to the change through the consultation stage | CLOSED
7 | 25/11/2022 | EES API Specification - We believe the information in section 11 of the specification (GetRelatedMPANs) needs to be expanded to provided. Also looking at the specification, it looks like if a Secondary MPAN has been removed from a relationship this will still appear in the API response again this should be covered in the spec. more details of what will be provided in the response around deleted and amended relationships. This is because if you search for an MPAN that was previously in a deleted relationship and now in the same one again the API response returns both sets of data. Given the purpose of using the API is to get the latest data we queried if this was corrected with C&C and they said yes, therefore we think this should be documented in the spec along with details of how this can be identified. | N/A |  | REC Performance Assurance | Supplier | 2022-09-12 | 09/12/2022 Action: Code Manager to investigate whether EES API is providing the correct response and whether the data specification reflects this | 13/10/2023 - service provider agreed that the definition could be made clearer. Code manager to work with service provider on this | CLOSED
8 | 2023-01-13 | Shipper and Supplier access to data in GES was separated at RECV.3 go-live. Some REC Parties believe that Suppliers and Shippers should have the same view, specifically highlighting the data items relating to meter read history (MRH). |  | R0047 | REC Service Providers and Data Access Matrix | Supplier | 2023-01-13 | 13/01/23 Action: RIG representatives to assess whether they have identified a need for the additional data items in GES (or note if they are missing them) and provide the REC with some user case scenarios that could inform the development of a CP. | 10/02/2023 - parties advised to raise instances of missing data items with their OAM who can feed into the change team | CLOSED
9 | 2023-01-06 | DNO B Code Escalations - Where B code timeframes have exceeded 41 working days is there a way to please escalate to the DNO? We will re-issue the D135 to receive a D126 reply stating, duplicate job but no outcome / update of the request that was raised. | N/A | N/A |  | Supplier/DNO | 2023-02-10 | 13/10/2023 - Raising party advised to look at DCUSA website. Code manager to assess whether the REC can signpost | 10/03/2023 - RIG members agreed that this issue could be closed | CLOSED
10 | 2023-01-24 | R0021 - Allowing MEMs to de-energise and re-energise supply points independent of the Supplier - issues with drafting | N/A | R0021 |  | MEM/Supplier | 2023-02-10 | 13/10/2023 - code manager to ensure that the Change webinar goes ahead and that this issue is covered | 17/02/2023 - webinar to be held 02/03/2023 | CLOSED
11 | 2023-02-22 | Registrations failing due to domestic/non-domestic indicator not matching | N/A |  |  | Supplier | 2023-03-10 |  | 10/03/2023 - Code Manager to investigate the DPI issue and send guidance to the Issue raiser. 12/04/2023 - Party confirmed that this issue can now be closed | CLOSED
12 | 2023-04-05 | Erroneous Switching Process - Use of the 'annulment' process to handle Erroneous switching causing concern that processes are not being followed correctly | N/A |  |  | Supplier | 2023-04-14 | 14/04/2023 - RIG members to discuss issues within their own organisations to understand how this process is managed. Code Manager to work with the change team to understand whether R0030 impacts this |  | LIVE
13 | 2023-04-05 | SDEP queries - increase in instances of queries being raised against incorrect MPIDs (ie. Domestic Query being raised to non-domestic MPID) | N/A |  |  | Supplier | 2023-04-14 | 14/04/2023 - Code Manager confirmed that SDEP changes are part of the Code Roadmap. The Code Manager will report back to the May RIG with an update |  | LIVE
14 | 2023-04-13 | Issues with communicating with 'white-label' suppliers. Escalation routes are not able to be followed | N/A |  |  | Supplier | 2023-04-14 | 14/04/2023 - Code Manager to liase with issue raise to discuss next steps |  | LIVE

## Data Cleanse issues
Data cleanse Issues
Issue No. | Date of Submission | Summary of Issue | Other related RIG Issue(s) | Related REC Change(s) | Impacted REC Area(s) | Party Roles Impacted | Date of RIG at which initially reviewed | Comments and/or actions | RIG recommendation | Issue Status
DC1 | 2022-11-09 | Proposal to split the NoMeterMTC Report into two sub-reports | N/A |  | REC Performance Assurance | Supplier | 2022-11-11 | 11/11/2022 Action: The Code Manager will investigate the most appropriate REC change process to be followed for this issue to be progressed. 09/12/2022 update: Code Manager confirmed that the reporting specs will be classified as category 3 documents, so that the change process can be followed. | 13/01/23 - CP in the process of being drafted to address this issue 23/01/2023 - CP R0019 raised 23/01/2023. Captured in Change C3-40032 | CLOSED
DC2 | 2022-11-09 | The Domestic Premise Indicator is required to reflect whether the MPAN is determined by the Supplier to be a Domestic or Non-Domestic premises. The Supplier has an obligation to set the indicator correctly. Initially populate the Domestic Premises Indicator using existing industry data. The basis described in the Ofgem CP related to metered MPANs (as per BSCP516), unfortunately it was not recognised that NHH Unmetered MPANs are governed under BSCP520 rather than BSCP516. | N/A |  | REC Performance Assurance | Supplier | 2022-11-11 | 11/11/2022 Action: Suppliers to update/correct the DPI directly into the Central CSS. This data will then be replicated in other systems including EES. Action: Parties to provide feedback as to whether the use of the DPI is a concern across the board. Action: Code Manager to investigate these rules and to consider whether any reporting is required to monitor this, for example whether a single data offload of MPANs having a DPI would be sufficient, or if a more enduring process is needed. 09/12/2022 update: Code Manager continues to investigate most appropriate data provision approach | Captured in Change C3-40032 | CLOSED
DC3 | 25/11/2022 | PLOT address amendments - Looking through the plot address amendments we have found that we have EV lamppost charging points listed. The charging points do not have a Post office address. What is the best course of action to get these resolved or removed from the report. | N/A |  | REC Performance Assurance | Electricity Supplier;Gas Supplier; | 2022-09-12 | 09/12/2022 action: RIG parties to provide examples. 13/01/2023: Code Manager is working with the DCC to seek guidance on this issue. | 10/03/2023 - group agreed that issue could be closed | CLOSED
DC4 | 2022-12-16 | Request from two Parties for exemptions to go back to being included in the individual supplier reports | N/A |  | REC Performance Assurance | Electricity Supplier;Gas Supplier; | 2023-01-13 |  | 13/01/23 - CP in the process of being drafted to address this issue . Captured in Change C3-40032 | CLOSED
DC5 | 2022-12-16 | MPANs in valid relationship, yet addreses do not match as they serve as identifiers | N/A |  | REC Performance Assurance | Electricity Supplier;Gas Supplier; | 2023-01-13 | 13/01/2023 - Suggested that the status quo for using the exemption process for these sites be maintained with the existing wording being amended rather than a new exemption code being created | 10/02/2023 - RIG parties agreed that E3 is the correct exemption code to be used in this situation. Description to be amended to make it clearer. | CLOSED
DC6 | 2022-06-01 | Managing discrepancy between supplier for relationship and registered supplier for MPAN for active relationship reports | N/A |  | REC Performance Assurance | Electricity Supplier;Gas Supplier; | 2023-01-13 | 13/01/2023 - The Code Manager agreed to investigate whether this scenario is an edge case or a wider issue | 10/02/2023 - Code Manager confirmed that they will make a change to the Disconnected MPANs/Active Realtionshop Logic to correct the issue | CLOSED
DC7 | 2023-01-27 | Correct MAP ID on systems but being flagged as 'invalid' in data cleanse report | N/A |  | REC Performance Assurance | Electricity Supplier;Gas Supplier; | 2023-02-10 | 10/01/2023 - more information needed | 10/03/2023 - agreed to close and for party to raise as a Service Desk Ticket | CLOSED
DC8 | 2023-04-14 | Concern raised over incorrect MAP IDs being included in data cleanse reports |  |  |  |  | 2023-04-14 | 14/04/2023 - Code Manager to reach out to MAPs to seek potential support in helping to resolve the issues |  | OPEN

## _56F9DC9755BA473782653E2940F9 (hidden)
wLs9iDSjVEuHzwT6lK6vuIsTg8IU4_9Ev834X1fhCSRUNDkxQk0zRllQU1BYQTJaSUhSM0YxVkdUSyQlQCN0PWcu
Form1
{f9c668d3-36bc-42ca-ad01-3da2dbdf3e2f}