## Sheet1
Reference | Describe what happened? | What was the impact? | Action items | Who can support and/or input into this issue? | Part of the REC Change Issue | Theme | Expected Meeting and Date of Discussion
SoLR.01 | The REC sets out that access is revoked to all services promptly. This resulted in Rebel Energy staff from no longer being able to access EES and SDEP. | This prevented Rebel staff from helping to work to progress the switch away from British Gas. | Consideration of moving the MAU to the SoLR so that they can decide who can retain access. |  | Yes | System Access | 29.01.2026 - Meeting 2
SoLR.02 | Increased focused on the deadline of all MPANs being switched within the schedule deadline of 5 days; however, as the ownership of the MPID had been transferred to BG, this was not a priority for anyone else. | Confusion and frustration for British Gas, lack of clarity on the requirements and expectations. | Consider whether the Schedule timetable should be updated to allow for a longer duration in this scenario. |  | Yes | Code-defined process | 29.01.2026 - Meeting 2
SoLR.03 | SDEP proforma process for the Gaining Supplier was not clear and not triggered correctly. | Delay in understanding of, and transfer of Consumer related issues and data fixes. | The SDEP proforma process should be completed to confirm the approach regarding current messages, archived messages, and user accounts. While we would not typically recommend user deletions, we are happy to support the incoming Supplier’s preferred approach. Confirm who is responsible to Action Proforma completion. |  | Yes | System Access | 29.01.2026 - Meeting 2
SoLR.04 | Relianced placed on communications with exiting Supplier to facilitate MPAN movements. | Expectation that losing Supplier would be available to support MPAN moves by both replacement supplier and Code Manager teams. Worked to a point in this scenario, but we should not place reliance on this being available. | Agree processes that exclude the reliance on the failing Supplier especially as at this point they are not a REC Party or licenced Energy Supplier. |  | Yes | Code-defined process | 29.01.2026 - Meeting 2
SoLR.05 | Approach of administrator unknown/not consistant so should not be relied on. | History has shown that each administrator acts differently, some close the business immendiately, others have retained key staff. Inconsistent approach may cause difficulties for Supplier operations that could create increased Consumer detriment. | Identify any potential risks to be addressed around Supplier communications, staffing, and billing. Are there any other risks that should be considered? |  | Yes | Code-defined process | 29.01.2026 - Meeting 2
SoLR.06 | Lack of guidance on best practice for all Parties/organisations involved during the SoLR process. | Replacement Supplier not getting what they need in terms of transfer reads, final bills etc. | Create and share 'best practice' document for Suppliers, adminstrators, DNOs,GTs etc Advising on areas where alignment could support better Consumer outcomes. |  | Yes | Supporting documentation | 29.01.2026 - Meeting 2
SoLR.07 | Lack of understanding over impact of change of MPID owner in EES. | No history when MPID moves, so replacement Supplier shown as responsible for MPID for all history. Creates difficulty for replacement supplier when being asked to resolve historic queries, especially via SDEP. | Consider benefit of a system change to note ownership dates for MPIDs. |  | Yes | Code-defined process | 29.01.2026 - Meeting 2
SoLR.08 | Existing SDEP cases for exiting Supplier are all lost. | All other REC Parties who have existing SDEP cases on MPID at time of SoLR, have SDEP cases fail. It has been unclear if this impacts their reporting, too. | Can these SDEP cases be migrated from existing Supplier to Gaining Supplier, or should all these SDEP cases be ceased and removed from other REC Parties reporting? Might it be possible to provide a data dump of the pre-existing SDEP queries to the failed Supplier and the Administrators? |  | Yes | Code-defined process | 29.01.2026 - Meeting 2
SoLR.09 | No tracking of Export MPxN's for exiting Supplier or awareness through reporting for Gaining Supplier? | No Export MPxN's are considered under a SoLR, or if they are, is there a way to quickly identify them? | Does reporting have a way of identifying Export MPxN's and should they be clearly identified so that they can be treated in the correct way? Latest data cleanse reports for the Failed Supplier could be handed over to the Replacement Supplier. |  | Yes | Data and Reporting | 29.01.2026 - Meeting 2
SoLR.10 | Failed Supplier could have multiple new MPAN requests sat with DNOs. | Unregistered MPANs sat in Industry, Consumers unable to sign up to SEG and other schemes. | Update RMP Lifecycle schedule to include SoLR process for these requests. Could REC communication channels be used to engage with DNOs for this information? |  | Yes | Code-defined process | 29.01.2026 - Meeting 2
SoLR.11 | British Gas were expecting to source the electricity meter point data from the EES, but in a way that is not currently supported (schedule defines that it is sourced from DNO). | British Gas did not have immediate access to specific meter point data that would have allowed them to allocate MPANs to specific MPIDs (e.g. small businesses to a dedicated MPID). This was resolved through adhoc reports from C&C as the EES Service Provider. | Reinstate previous CR supporting this approach (now CR91). |  | Yes | Data and Reporting | 12.03.2026 - Meeting 3
SoLR.12 | Energy Suppliers may not want to use DNO data for initial handover. | CR91 was needing to be created retrospectivly. | Need to understand if the supposed "DNO Data" is fit for purpose and the right method for initial data handover. Could this be sourced centrally from EES / GES / CSS? |  | Yes | Data and Reporting | 12.03.2026 - Meeting 3
SoLR.13 | Tracking all activities within the schedule was not always straightforward, especially items that are not under Code Manager/RECCo control | Having no direct contact with the DNOs means that Energy Suppliers issues relating to DNO data can be slower to resolve. | Consider implementing a mechanism for all Parties to update progress Update process to get the data from EES/GES/CSS instead. |  | Yes | Data and Reporting | 12.03.2026 - Meeting 3
SoLR.14 | Lack of consistency between Ofgem portfolio data provided at point of SoLR and 'real' data available from Enquiry Services. | Replacement Supplier noting inconsistencies in numbers leading to delay in provision of plan and potentially the start of transfers, concerns around numbers of domestic vs non domestic, PPMIP etc. | Enquiry Service Service Provider reporting delivered on day zero and then periodically in line with the SoLR migration plan. |  | Yes | Data and Reporting | 12.03.2026 - Meeting 3
SoLR.15 | Schedule 19, 5.8.12, requires DNOs to send Meter point to replacement Supplier | No understanding of requirement by DNOs and no clarity whether this was delivered to Replacement Supplier. | Consider raising awareness of requirement with DNOs, and allowing data to be shared with the Code Manager at point of delivery to Replacement Supplier (this would become redundant with the provision of centrally generated reporting). |  | Yes | Data and Reporting | 12.03.2026 - Meeting 3
SoLR.16 | Lack of consistency between data available and frequency of delivery. | GES reporting is available immediately and delivered on request. EES data was not readily available. Lack of clarity of portfolio size and lack of visibility of progress for Replacement Supplier and Code Manager | Define consistent 'SoLR reporting' for each enquiry service, defining data items, delivery frequency and duration following a SoLR event - delivery costs should be reduced as the basis for the reports now exists . |  | Yes | Data and Reporting | 12.03.2026 - Meeting 3
SoLR.17 | Unallocated Transaction for Prepayment - clarity on who is responsible for what, when? | Understanding is required on the Unallocated Transaction for Prepayment and how this may be impacted by any SoLR cases. | Explore if the Unallocated Transaction Payments can be included in any potential change raised, to confirm in a SoLR process who is responsible for what, and any applicable timescales. |  | Yes | Data and Reporting | 12.03.2026 - Meeting 3
SoLR.18 | Payment Method Levelisation (PML) considerations should be added to the SoLR process. | On the first day of the month following the appointment of the SoLR, access rights within the PML systems should be updated to allow the replacement Supplier to submit portfolio data for the codes relating to the failed Supplier. This should only be activated on the first day of the month, as this is the first date on which the replacement Supplier is responsible for the PML portfolio snapshot. | Consider if the PML, as a Market Scheme, should be added to the process? If yes, consider the previous impact and the timescales associated with the process. |  | TBC | Data and Reporting | 12.03.2026 - Meeting 3
SoLR.19 | Confusion around which portfolio data will be used in the event of a non-submission following a SoLR event (with regards to the standard non-submission process) | Clarifying which portfolio data set will be used in a non‑submission scenario ensures there is a consistent and predictable fallback during a SoLR event, avoiding disputes between parties. This reduces delay and stabilises settlement by ensuring the Replacement Supplier inherits a clear and uncontested portfolio position. | Clarifying what set of portfolio data will be used in the event of a non-submission following a SoLR event (signpost to standard non-submission process). |  | Yes | Payments | 29.01.2026 - Meeting 2
SoLR.20 | It is not clear at what point in time the replacement Supplier assumes responsibility of 1) portfolio submission, 2) invoice payment, 3) credit receipt. There is currently no natural place in Schedule 31 for this. | The lack of a clearly defined transfer point in Schedule 31 creates ambiguity over when the Replacement Supplier becomes responsible for portfolio submissions, invoice payments, and credit receipts, leading to potential billing errors, disputes, and operational inconsistencies | Clarifying at what point in time the replacement supplier assumes responsibility of 1) portfolio submission, 2) invoice payment, 3) credit receipt. There is currently no natural place in Schedule 31 for this, and may require a new section within the legal drafting of the Code. |  | Yes | Payments | 29.01.2026 - Meeting 2
SoLR.21 | The standard non-payment process will apply when/if the collapsed Supplier does not pay their invoice. | The standard non‑payment process being applied to a collapsed Supplier means any unpaid invoices trigger debt recovery steps, which can slow or complicate the financial handover in a Supplier of Last Resort event. | Clarify and determine how any late payment by administrators would feed back into the scheme (referral to standard non-payment/late payment process). |  | Yes | Payments | 29.01.2026 - Meeting 2
SoLR.22 | Any credits due to the collapsed Supplier can be withheld if they owe money to the scheme (standard non-payment process). | Withholding credits owed to a collapsed Supplier can leave unrecovered debt in the scheme, increasing the financial burden that must be socialised across the market during a Supplier of Last Resort event. This raises the costs and credit exposure passed to the Replacement Supplier and ultimately complicates the SOLR onboarding and stabilisation process. | Provide clarity that any credits due to the collapsed supplier can be withheld if they owe money to the scheme (refer to standard non-payment process). |  | Yes | Payments | 29.01.2026 - Meeting 2