This document is classified as WHITE. Information is for public, unrestricted dissemination and publication.

Theft Issues Group

risks, ASSUMPTIONS, issues AND DEPENDENCIES

| No. | RISK | NOTES | MITIGATION |
| --- | --- | --- | --- |
| R01 | There is a risk that the perception that the investigation of theft is not commercially viable continues and that some organisations may only complete the bare minimum to meet obligations. |  |  |
| R02 | There is a risk of potential damage to reputation including individual Parties, RECCo/Code Manager and industry as a whole. |  |  |
| R03 | There is a risk that if the industry cannot agree on a scheme, albeit an imperfect one, a new scheme will never be introduced, and any potential benefits will never be realised. |  |  |
| R04 | There is a risk that a newly introduced scheme could drive unwanted behaviour or result in unintended consequences. |  |  |
| R05 | There is a risk of consequences for Network partners if Suppliers don’t address issues. | This can have an unintended consequence for costs on Network parties. |  |
| R06 | There is a risk of resource capacity constraints where an increase in theft detections and remedial works are required. |  |  |
| R07 | There is a risk that certain types of theft are not effectively and appropriately investigated to the required volumes as they are more difficult to identify. |  |  |
| R08 | There is a risk that the savvier and more knowledgeable base of perpetrators including rogue traders become increasingly ahead of industry. |  |  |

| No. | ASSUMPTION | NOTES | HOW/WHEN TO VALIDATE |
| --- | --- | --- | --- |
| A01 | There is an assumption that the TIG and any subsequent Change Proposals will work to overcome identified disincentives. | Certain Suppliers see theft as a cost and any future Change Proposals need to remove the negatives for finding theft. There needs to be a benefit for proactively working to decrease theft. |  |
| A02 | There is an assumption that any Change Proposals will not require any Licence or cross-code changes. |  | This will be validated following an agreement on the scope of any future Change Proposals. |
| A03 | There is an assumption that any future changes will work to drive the correct behaviour. | The TIG will work to ensure that solutions promote the following. - All theft requires the same level of investigation. - Safety should be more important than profit. - Safety should be the priority and at the forefront of all incentives. |  |
| A04 | There is an assumption that any costs associated with the detection or non-detection of theft is funded through industry and therefore Consumers. | The industry must be seen to spend Consumer funds wisely. |  |
| A05 | There is an assumption that any future scheme would be simple to administer both for the REC Code Manager and Parties. |  |  |
| A06 | There is an assumption that any future incentive scheme would appropriately socialise costs and allow the appropriate cost recovery. |  |  |
| A07 | There is an assumption that any future solutions would operate within the original principles of what TDIS intended to achieve. |  |  |
| A08 | There is an assumption that any future solution would reward and value good practice on safety. |  |  |
| A09 | There is an assumption that billing fraud will be confirmed as in or out of scope of TIG. |  |  |
| A10 | There is an assumption that consideration will be given on how to incentivise/reward activity that identifies theft actions like rogue traders/electricians. |  |  |

| No. | ISSUE | NOTES | HOW TO PROGRESS |
| --- | --- | --- | --- |
| I01 | TDIS - short term | This may entail small incremental improvements to the way the current scheme is administered. | To be discussed at May TIG. |
| I02 | TDIS – medium term or long term | Change within TDIS or entirely different incentive scheme/replacement. |  |
| I03 | Revenue Protection Service | Early thoughts: - Create minimum standard of investigation in market. Are the standards fit for purpose? - Confirmation on whether all Parties are required to utilise the service or provide it themselves - available to all but not needed to be used by all. - Consistent centralised point of theft. - Collate information/leads/confirmations from different organisations – better data to identify trends. - Allows Parties who have isolated and sporadic theft incidents to have ready resource to access. - Confirmation on whether this will be National or Regional. |  |
| I04 | Reasonable Endeavours | Early thoughts: - Confirmation on whether the current scheme under GT Licence could be scaled up again. - Confirmation on whether this would be focussed on Suppliers and adapted to be dual-fuel. - Confirmation on whether this would run alongside a TDIS Scheme. |  |
| I05 | Review of minimum standards | Early thoughts: - Review of Unbilled Energy Code of Practice. - Create clear guidance of expectations e.g. job card template. - If processes are in the same format, this will make it easier to move into a centralised function. |  |

| No. | DEPENDENCY | NOTES | STATUS |
| --- | --- | --- | --- |